NIGHTWATCH OBSERVATORY

Telescope Mount & Roll-off 'Turret'
Fabrication Tender / Request for Quotation

ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Rev A · dimensions dual-unit (mm [inch]) · generated from the proven design (design/mechanical/calc/params.py)

# Part I — Master Tender Dossier (BP-00)

# NIGHTWATCH Observatory — Master Tender Dossier (BP-00)

ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Document set: BP-00 (umbrella). Rev A. Units: mm primary, [inch] in brackets.

Technical Data Package structured per MIL-STD-31000A.

---

This dossier is the umbrella over five bid packages (BP-01 … BP-05) that together

build the NIGHTWATCH telescope mount and its roll-off roof enclosure. The mechanical

engineering is proven out and frozen (see design/mechanical/MECHANICAL_DESIGN.md);

this dossier and its child packages are the procurement documents that let a shop

price and fabricate the work. Every controlling dimension quoted anywhere in the

dossier is pulled from the parts registry design/mechanical/tender/gen/partspec.py

and the generated Bill of Materials — no dimension is invented here.

## 1. Package index

| Pkg | Title | Trade | Line items | Fab drawings | Key vendor deliverables |
| --- | --- | --- | --- | --- | --- |
| BP-01 | Mount head machining | CNC machining, 6061-T6 aluminium | 3 | 3 | 3× machined housings/bar, Type III hardcoat anodize, CMM report on H7 bores, material certs |
| BP-02 | Precision turned parts | CNC / manual turning, 303 stainless | 3 | 3 | 3× turned spindles/shaft, passivation cert, concentricity report, material certs |
| BP-03 | Pier & foundation | Reinforced concrete + structural steel | 4 | 3 | Cast-in-place RC pier, galvanized top plate, anodized adapter plate, cast-in anchor set + template. PE stamp + concrete cylinder breaks required |
| BP-04 | Roll-off roof ("disappearing turret") | Structural steel fab + rail/drive install | 6 | 6 | Welded HSS roof frame, rafters/purlins, box-track rails, wheel/drive/hold-down brackets, hot-dip galvanized. AWS D1.1 WPS/PQR + welder quals required |
| BP-05 | COTS procurement schedule | Purchase (buy-to-print / off-the-shelf) | 14 | 0 | Harmonic drives, angular-contact bearings, on-axis encoders, motors/drivers, focuser, wheels, roof drive, roofing, 48 V power pack, fasteners, anchor set |

Line-item and fabricated-drawing counts above are the current registry output

(python3 -m design.mechanical.tender.gen.partspec). Total across the job:

30 registry line items, 15 fabricated control drawings (BP-05 and the

anchor set NW-PF-004 are buy items and carry no fabrication drawing).

## 2. BID IN PARTS OR WHOLE

A vendor may bid **any single package, any combination of packages, or the whole

job.** There is no requirement to bid the complete scope.

Single-trade shops — a machine shop may bid BP-01 and/or BP-02 alone; a steel

fabricator may bid BP-04 alone; a concrete/foundation contractor may bid BP-03

alone; a distributor may quote BP-05 alone.

Line-item bidding — within a package a bidder may price individual NW-xx line

items. The pricing schedule (05_bid_form.md) has one row per line item plus a

per-package subtotal and a whole-job total, so partial bids are first-class.

Whole-job bidding — a general/turnkey bidder prices every package plus the

integration/install scope and submits the whole-job total.

Interfaces stay the owner's risk to coordinate. Mating features are held on the

drawings by shared bolt patterns and registers (e.g. NW-MH-001 flange ↔ NW-TP-002

register; NW-PF-002 ↔ NW-PF-003 hole pattern; NW-RR-004 bracket ↔ NW-CO-010

wheel). A partial bidder is responsible only for their own package's conformance to

the published dimensions and datums; the owner coordinates cross-package fit.

Award may be made by package, so price each package to stand alone.

## 3. Part-numbering scheme (NW-xx)

Every fabricated or purchased item carries a stable part number of the form

NW-<TT>-<NNN>:

| Field | Meaning |
| --- | --- |
| NW | Project prefix — NIGHTWATCH |
| TT | Trade/type code: MH = mount-head machined, TP = turned part, PF = pier/foundation, RR = roll-off roof, CO = commercial off-the-shelf |
| NNN | Sequential item within the trade (001, 002, …) |

The trade code maps one-to-one onto the bid package: MH→BP-01, TP→BP-02, PF→BP-03,

RR→BP-04, CO→BP-05. A part number never changes across revisions; the sheet revision

(Rev A at issue) tracks changes. Control drawings are named NW-<TT>-<NNN>.svg

(PDF at issue) and match the part number exactly.

## 4. File-format map (which trade gets what)

The 3-D machining master for every fabricated part is the parametric

design/mechanical/cad/*.scad and the STEP (ISO 10303 AP242) exported from it.

The dimensioned bid control drawing is the per-part sheet. Deliverable formats a

bidder receives / returns by trade:

| Package | Trade | Native/CNC geometry | Cutting / flat pattern | Drawing | BOM / schedule |
| --- | --- | --- | --- | --- | --- |
| BP-01 Mount head machining | 3-axis CNC mill | STEP AP242 (3-D master) | — | PDF (NW-MH-00x) | XLSX |
| BP-02 Precision turned parts | CNC / manual turn | STEP AP242 | — | PDF (NW-TP-00x) | XLSX |
| BP-03 Pier & foundation | RC + steel + anodized adapter | STEP AP242 (adapter/top plate) | DXF/DWG (plate profiles) | PDF (NW-PF-00x) | XLSX |
| BP-04 Roll-off roof | Steel fab (cut + weld) | STEP AP242 (assembly ref) | DXF/DWG (flat-pattern laser/waterjet cut) | PDF (NW-RR-00x) | XLSX |
| BP-05 COTS procurement | Purchase | — | — | Vendor datasheets (PDF) | XLSX (COTS schedule) |

Rule of thumb: **STEP AP242 for anything CNC-machined in 3-D; DXF/DWG for anything

cut flat and welded; PDF for every dimensioned drawing; XLSX for every BOM and the

COTS schedule.** Drawings and BOM are also carried in this repo as generator source

(SVG sheets, CSV BOM) so the package regenerates deterministically.

## 5. DISAPPEARING TURRET — VARIANT APPENDIX

The observatory's popular name is the "disappearing turret." **The primary,

tendered, and proven scope is the roll-off roof of BP-04** — a rectangular steel

roof frame that rolls its own length off the aperture on box-track rails, selected

in the trade study (Weighted-Pugh 3.92, the winner at default and cost-heavy

weights) and proven in the enclosure and wind proofs (drive move-force 235 N at

SF 2.1; snow case governs; survival-wind hold-down anchors mandatory). Bidders

should price BP-04 as the delivered enclosure.

**A retractable / telescoping vertical turret is documented here as a future

ALTERNATE only.** A turret that lowers or telescopes the whole enclosure below a

parapet has architectural appeal but is not engineered in this data package and

must not be priced as the base scope. Any bidder proposing it must treat it as a

separate, later procurement subject to these gates:

It needs its own structural proof first. None of the eleven Phase-C proofs

covers a telescoping turret: its lifting structure, guide columns, seals, snow and

survival-wind load paths, and drive are all unproven. The roll-off roof's wind

proof (survival uplift 9.2 kN, hold-downs → SF 3.9) and snow proof (10.8 kN closed

roof) do not transfer.

It is an ASSUMED design-intent concept — bidder/PE to confirm. Member sizing,

drive selection, seal detail, and foundation reactions are all open.

Bid it as a priced alternate, in the "Alternates" block of 05_bid_form.md,

clearly separated from the base roll-off scope, and flagged as requiring an

independent PE-stamped structural analysis before it can be built.

Until that analysis exists, the roll-off roof (BP-04) is the only enclosure

authorized for construction pricing.

## 6. Dossier contents

| File | Purpose |
| --- | --- |
| README.md | This index — packages, bid-in-parts rules, numbering, formats, turret appendix |
| 00_instructions_to_bidders.md | ITB — eligibility, RFI, validity, evaluation, submission, schedule |
| 01_statement_of_work_general.md | General SOW — scope, site, responsibilities, standards applicability |
| 02_standards_register.md | Full standards table and what each governs |
| 03_drawing_register.md | Every control drawing (part_no, name, pkg, material, rev, sheet) |
| 04_inspection_test_plan.md | ITP — acceptance criteria per trade, hold/witness points |
| 05_bid_form.md | Pricing schedule the vendor fills (per package, per line item, whole-job, alternates) |
| 06_terms_and_conditions.md | Commercial T&Cs placeholders |

Child bid packages BP-01 … BP-05 (their SOWs, per-part fabrication notes, and

package-specific ITPs) live under their own packages/BP-0x_*/ directories and

inherit every general document in this dossier.

---

*Every "ASSUMED design-intent" item in this dossier and its children is a value the

proven design does not yet fix (weld sizes, roof member sizing, rail/drive product

selection, GD&T tolerance values, surface finish, rebar/anchor sizing). Each is

explicitly flagged for the bidder/PE to confirm and is never presented as final.*

# 00 — Instructions to Bidders (ITB)

Project: NIGHTWATCH Observatory — telescope mount + roll-off roof enclosure

Document: BP-00 / 00 — Instructions to Bidders, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets throughout the package.

This tender is packaged as a **Technical Data Package structured per

MIL-STD-31000A** (product definition data, associated lists, and the "issued for

bid" data management state). The technical baseline is the parts registry

design/mechanical/tender/gen/partspec.py and the generated BOM/cut-list/COTS

schedule; the commercial baseline is this ITB together with 06_terms_and_conditions.md.

---

## 1. Eligibility

A bidder is eligible to bid one or more packages if it can demonstrate, for each

package bid:

| Package | Minimum qualification |
| --- | --- |
| BP-01 Mount head machining | 3-axis CNC milling of 6061-T6 aluminium; ability to hold ISO 286 H7 bearing bores and produce a CMM inspection report; anodizing per MIL-A-8625F Type III (in-house or qualified sub) |
| BP-02 Precision turned parts | CNC/manual turning of 303 stainless per ASTM A582; concentricity ≤ 0.02 TIR; passivation per ASTM A967 (in-house or qualified sub) |
| BP-03 Pier & foundation | Cast-in-place reinforced concrete per ACI 301 / ACI 318; ability to deliver a PE-stamped foundation design and ACI concrete cylinder break reports; hot-dip galvanizing per ASTM A123 (sub OK) |
| BP-04 Roll-off roof | Structural steel welding per AWS D1.1 with current WPS/PQR and welder qualifications; hot-dip galvanizing per ASTM A123; rail/drive installation |
| BP-05 COTS procurement | Authorized distribution / procurement of the specified commercial items; ability to provide manufacturer datasheets and certificates of conformance |

Bidders shall submit evidence of the above (certifications, welder qual records, PE

registration in the project jurisdiction, sample inspection reports) with their

quote. A whole-job bidder shall evidence every package it self-performs and name its

subcontractors for the rest.

## 2. Request-for-Information (RFI) process

All questions shall be submitted in writing to the Owner's technical

representative by the RFI cut-off date (SCHEDULE PLACEHOLDER — TBD), no later

than [N] business days before the bid due date.

Reference each question to a NW-xx part number, a drawing sheet, or a numbered

clause of this dossier.

Answers are issued to all bidders as numbered addenda; only written addenda

amend the tender. Verbal guidance is not binding.

**Every item flagged "ASSUMED design-intent — bidder/PE to confirm" is a valid RFI

subject.** Where a bidder's fabrication method needs a value the frozen design does

not fix (weld size, roof member size, rail/drive product, GD&T value, surface

finish, rebar/anchor sizing), raise it as an RFI rather than assuming silently.

## 3. Quote validity

Quotes shall remain firm and open for acceptance for 90 calendar days from the

bid due date unless a longer period is stated on the bid form. Prices shall be fixed

(not indexed) for that period. Any assumptions, exclusions, or clarifications a

bidder relies on shall be listed explicitly on the bid form; unstated assumptions

are not binding on the Owner.

## 4. Basis of evaluation

Bids are evaluated on best overall value to the Owner, not lowest price alone.

The evaluation considers:

Compliance with the technical baseline (partspec dimensions, materials,

finishes, tolerances, and the applicable standards register) and completeness of

the required certs/reports.

Total evaluated price for the package(s) bid — labour + material + finish,

inclusive of the Inspection & Test Plan deliverables of 04_inspection_test_plan.md.

Lead time and schedule fit (see §7).

Qualification and past performance on comparable precision-mechanical /

structural-steel / concrete work.

Handling of ASSUMED design-intent items — a bidder who prices these

transparently and flags confirmations needed is preferred over one who buries them.

Award may be made by individual package, by combination, or whole-job, whichever

gives the Owner best overall value. The Owner may award different packages to

different bidders. The Owner is not bound to accept the lowest or any bid.

## 5. Submission format

Each bid shall contain, as separate clearly-labelled files:

Completed pricing schedule (05_bid_form.md filled in) — per line item, per

package subtotal, whole-job total, and any alternates priced.

Eligibility evidence per §1.

Compliance statement — a line-by-line confirmation of conformance to each

applicable standard in 02_standards_register.md, with any deviations listed.

Assumptions & exclusions — including every "ASSUMED design-intent" value the

bidder has resolved in order to price, stated for PE confirmation.

Proposed lead time and schedule against the placeholders in §7.

For BP-04: draft WPS/PQR references. For BP-03: the PE who will stamp the

foundation. For BP-01/02: sample inspection report formats.

Preferred transmittal formats mirror the file-format map (README §4): PDF for

narrative and signed documents, XLSX for the priced schedule.

## 6. Award and documentation

The successful bidder shall, before fabrication, receive the released Technical Data

Package for the awarded package(s): the STEP AP242 3-D masters (BP-01/02/03

machined items), DXF/DWG flat patterns (BP-03/04 cut parts), PDF control

drawings (NW-xx sheets), and the XLSX BOM / COTS schedule. All released data

remains marked "ISSUED FOR BID / FOR PE REVIEW" until the responsible PE stamps the

package for construction; **no fabrication for permanent installation shall proceed

on unstamped data** (see BP-03 pier and BP-04 roof, both PE gates).

## 7. Schedule (PLACEHOLDERS — TBD)

| Milestone | Date |
| --- | --- |
| Tender issued | [TBD] |
| RFI cut-off | [TBD] |
| Final addenda issued | [TBD] |
| Bids due | [TBD] |
| Evaluation / clarifications | [TBD] |
| Award / letter of intent | [TBD] |
| Released-for-construction data (post PE stamp) | [TBD] |
| Delivery / installation window | [TBD] |

All dates are placeholders to be fixed in the issued tender. Bidders shall quote lead

times as calendar weeks from award on the bid form so schedules can be normalized

across partial and whole-job bids.

---

*This ITB is a commercial framing document. It does not alter any dimension, material,

finish, or tolerance in the frozen technical baseline; where it and a control drawing

appear to conflict on a technical value, the partspec/drawing governs and the

conflict shall be raised as an RFI.*

# 01 — Statement of Work (General)

Project: NIGHTWATCH Observatory — telescope mount + roll-off roof enclosure

Document: BP-00 / 01 — General Statement of Work, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets.

---

## 1. Scope summary

NIGHTWATCH is a small robotic astronomical observatory: a **counterweight-free German

equatorial mount (GEM)** carrying an Intes-Micro MN78 f/8 optical tube, mounted on an

isolated reinforced-concrete pier, inside a roll-off roof enclosure. This

tender procures the fabricated mechanical hardware and the commercial (COTS) hardware

for that build, organized into five packages:

The mount — a machined 6061-T6 aluminium head (RA + DEC housings and saddle,

BP-01), 303 stainless turned spindles and shaft (BP-02), driven by COTS harmonic

drives, angular-contact bearings, on-axis absolute encoders, and stepper

drivetrains (BP-05).

The foundation — an isolated cast-in-place concrete pier with a galvanized steel

top plate, an anodized aluminium pier-to-mount adapter, and a cast-in anchor-bolt

set (BP-03).

The roll-off roof ("disappearing turret") — a welded structural-steel roof frame

with rafters/purlins, box-track rails, wheel/drive/hold-down brackets, hot-dip

galvanized, with a COTS gate-operator drive, V-groove wheels, and metal roofing

(BP-04 fabrication + BP-05 purchase).

The mechanical design is frozen and proven (design/mechanical/MECHANICAL_DESIGN.md,

6 PASS / 5 remediated-FAIL across eleven proofs). This SOW procures the build to that

baseline; it does not re-open design decisions.

### 1.1 Proof-out remediations embedded in this scope

The tender carries the five computed remediations from the proof-out; bidders shall

treat each as a mandatory feature of the parts they touch:

| Remediation | Where it appears | Registry basis |
| --- | --- | --- |
| Angular-contact 7008 (RA) / 7006 (DEC) bearings, back-to-back — replace deep-groove 6008/6006 | Housing seats NW-MH-001 (7008 seat) / NW-MH-002 (7006 seat); spindle journals NW-TP-002 / NW-TP-003; bearings NW-CO-003 / NW-CO-004 | Stiffness proof: 6008/6006 were ~98% of the 43.5″ deflection FAIL |
| On-axis absolute encoder (RA + DEC) — replaces homing-grade baseline | NW-CO-005 | Encoder proof: baseline 5.02″ RMS FAIL → on-axis ring 0.54″ |
| 4× wind hold-down anchors | Brackets NW-RR-006 + anchor set NW-PF-004 | Wind proof: survival uplift 9.2 kN, 4× 2 klbf anchors → SF 3.9 |
| Temperature-compensated focuser | NW-CO-008 | Thermal proof: 22 K diurnal swing walks focus ~10× depth-of-focus |
| 48 V power pack (v2 autonomy) | NW-CO-013 | Power proof: 12 V pack 3.3 h vs 10 h night; 48 V → 13.4 h |

## 2. Site

| Parameter | Value | Basis |
| --- | --- | --- |
| Location | Central Nevada (high-desert site) | Config baseline (SOURCED) |
| Elevation | 1800 m [5906 ft] | params.SITE.elevation_m |
| Latitude | 38.9° N | params.SITE.latitude_deg |
| Air density | ISA at 1800 m (derived) — reduced density lowers wind drag but is used for the survival case | params.SITE.air_density (DERIVED) |
| Design wind | Operational gust and 105 mph survival governs roof uplift | Wind proof (ASCE 7 framing) |
| Snow | Closed-roof snow case governs roof structure (10.8 kN, ~6.1× dead weight) | Enclosure proof |
| Seismic / foundation | Pier passes with governing SF 6.8, f_n 152 Hz; embedment > frost line, isolated from any building slab | Pier proof |

**Site loads (wind/snow/seismic) are ASSUMED design-intent at the ASCE 7 level and

shall be confirmed by the responsible PE against the actual permitted site

(ground-snow load, wind exposure category, seismic design category).** Bidders on

BP-03 and BP-04 shall price to the loads the PE confirms.

## 3. General responsibilities

### 3.1 Owner (or Owner's engineer) provides

The released Technical Data Package for each awarded package: STEP AP242 masters,

DXF/DWG flat patterns, PDF control drawings (NW-xx), and the XLSX BOM.

The responsible Professional Engineer who reviews and stamps the pier (BP-03)

and the roof structure (BP-04) before construction.

Confirmed site loads and the survey/benchmark for pier location and orientation to

latitude 38.9°.

Coordination of cross-package interfaces where packages are awarded separately.

### 3.2 Bidder / Contractor provides (for each package bid)

All labour, materials to the specified stock (see cut list), consumables, finishes,

fixturing, and shipping to the delivery point.

Fabrication to the frozen dimensions, materials, finishes, and tolerances of the

control drawings and partspec — dual-unit dimensions govern as drawn.

The Inspection & Test Plan deliverables of 04_inspection_test_plan.md

(CMM reports, weld NDE, concrete cylinder breaks, material certs, finish checks) as

a condition of acceptance.

Resolution — via RFI — of any "ASSUMED design-intent" value needed to fabricate,

submitted for PE confirmation; the contractor shall not silently finalize an

assumed value.

For BP-03/BP-04: the PE-stampable structural submittals (rebar/anchor design; weld

procedures and member-size confirmation) required before construction.

## 4. Standards applicability matrix

Which standards govern which package. Full text and scope in 02_standards_register.md.

| Standard(s) | BP-01 | BP-02 | BP-03 | BP-04 | BP-05 | Governs |
| --- | --- | --- | --- | --- | --- | --- |
| MIL-STD-31000A | ● | ● | ● | ● | ● | Technical Data Package structure |
| ASME Y14.5-2018 (GD&T) | ● | ● | ● | ● |  | Geometric dimensioning & tolerancing |
| ASME Y14.100 / .24 / .34 / .1 | ● | ● | ● | ● | ● | Drawing practice, types, associated lists/BOM, sheet/title block |
| ASME Y14.36 / ASME B46.1 | ● | ● | ○ |  |  | Surface texture symbols & measurement |
| ISO 286 (H7/js6) | ● | ● | ○ |  |  | Bearing-bore / journal fits |
| ISO 2768 (mK) | ● | ● | ● | ● |  | General tolerances |
| ASTM B209 / AMS-QQ-A-250/11 | ● |  | ● |  |  | 6061-T6 plate material |
| ASTM A582 |  | ● |  |  |  | 303 stainless bar |
| ASTM A36 |  |  | ● | ● |  | Structural steel plate |
| ASTM A500 Gr B |  |  |  | ● |  | HSS members |
| ASTM A615 Gr60 |  |  | ● |  |  | Rebar |
| ASTM F1554 Gr36 |  |  | ● | ● | ● | Anchor bolts |
| ASTM A574 | ● | ● | ● | ● | ● | Socket-head cap screws |
| MIL-A-8625F Type III | ● |  | ● |  |  | Hardcoat anodize (aluminium) |
| ASTM A123 |  |  | ● | ● |  | Hot-dip galvanize (steel) |
| ASTM A967 |  | ● |  |  |  | Passivation (stainless) |
| AWS A2.4 / D1.1 (+ WPS/PQR) |  |  | ○ | ● |  | Weld & NDE symbols; structural steel welding |
| AWS D1.2 |  |  |  | ○ |  | Aluminium welding (if any welded Al) |
| ACI 318 (Ch. 17) / ACI 301 |  |  | ● | ○ |  | Concrete design/spec & anchoring |
| ASCE 7 |  |  | ● | ● |  | Wind / snow / seismic loads |
| STEP ISO 10303 AP242 | ● | ● | ● | ○ |  | 3-D / CNC exchange |
| DXF / DWG |  |  | ● | ● |  | Flat-pattern cutting |
| PDF / XLSX | ● | ● | ● | ● | ● | Drawings / BOM formats |

● = primary/applicable · ○ = conditionally applicable (as-noted / if that process is used).

## 5. Interfaces (owner-coordinated on split awards)

Key mating features held by shared datums across packages — a partial bidder builds

to their own published dimensions; the Owner coordinates fit:

RA housing NW-MH-001 flange (104 mm [4.094 in] bolt circle, 8 holes) ↔ **RA

spindle NW-TP-002 (8× M4 on 104 PCD) ↔ CSF-32 harmonic drive NW-CO-001** (bore

80.0 mm [3.150 in]).

DEC housing NW-MH-002 (83 mm [3.268 in] bolt circle) ↔ DEC spindle NW-TP-003

↔ CSF-25 NW-CO-002 (bore 64.0 mm [2.520 in]).

Bearing seats NW-MH-001 (Ø68.0 mm [2.677 in] H7, 7008) / NW-MH-002 (Ø55.0 mm

[2.165 in] H7, 7006) ↔ spindle journals ↔ COTS bearings NW-CO-003/004.

Pier top plate NW-PF-002 (12 in sq) ↔ adapter plate NW-PF-003 (10 in sq) ↔

RA housing NW-MH-001 ↔ anchor set NW-PF-004 (4× Ø19.05 mm [0.750 in] F1554).

Roof wheel brackets NW-RR-004 ↔ V-groove wheels NW-CO-010 ↔ **rails

NW-RR-003; drive bracket NW-RR-005 ↔ gate-operator NW-CO-011; hold-down

brackets NW-RR-006 ↔ anchors** (mandatory wind remediation).

---

*Package-specific SOWs (per-part fabrication notes, sequencing, and acceptance)

accompany each child package BP-01 … BP-05 and incorporate this general SOW by

reference.*

# 02 — Standards Register

Document: BP-00 / 02 — Standards Register, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets.

Every standard is cited by number. Bidders shall comply with the latest issue in

force at bid date unless a specific edition is named. Where a standard is marked

*ASSUMED / PE-to-confirm*, the design does not yet fix the governed value and the

bidder/PE shall confirm it before construction.

---

## 1. Technical Data Package

| Standard | Governs | Applies to |
| --- | --- | --- |
| MIL-STD-31000A | Technical Data Package: product-definition data set, associated lists, data-management "issued for" states (this package is issued at the *bid* state) | Whole dossier (BP-00 … BP-05) |

## 2. Drawing practice, GD&T, and surface texture

| Standard | Governs | Applies to |
| --- | --- | --- |
| ASME Y14.5-2018 | Geometric dimensioning & tolerancing (datums, feature control frames, position/flatness/concentricity) | BP-01, BP-02, BP-03, BP-04 machined/fabricated features |
| ASME Y14.100 | Engineering drawing practices (general) | All control drawings NW-xx |
| ASME Y14.24 | Drawing types (detail, assembly, control) — these sheets are *bid control drawings* | All control drawings |
| ASME Y14.34 | Associated lists / bill of material (parts list, data list) | Master BOM, cut list, COTS schedule (XLSX) |
| ASME Y14.1 | Sheet size and title-block format | All control drawings (ANSI B-class sheet, ASME-style title block) |
| ASME Y14.36 | Surface texture symbols on drawings | BP-01, BP-02 (Ra callouts), BP-03 adapter |
| ASME B46.1 | Surface texture (measurement of roughness Ra) | Verification of BP-01/BP-02 finish (see ITP) |

ASSUMED / PE-to-confirm — GD&T tolerance values. The registry states general

tolerances (ISO 2768-mK) and critical callouts (H7 bores, h6/j6 journals,

concentricity 0.02 TIR, flange flatness 0.05); specific **feature-control-frame

values per Y14.5** (true position of bolt patterns, datum references) are ASSUMED

design-intent and shall be confirmed by the PE on the released drawings.

## 3. Fits and general tolerances

| Standard | Governs | Applies to |
| --- | --- | --- |
| ISO 286 | Limits & fits — H7 bearing bores, js6/j6/h6 journals | BP-01 seats (Ø68.0 mm [2.677 in] H7 RA; Ø55.0 mm [2.165 in] H7 DEC), BP-02 journals |
| ISO 2768 (class mK) | General linear and angular tolerances for un-toleranced dimensions | BP-01, BP-02, BP-03, BP-04 |

## 4. Materials

| Standard | Governs | Applies to |
| --- | --- | --- |
| ASTM B209 / AMS-QQ-A-250/11 | 6061-T6 aluminium plate | BP-01 (NW-MH-001/002/003), BP-03 adapter (NW-PF-003) |
| ASTM A582 | 303 free-machining stainless bar | BP-02 (NW-TP-001/002/003) |
| ASTM A36 | Structural carbon-steel plate | BP-03 top plate (NW-PF-002); BP-04 rails/brackets (NW-RR-003/004/005/006) |
| ASTM A500 Gr B | Cold-formed welded HSS | BP-04 roof frame & purlins (NW-RR-001/002) |
| ASTM A615 Gr60 | Deformed rebar | BP-03 pier cage (NW-PF-001) — *schedule ASSUMED, PE-to-confirm* |
| ASTM F1554 Gr36 | Anchor bolts (headed/threaded) | BP-03 anchor set (NW-PF-004); BP-04 hold-down anchors — *sizing ASSUMED, PE-to-confirm* |
| ASTM A574 | Alloy-steel socket-head cap screws | Fastener schedule (NW-CO-014), all bolted joints |

## 5. Finishes

| Standard | Governs | Applies to |
| --- | --- | --- |
| MIL-A-8625F Type III | Hardcoat anodize (Class 1 clear, 0.002 in [0.051 mm]) | BP-01 aluminium (NW-MH-001/002/003), BP-03 adapter (NW-PF-003) |
| ASTM A123 | Hot-dip galvanizing of steel | BP-03 top plate, anchor set; BP-04 all steel (NW-RR-001…006) |
| ASTM A967 | Passivation of stainless (nitric) | BP-02 (NW-TP-001/002/003) |

## 6. Welding and NDE

| Standard | Governs | Applies to |
| --- | --- | --- |
| AWS A2.4 | Weld and NDE symbols on drawings | BP-04 weld callouts; BP-03 (if any steel welding) |
| AWS D1.1 | Structural steel welding code, incl. WPS / PQR and welder qualification | BP-04 (NW-RR-001…006) |
| AWS D1.2 | Structural aluminium welding | *Conditional* — only if any aluminium is welded (BP-01 items are machined, not welded, at baseline) |

ASSUMED / PE-to-confirm — weld sizes. Fillet/groove sizes, joint details, and NDE

extent for BP-04 are ASSUMED design-intent (registry: "fully welded, gusseted"

corners). The bidder's WPS/PQR and the PE shall fix weld sizes and NDE scope

against the confirmed ASCE 7 loads.

## 7. Foundation and loads

| Standard | Governs | Applies to |
| --- | --- | --- |
| ACI 318 (incl. Ch. 17 anchoring-to-concrete) | Reinforced-concrete design; cast-in / post-installed anchor capacity | BP-03 pier (NW-PF-001), anchor set (NW-PF-004), roof hold-down anchors |
| ACI 301 | Specification for structural concrete (materials, placement, cylinder testing) | BP-03 concrete work |
| ASCE 7 | Minimum design loads — wind, snow, seismic | BP-03 pier; BP-04 roof (survival-wind uplift & snow cases govern) |

PE-stamp gate. BP-03 (pier + anchors) and the BP-04 roof structure are

construction-gated on a PE-stamped analysis against ASCE 7 loads confirmed for

the permitted site. Rebar schedule, anchor sizing, member sizing, and weld sizing are

ASSUMED design-intent until stamped.

## 8. Deliverable data formats

| Standard / format | Governs | Applies to |
| --- | --- | --- |
| STEP ISO 10303 AP242 | 3-D product model exchange for CNC | BP-01, BP-02, BP-03 machined items (cad/*.scad → STEP master) |
| DXF / DWG | 2-D flat-pattern cutting geometry | BP-03/BP-04 laser/waterjet-cut plates |
| PDF | Released drawing sheets | All NW-xx control drawings |
| XLSX | Bill of material / associated lists / COTS schedule | Master BOM, cut list, COTS schedule |

---

*Standards are cited to establish acceptance criteria only; they do not change any

dimension in the frozen technical baseline. Where a standard and a control drawing

conflict on a value, the drawing/partspec governs and the conflict is an RFI item.*

# 03 — Drawing Register

Document: BP-00 / 03 — Drawing Register, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets.

Every fabricated part in the parts registry carries one control drawing — a

to-scale stock envelope with the controlling dual-unit dimensions, a keyed

feature/dimension table, and an ASME-Y14-style title block (material, finish,

tolerance, GD&T status, and the "ISSUED FOR BID / FOR PE REVIEW" state). The sheet is

the dimensioned, quotable summary a shop reviews to price the job; the **3-D

machining master** for every machined feature is the parametric

design/mechanical/cad/*.scad and the STEP (ISO 10303 AP242) exported from it.

This register lists partspec.fabricated_parts() — parts with a fabrication drawing

and non-COTS stock. 15 control drawings across four fabrication packages.

Drawing practice per ASME Y14.100 / Y14.24 / Y14.1; associated list per

ASME Y14.34.

---

## 1. Register

| # | Part No. | Name | Pkg | Material | Finish | Process | Rev | Sheet |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | NW-MH-001 | RA (polar) axis housing | BP-01 | 6061-T6 aluminium plate per ASTM B209 / AMS-QQ-A-250/11 | Type III hardcoat anodize per MIL-A-8625F | CNC mill, 3-axis | A | NW-MH-001.svg → PDF |
| 2 | NW-MH-002 | DEC axis housing + Losmandy-D saddle | BP-01 | 6061-T6 aluminium plate per ASTM B209 / AMS-QQ-A-250/11 | Type III hardcoat anodize per MIL-A-8625F | CNC mill, 3-axis | A | NW-MH-002.svg → PDF |
| 3 | NW-MH-003 | DEC saddle clamp bar | BP-01 | 6061-T6 aluminium plate per ASTM B209 / AMS-QQ-A-250/11 | Type III hardcoat anodize per MIL-A-8625F | CNC mill, 3-axis | A | NW-MH-003.svg → PDF |
| 4 | NW-TP-001 | Counterweight shaft | BP-02 | 303 stainless per ASTM A582 | Passivate per ASTM A967 (nitric) | CNC turn | A | NW-TP-001.svg → PDF |
| 5 | NW-TP-002 | RA drive spindle / drawbar adapter | BP-02 | 303 stainless per ASTM A582 | Passivate per ASTM A967 (nitric) | CNC turn + mill | A | NW-TP-002.svg → PDF |
| 6 | NW-TP-003 | DEC drive spindle / saddle stub | BP-02 | 303 stainless per ASTM A582 | Passivate per ASTM A967 (nitric) | CNC turn + mill | A | NW-TP-003.svg → PDF |
| 7 | NW-PF-001 | Reinforced-concrete telescope pier | BP-03 | Cast-in-place concrete f′c = 4000 psi (27.6 MPa) per ACI 318 / ACI 301 | none (concrete) | Cast-in-place | A | NW-PF-001.svg → PDF |
| 8 | NW-PF-002 | Pier top plate | BP-03 | ASTM A36 structural steel | Hot-dip galvanize per ASTM A123 | Laser/waterjet cut + drill | A | NW-PF-002.svg → PDF |
| 9 | NW-PF-003 | Pier-to-mount adapter plate | BP-03 | 6061-T6 aluminium per ASTM B209 | Type III hardcoat anodize per MIL-A-8625F | CNC mill | A | NW-PF-003.svg → PDF |
| 10 | NW-RR-001 | Roof frame perimeter (HSS) | BP-04 | ASTM A500 Gr B HSS (steel) | Hot-dip galvanize per ASTM A123 | Cut + weld (AWS D1.1) | A | NW-RR-001.svg → PDF |
| 11 | NW-RR-002 | Roof rafters / purlins | BP-04 | ASTM A500 Gr B HSS (steel) | Hot-dip galvanize per ASTM A123 | Cut + weld (AWS D1.1) | A | NW-RR-002.svg → PDF |
| 12 | NW-RR-003 | Track rail beams (box track) | BP-04 | ASTM A36 structural steel | Hot-dip galvanize per ASTM A123 | Cut + weld / bolt to piers | A | NW-RR-003.svg → PDF |
| 13 | NW-RR-004 | Wheel axle brackets | BP-04 | ASTM A36 structural steel | Hot-dip galvanize per ASTM A123 | Laser cut + weld | A | NW-RR-004.svg → PDF |
| 14 | NW-RR-005 | Drive bracket + end stops | BP-04 | ASTM A36 structural steel | Hot-dip galvanize per ASTM A123 | Laser cut + weld | A | NW-RR-005.svg → PDF |
| 15 | NW-RR-006 | Wind hold-down anchor brackets | BP-04 | ASTM A36 structural steel | Hot-dip galvanize per ASTM A123 | Laser cut + weld | A | NW-RR-006.svg → PDF |

Sheets are held in the repo as SVG (design/mechanical/tender/drawings/NW-xx.svg) and

issued to bidders as PDF. All at Rev A at this issue.

## 2. 3-D / cutting masters and format map

| Package | 3-D machining master | Cutting geometry | Sheet |
| --- | --- | --- | --- |
| BP-01 (NW-MH-00x) | cad/ra_housing.scad, cad/dec_housing.scad → STEP AP242 | — | PDF |
| BP-02 (NW-TP-00x) | cad/counterweight_shaft.scad (+ turned masters) → STEP AP242 | — | PDF |
| BP-03 (NW-PF-00x) | cad/pier_adapter.scad → STEP AP242 (adapter/top plate) | DXF/DWG plate profiles | PDF |
| BP-04 (NW-RR-00x) | cad/assembly.scad (assembly reference) | DXF/DWG flat patterns for laser/waterjet cut | PDF |

The .scad source and its STEP export are the geometry of record for machined 3-D

features; the control sheet governs the dimensioned, toleranced callouts. Where

the STEP model and the sheet disagree, the sheet governs and it is an RFI item.

## 3. Registry exceptions (no fabrication drawing)

The following are in the parts registry but carry no fabrication control drawing

(they are purchased / buy-to-print):

NW-PF-004 — Anchor-bolt set + template (BP-03): COTS ASTM F1554 Gr36 bolts plus

a fabricated template; listed on the COTS schedule and the BP-03 SOW, sizing

ASSUMED per ACI 318 Ch. 17 (PE to confirm for ~9.2 kN uplift). No NW-PF-004.svg.

NW-CO-001 … NW-CO-014 (BP-05): all commercial off-the-shelf; specified by

manufacturer datasheet on the COTS schedule, not by a NIGHTWATCH drawing.

## 4. Notes on the register

Revisions. Part numbers are stable; changes advance the sheet revision. Rev A is

the issue-for-bid revision. A released-for-construction revision follows the PE stamp

(see BP-03/BP-04 gates).

ASSUMED design-intent on the sheets. Several sheets carry values the frozen

design does not fix — Losmandy-D saddle/clamp geometry (NW-MH-002/003), spindle body

diameters (NW-TP-002/003), adapter geometry (NW-PF-003), rebar schedule (NW-PF-001),

roof member sizes and weld sizes (NW-RR-001…006). Each is tagged **ASSUMED

design-intent — bidder/PE to confirm** in the sheet's PROVENANCE/NOTE line and shall

be confirmed before construction.

Title-block status. Every sheet's title block reads **"ISSUED FOR BID / FOR PE

REVIEW — NOT FOR CONSTRUCTION"** and shall not be used for construction until

re-issued post-stamp.

---

*This register is generated from partspec.fabricated_parts(); if the parts registry

changes, regenerate the sheets (python3 -m design.mechanical.tender.gen.drawing) and

reconcile this table.*

# 04 — Inspection & Test Plan (ITP)

Document: BP-00 / 04 — Inspection & Test Plan, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets.

This ITP sets acceptance criteria and hold/witness points for each trade. The

deliverable reports named here are a condition of acceptance and payment and shall

be priced into every bid (see 00_instructions_to_bidders.md §4). Verification

methods reference the standards register (02_standards_register.md).

Point types: H = Hold point (work shall not proceed past this point until the

Owner/PE releases it) · W = Witness point (Owner may attend; contractor gives

notice, work may proceed if Owner declines) · R = Review of records (documentation

only) · S = Surveillance (contractor's own QC, records retained).

---

## 1. BP-01 — Mount head machining (6061-T6, CNC)

Parts: NW-MH-001 (RA housing), NW-MH-002 (DEC housing + saddle), NW-MH-003 (clamp bar).

| # | Characteristic | Acceptance criterion | Method / standard | Point |
| --- | --- | --- | --- | --- |
| 1.1 | Material | 6061-T6 per ASTM B209 / AMS-QQ-A-250/11 | Mill certificate (heat/lot traceable) | R |
| 1.2 | Bearing seat bore — RA | Ø 68.0 mm [2.677 in] H7 (+0.030/0), for 7008 pair | CMM dimensional report | H |
| 1.3 | Bearing seat bore — DEC | Ø 55.0 mm [2.165 in] H7 (+0.030/0), for 7006 pair | CMM dimensional report | H |
| 1.4 | Drive register bores | RA Ø 80.0 mm [3.150 in] (CSF-32); DEC Ø 64.0 mm [2.520 in] (CSF-25) | CMM | W |
| 1.5 | Flange bolt patterns | RA 8× on 104 mm [4.094 in] PCD; DEC on 83 mm [3.268 in] PCD; true position per Y14.5 | CMM | W |
| 1.6 | Flange face flatness | 0.05 mm [0.002 in] flat | CMM / surface plate | W |
| 1.7 | General tolerances | ISO 2768-mK | Calipers/micrometer, first-article | S |
| 1.8 | Surface finish | Ra 1.6 µm (NW-MH-001/002), Ra 3.2 µm (NW-MH-003) | Profilometer per ASME B46.1 | W |
| 1.9 | Finish | Type III hardcoat anodize, 0.002 in [0.051 mm], MIL-A-8625F Class 1 | Coating-thickness gauge; anodizer CoC | R |

First-Article Inspection (FAI): full CMM report on the first RA and DEC housing is

a hold point before running the balance of the lot / releasing to anodize.

## 2. BP-02 — Precision turned parts (303 SS, turned)

Parts: NW-TP-001 (CW shaft — *optional, counterweighted variant only*), NW-TP-002 (RA

spindle), NW-TP-003 (DEC spindle).

| # | Characteristic | Acceptance criterion | Method / standard | Point |
| --- | --- | --- | --- | --- |
| 2.1 | Material | 303 stainless per ASTM A582 | Mill certificate | R |
| 2.2 | Bearing journals | RA j6 Ø 40.0 mm [1.575 in] (7008); DEC j6 Ø 30.0 mm [1.181 in] (7006) | CMM / air gauge | H |
| 2.3 | Concentricity | 0.02 mm [0.0008 in] TIR journal-to-register | Between-centres runout / CMM | H |
| 2.4 | Drive registers | RA 80.0 mm [3.150 in] (CSF-32); DEC 64.0 mm [2.520 in] (CSF-25) | CMM | W |
| 2.5 | Bolt patterns | 8× M4 on RA 104 mm [4.094 in] / DEC 83 mm [3.268 in] PCD | CMM | W |
| 2.6 | General tolerances | ISO 2768-mK; journals h6/j6 per ISO 286 | First-article gauge | S |
| 2.7 | Surface finish | Ra 0.8 µm journals | Profilometer per ASME B46.1 | W |
| 2.8 | Finish | Passivate per ASTM A967 (nitric) | Passivation CoC; optional copper-sulphate / water-immersion test | R |

## 3. BP-03 — Pier & foundation (RC + steel). **PE-STAMP GATE.**

Parts: NW-PF-001 (RC pier), NW-PF-002 (steel top plate), NW-PF-003 (Al adapter),

NW-PF-004 (anchor set + template).

| # | Characteristic | Acceptance criterion | Method / standard | Point |
| --- | --- | --- | --- | --- |
| 3.1 | Foundation design | PE-stamped rebar/anchor design vs confirmed ASCE 7 loads (survival-wind uplift ~9.2 kN, seismic) | Stamped calc + drawings, ACI 318 Ch. 17 | H |
| 3.2 | Concrete mix | f′c = 4000 psi [27.6 MPa] per ACI 301 | Approved mix design | H |
| 3.3 | Rebar cage | 6× #4 vertical + #3 ties @ 12 in oc (A615 Gr60) — *ASSUMED, PE-to-confirm* | Placement inspection before pour | H |
| 3.4 | Anchor template / setting | 4× Ø 19.05 mm [0.750 in] F1554, embedment 304.8 mm [12.000 in], projection 50 mm [1.969 in]; template hole tol 0.02 mm | Survey of bolt pattern before pour | H |
| 3.5 | Concrete strength | Cylinder breaks meet f′c at 28 days (and 7-day check) | ACI cylinder break test (4 cylinders/pour min) | H |
| 3.6 | Pier geometry | Ø 304.8 mm [12.000 in]; height above grade 914.4 mm [36.000 in]; embedment > frost line; plumb 1:200; top level 0.5°; isolated from any slab | Survey / level | W |
| 3.7 | Top plate NW-PF-002 | 304.8 mm [12.000 in] sq × 9.5 mm [0.375 in]; hole pattern ±0.25 mm | Dimensional; A123 galvanize CoC | W |
| 3.8 | Adapter NW-PF-003 | 254.0 mm [10.000 in] sq × 19.05 mm [0.750 in]; latitude-38.9° orientation | CMM; anodize CoC | W |
| 3.9 | Grout / seating | Non-shrink grout under top plate, full bearing | Visual | W |

Hold: no concrete pour until 3.1, 3.3, and 3.4 are released. The pier is

construction-gated on the PE stamp (02_standards_register.md §7).

## 4. BP-04 — Roll-off roof (structural steel, AWS D1.1)

Parts: NW-RR-001 (frame), NW-RR-002 (rafters/purlins ×5), NW-RR-003 (rails ×2),

NW-RR-004 (wheel brackets ×8), NW-RR-005 (drive bracket ×4), NW-RR-006 (hold-down ×4).

| # | Characteristic | Acceptance criterion | Method / standard | Point |
| --- | --- | --- | --- | --- |
| 4.1 | Weld procedures & personnel | Qualified WPS / PQR and current welder qualifications | Records review, AWS D1.1 | H |
| 4.2 | Member sizing | Roof member sizes vs confirmed ASCE 7 snow (10.8 kN closed-roof case) + wind — *ASSUMED, PE-to-confirm* | PE-stamped submittal | H |
| 4.3 | Material | HSS ASTM A500 Gr B (NW-RR-001/002); plate ASTM A36 (NW-RR-003…006) | Mill certificates | R |
| 4.4 | Weld quality | Visual (VT) 100% per AWS D1.1; NDE (MT/UT) on critical/CJP joints per PE-set extent — *weld sizes ASSUMED, PE-to-confirm* | VT + MT/UT, symbols per AWS A2.4 | H |
| 4.5 | Frame geometry | Square 3 mm/m, diagonal 5 mm; gauge (rail spacing) matches roof span | Tape/laser measure | W |
| 4.6 | Rail straightness | 3 mm [0.118 in] over run; gauge 2 mm; rail run = 2× roof length so roof clears aperture | Survey / string line | W |
| 4.7 | Wheel brackets | 8×, bore for Ø4 in V-groove wheel (NW-CO-010), M16 axle; sized ≥ 4× roof + snow | Dimensional; load rating check | W |
| 4.8 | Wind hold-down brackets NW-RR-006 | 4×, Ø 19.05 mm [0.750 in] F1554 anchor, capacity ≥ 2 klbf each → survival SF 3.9 (MANDATORY wind remediation) | Dimensional; anchor pull-test per ACI 318 Ch.17 | H |
| 4.9 | Drive & interlocks | Gate-operator (NW-CO-011) mounted; hard end stops; snow + wind interlocks functional | Function test (open/close, interlock trip) | H |
| 4.10 | Finish | Hot-dip galvanize per ASTM A123 | Coating-thickness gauge; galvanizer CoC | R |

## 5. BP-05 — COTS procurement

| # | Characteristic | Acceptance criterion | Method | Point |
| --- | --- | --- | --- | --- |
| 5.1 | Item conformance | Each NW-CO-xxx matches specified part/rating on the COTS schedule | Certificate of Conformance + datasheet | R |
| 5.2 | Remediation items | 7008/7006 angular-contact DB pairs (NW-CO-003/004); on-axis absolute encoder (NW-CO-005); temp-comp focuser (NW-CO-008); 48 V pack (NW-CO-013) supplied as specified (no deep-groove/homing-grade substitution) | Datasheet verification | H |
| 5.3 | Bearings | 7008 bore Ø40 / OD Ø68 mm; 7006 bore Ø30 / OD Ø55 mm; back-to-back preload set | Manufacturer data; incoming dimensional check | W |
| 5.4 | Fasteners | A574 SHCS; F1554 Gr36 anchors, galvanized | Mill certs / CoC | R |
| 5.5 | Incoming inspection | No transit damage; quantities per schedule | Visual + count | S |

No substitution of the five proof-out remediation items without written Owner/PE

approval — each closes a documented FAIL and a like-for-like commercial swap is not

equivalent.

## 6. Documentation package (all trades)

At delivery the contractor shall provide, per package:

Material certificates / mill certs (traceable to heat/lot).

First-Article Inspection and CMM reports (BP-01/BP-02 dimensional).

Weld records — WPS/PQR, welder quals, VT/NDE reports (BP-04).

Concrete records — mix design, placement logs, cylinder-break results,

pre-pour rebar/anchor inspection sign-offs (BP-03).

Finish certificates — anodize (MIL-A-8625F), galvanize (A123), passivation

(A967) CoCs with thickness/verification data.

Certificates of Conformance for all COTS (BP-05).

As-built notes on any RFI-resolved ASSUMED design-intent value.

Acceptance is conditional on a complete documentation package; a shortfall is grounds

to withhold acceptance of the affected line items.

---

*Hold points marked H require Owner/PE release; the contractor shall give the

notice period stated in the awarded contract before proceeding. All ASSUMED

design-intent values (weld sizes, roof member sizing, rebar/anchor sizing, GD&T

values, surface finish, rail/drive product) remain bidder/PE to confirm and are

verified against the PE-stamped, released-for-construction data — not this bid issue.*

# 05 — Bid Form / Pricing Schedule

Document: BP-00 / 05 — Bid Form, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets. Prices in USD, exclusive of tax.

Bidder: ______________________  Date: ____________

Quote valid for: _______ days (≥ 90 per ITB §3)  Currency: USD

Fill the price cells. A bidder may price **any single package, any combination, or

the whole job** (README §2). Leave a package blank if not bidding it. Each line item

splits Labour / Material / Finish; enter a Lead time in calendar weeks from

award. Every fabricated line ships with its ITP deliverables (04_inspection_test_plan.md)

priced in. Quantities and stock are from the parts registry — do not re-scope.

Legend: *Ext.* = extended (unit × qty). Blank cells are for the bidder.

---

## BP-01 — Mount head machining (CNC, 6061-T6; Type III anodize)

| Part No. | Description | Qty | Stock (from cut list) | Labour $ | Material $ | Finish $ | Ext. $ | Lead (wks) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NW-MH-001 | RA (polar) axis housing | 1 | plate 203.2×203.2×76.2 mm [8.000×8.000×3.000 in] |  |  |  |  |  |
| NW-MH-002 | DEC axis housing + Losmandy-D saddle | 1 | plate 152.4×152.4×63.5 mm [6.000×6.000×2.500 in] |  |  |  |  |  |
| NW-MH-003 | DEC saddle clamp bar | 1 | plate 101.6×76.2×25.4 mm [4.000×3.000×1.000 in] |  |  |  |  |  |
|  | BP-01 subtotal |  |  |  |  |  | $________ |  |

Deliverables priced in: CMM/FAI reports (H7 bores), mill certs, anodize CoC.

## BP-02 — Precision turned parts (303 SS; passivate)

| Part No. | Description | Qty | Stock | Labour $ | Material $ | Finish $ | Ext. $ | Lead (wks) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NW-TP-001 | Counterweight shaft (OPTIONAL — counterweighted variant only) | 1 | round Ø31.8 × 457.2 mm [Ø1.250 × 18.000 in] |  |  |  |  |  |
| NW-TP-002 | RA drive spindle / drawbar adapter | 1 | round Ø88.9 × 101.6 mm [Ø3.500 × 4.000 in] |  |  |  |  |  |
| NW-TP-003 | DEC drive spindle / saddle stub | 1 | round Ø76.2 × 88.9 mm [Ø3.000 × 3.500 in] |  |  |  |  |  |
|  | BP-02 subtotal |  |  |  |  |  | $________ |  |

Deliverables priced in: CMM report (journals, 0.02 TIR concentricity), mill certs,

passivation CoC. *NW-TP-001 is deleted in the baseline counterweight-free build; price

it as a separate add if the counterweighted variant is elected (see Alternates).*

## BP-03 — Pier & foundation (RC + steel). **PE-STAMP GATE**

| Part No. | Description | Qty | Stock | Labour $ | Material $ | Finish $ | Ext. $ | Lead (wks) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NW-PF-001 | Reinforced-concrete telescope pier | 1 | Ø304.8 × 1828.8 mm [Ø12.000 × 72.000 in] cast-in-place |  |  | — |  |  |
| NW-PF-002 | Pier top plate | 1 | plate 304.8×304.8×9.5 mm [12.000×12.000×0.375 in] A36 |  |  |  |  |  |
| NW-PF-003 | Pier-to-mount adapter plate | 1 | plate 254.0×254.0×19.05 mm [10.000×10.000×0.750 in] 6061-T6 |  |  |  |  |  |
| NW-PF-004 | Anchor-bolt set + template | 1 | 4× Ø19.05 × 304.8 mm [Ø0.750 × 12.000 in] F1554 + template |  |  |  |  |  |
|  | PE-stamped foundation design + cylinder-break testing (ITP 3.1/3.5) | 1 | lump sum |  |  |  |  |  |
|  | BP-03 subtotal |  |  |  |  |  | $________ |  |

Deliverables priced in: PE stamp, rebar/anchor design, ACI cylinder breaks,

galvanize CoC (top plate/anchors), anodize CoC (adapter). *Anchor/rebar sizing ASSUMED

— confirm against confirmed ASCE 7 loads.*

## BP-04 — Roll-off roof (structural steel; galvanize; AWS D1.1)

| Part No. | Description | Qty | Stock | Labour $ | Material $ | Finish $ | Ext. $ | Lead (wks) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NW-RR-001 | Roof frame perimeter (HSS) | 1 | HSS 50.8 sq × 3.2 wall mm [2.000 × 0.125 in], 12000 mm run |  |  |  |  |  |
| NW-RR-002 | Roof rafters / purlins | 5 | HSS 38.1 sq × 3.2 wall mm [1.500 × 0.125 in] |  |  |  |  |  |
| NW-RR-003 | Track rail beams (box track) | 2 | box track ~63.5 sq × 4.0 wall mm [2.500 × 0.157 in], run = 2× roof length |  |  |  |  |  |
| NW-RR-004 | Wheel axle brackets | 8 | plate 101.6×76.2×9.5 mm [4.000×3.000×0.375 in] A36 |  |  |  |  |  |
| NW-RR-005 | Drive bracket + end stops | 4 | plate 150.0×100.0×9.5 mm [5.906×3.937×0.375 in] A36 |  |  |  |  |  |
| NW-RR-006 | Wind hold-down anchor brackets (MANDATORY) | 4 | plate 127.0×101.6×12.7 mm [5.000×4.000×0.500 in] A36 |  |  |  |  |  |
|  | WPS/PQR + welder quals + VT/NDE (ITP 4.1/4.4) | 1 | lump sum |  |  |  |  |  |
|  | Rail + drive install / commissioning (interlocks) | 1 | lump sum |  |  |  |  |  |
|  | BP-04 subtotal |  |  |  |  |  | $________ |  |

Deliverables priced in: WPS/PQR, welder quals, VT + NDE reports, galvanize CoC,

hold-down anchor pull-test. *Roof member sizes and weld sizes ASSUMED — confirm vs

ASCE 7 snow/wind (PE).*

## BP-05 — COTS procurement schedule (purchase)

| Part No. | Description | Qty | Unit $ | Ext. $ | Lead (wks) |
| --- | --- | --- | --- | --- | --- |
| NW-CO-001 | Harmonic drive, RA (CSF-32-100-2A-GR) | 1 |  |  |  |
| NW-CO-002 | Harmonic drive, DEC (CSF-25-80-2A-GR) | 1 |  |  |  |
| NW-CO-003 | Angular-contact bearing 7008 (RA pair, DB) — *remediation* | 2 |  |  |  |
| NW-CO-004 | Angular-contact bearing 7006 (DEC pair, DB) — *remediation* | 2 |  |  |  |
| NW-CO-005 | On-axis absolute encoder (RA + DEC) — *remediation* | 2 |  |  |  |
| NW-CO-006 | Stepper motor NEMA17 + 27:1 planetary | 2 |  |  |  |
| NW-CO-007 | Motor driver (TMC5160) / OnStepX board | 2 |  |  |  |
| NW-CO-008 | Temperature-compensated focuser — *remediation* | 1 |  |  |  |
| NW-CO-009 | Counterweights (5 kg×2, 2.5 kg×1) — *optional* | 3 |  |  |  |
| NW-CO-010 | V-groove track wheels | 8 |  |  |  |
| NW-CO-011 | Roof drive (gate operator) | 1 |  |  |  |
| NW-CO-012 | Metal roofing panel + flashing (~9.0 m²) | 1 |  |  |  |
| NW-CO-013 | 48 V LiFePO4 battery pack + solar — *remediation (v2)* | 1 |  |  |  |
| NW-CO-014 | Fastener schedule (SHCS, anchors) | 1 |  |  |  |
|  | BP-05 subtotal |  |  | $________ |  |

*No substitution of the remediation items (NW-CO-003/004/005/008/013) without written

Owner/PE approval — each closes a documented proof FAIL.*

---

## Whole-job summary

| Package | Subtotal $ | Lead time (wks) |
| --- | --- | --- |
| BP-01 Mount head machining |  |  |
| BP-02 Precision turned parts |  |  |
| BP-03 Pier & foundation |  |  |
| BP-04 Roll-off roof |  |  |
| BP-05 COTS procurement |  |  |
| Sum of packages | $________ |  |
| Whole-job integration / install / project management (whole-job bidders) |  |  |
| WHOLE-JOB TOTAL | $________ |  |

## Alternates (price separately; do NOT include in base totals)

| Ref | Alternate | Basis | Price Δ $ | Lead (wks) |
| --- | --- | --- | --- | --- |
| ALT-1 | Counterweighted variant — add NW-TP-001 shaft + NW-CO-009 weights | Baseline is counterweight-free (torque proof SF 2.5/2.6); §9 delta −$110 to delete |  |  |
| ALT-2 | v2 sub-arcsec upgrade — full on-axis RESA ring in lieu of hybrid encoder | Encoder proof: hybrid → full ring reaches 0.54″; §9 +$1,500–5,000 |  |  |
| ALT-3 | Active-thermal enclosure — ventilation + insulation + day pre-cool on the roll-off roof | Thermal FAIL + DGX heat finding; §9 +$300 |  |  |
| ALT-4 | 48 V off-grid power pack (NW-CO-013) in lieu of grid + UPS | Power proof: 12 V 3.3 h → 48 V 13.4 h; §9 +$400 (v2) |  |  |
| ALT-5 | Torque-motor direct drive (precision-weighted upgrade) | Trade study: flips to torque motor when precision dominates |  |  |
| ALT-6 | DISAPPEARING-TURRET variant — retractable/telescoping turret in lieu of roll-off roof | NOT engineered; requires its own PE-stamped structural proof first (README §5). Concept price only. |  |  |

*ALT-6 is a concept-level price only and is not a construction bid; it is priced

here solely to size the future scope and shall carry the bidder's stated assumptions.*

---

Bidder assumptions / exclusions / RFI-resolved ASSUMED values (attach as needed):

_______________________________________________________________________________

Signed: ______________________  Title: ______________  Date: __________

*Prices are firm for the validity period (ITB §3). Where this form and a control

drawing differ on a dimension, the drawing/partspec governs; raise it as an RFI.*

# 06 — Terms & Conditions (Commercial)

Document: BP-00 / 06 — Terms & Conditions, Rev A

Status: ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION

Units: mm primary, [inch] in brackets.

These are brief commercial placeholders to frame a bid. They are **not legal

advice** and shall be replaced/superseded by the Owner's executed purchase order or

contract, which governs on conflict. Bracketed [TBD] values are set at award.

---

## 1. Scope of agreement

The awarded contractor shall furnish the labour, materials, finishes, inspection, and

documentation for the awarded package(s) BP-01 … BP-05 as defined by the released

Technical Data Package (partspec-derived control drawings NW-xx, STEP/DXF masters,

BOM, and the ITP 04_inspection_test_plan.md), per MIL-STD-31000A. Award may be

by package, combination, or whole-job (README §2).

## 2. Price and payment

Prices are those on the completed bid form (05_bid_form.md), firm for the

quote-validity period (ITB §3).

Payment terms: [TBD — e.g. Net 30 from acceptance]. Progress/milestone payments

(e.g. material release, FAI acceptance, PE stamp, delivery) may be scheduled at award.

Payment of any line item is conditioned on its ITP acceptance (hold-point

releases, CMM/weld/concrete/finish records, COTS CoCs).

## 3. Delivery

Delivery point / Incoterms: [TBD] (e.g. FCA contractor's works, or DAP central

Nevada site at 1800 m [5906 ft] elevation).

Lead time runs in calendar weeks from award, as quoted per line item on the bid

form. Time is of the essence for the PE-gated items (BP-03 pier, BP-04 roof).

Risk of loss and packaging/preservation for transit are the contractor's until the

agreed delivery point; galvanized/anodized/passivated surfaces shall be protected.

## 4. Title

Title to conforming goods passes to the Owner on **[the later of delivery and

payment — TBD]**. Title to materials and work-in-progress for which the Owner has made

progress payment passes on payment, with the contractor retaining care, custody, and

control until delivery.

## 5. Warranty

The contractor warrants that all work is **free from defects in material and

workmanship and conforms to the released drawings, specified materials,

finishes, tolerances, and the cited standards for [TBD — e.g. 12 months from

acceptance / 18 months from delivery]**.

Finishes are warranted to their standard (MIL-A-8625F Type III anodize; ASTM A123

galvanize; ASTM A967 passivation).

Structural work (BP-03 pier, BP-04 roof) is warranted as built to the **PE-stamped,

released-for-construction** design; the Owner-provided PE design intent itself is not

a contractor warranty item except as to conforming execution.

Remedy: repair, replace, or re-work non-conforming items at the contractor's cost.

COTS items (BP-05) pass through the manufacturer's warranty.

## 6. Change orders

No change to scope, dimensions, materials, finishes, or the technical baseline is

effective except by written change order signed by the Owner.

Resolution of any "ASSUMED design-intent — bidder/PE to confirm" value (weld

sizes, roof member sizing, rail/drive product, GD&T values, surface finish,

rebar/anchor sizing) that alters cost, schedule, or scope shall be handled as a

change order following the RFI process (ITB §2). Silent deviation from the

released baseline is not authorized.

Verbal instructions are not change orders.

## 7. Intellectual property / ownership of drawings

All drawings, the parts registry, STEP/DXF models, the BOM, and this dossier are the

Owner's property, furnished solely to bid and, if awarded, fabricate the

NIGHTWATCH work.

They shall not be copied, disclosed to third parties, or used for any other

project without the Owner's written consent, and shall be returned or destroyed on

request. Subcontractors are bound to the same restriction.

The contractor retains its own pre-existing manufacturing know-how; deliverable

fabricated goods and their inspection records are the Owner's on payment.

Status control: documents remain marked **"ISSUED FOR BID / FOR PE REVIEW — NOT

FOR CONSTRUCTION"** until re-issued post-PE-stamp. No permanent-installation

fabrication shall proceed on unstamped data (BP-03/BP-04 gates).

## 8. Compliance, permits, and PE stamp

The contractor shall comply with applicable OSHA / jurisdictional safety and

building requirements for the work it performs.

Permits and the Professional Engineer's stamp for the pier and roof structure are

**[TBD — Owner-provided per SOW §3.1 unless the contract assigns them to the

contractor]**. Construction of PE-gated items shall not begin on unstamped data.

## 9. Liability, indemnity, insurance

[TBD] — limits of liability, mutual indemnity for third-party claims, and

required insurance (general liability, workers' comp, professional/E&O for any

design-delegated structural work) are set at award.

## 10. Termination and disputes

[TBD] — termination for convenience / for cause, and the governing law and

dispute-resolution forum (venue, mediation/arbitration) are set at award. Absent a

stated choice, the law of the project jurisdiction (Nevada) applies.

---

*These commercial terms do not alter any technical value in the frozen baseline. On

any conflict between these terms and the executed purchase order/contract, the **PO/

contract governs**; on any conflict with a control drawing on a technical value, the

drawing/partspec governs and the conflict is an RFI item.*

# Part II — BP-01 mount machining

# BP-01 — Mount Head Machining (CNC 6061-T6) — Bidder README

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-01 — Mount head machining |
| Trade | CNC machining (6061-T6 aluminium), 3-axis mill |
| Parts | NW-MH-001, NW-MH-002, NW-MH-003 (3 fabricated line items) |
| Branch / project | design/mechanical-tender — NIGHTWATCH Observatory Mount & Roll-off Tender |
| Issue date | 2026-08-06 |
| Revision | A |
| Governing TDP standard | MIL-STD-31000A (Technical Data Package) |

This README is the entry point for the machine shop bidding BP-01. It defines the scope, the

data package the shop receives, the bidder deliverables, and the items still carried as

ASSUMED design-intent. Read it with SOW.md (the per-part machining specification) and

acceptance.md (the CMM dimensional acceptance plan) in this same folder.

---

## 1. Scope

BP-01 covers the mount head only — the three fabricated 6061-T6 aluminium parts that form the

right-ascension (RA) and declination (DEC) axis housings and the dovetail saddle clamp. The shop:

Procures 6061-T6 plate to spec, with material certification.

CNC-machines the three parts to the STEP master and the NW-MH control drawings.

Applies Type III hardcoat anodize per MIL-A-8625F Class 1 (clear).

Inspects per acceptance.md and delivers finished, certified, first-article-inspected parts.

Out of scope for BP-01 (separate packages — the head *interfaces* to these but the shop does not

supply them):

| Interface | Supplied under | Notes |
| --- | --- | --- |
| Counterweight shaft, RA drive spindle, DEC drive spindle | BP-02 (303 SS precision turned) | Spindles carry the bearing inner races that seat in the BP-01 housings. |
| Concrete pier, pier top plate, pier-to-mount adapter | BP-03 (pier & foundation) | The RA housing mounts to the adapter plate (NW-PF-003). |
| Roll-off roof steelwork | BP-04 | Not a mount-head interface. |
| Harmonic drives, angular-contact bearings, on-axis encoders, motors, fasteners | BP-05 (COTS) | See §4 interface list. |

---

## 2. Data package the shop receives (per MIL-STD-31000A)

| Item | Format / standard | Role |
| --- | --- | --- |
| 3-D solid master | STEP ISO 10303 AP242 | CNC authority — governs as-modelled geometry. |
| Control drawings NW-MH-001 / -002 / -003 | PDF (drawing practices per ASME Y14.100; drawing types Y14.24; sheet & title block Y14.1) | Envelope + title block + key dimensions & features; bid control drawing. |
| SOW.md | Markdown | Per-part machining spec: datums, H7 bores, registers, saddle, finish, GD&T, certs. |
| acceptance.md | Markdown | CMM dimensional acceptance of the H7 bores + flatness; FAI requirements. |
| cut_list.csv (rows for NW-MH-001/002/003) | CSV/XLSX | Stock size, cut allowance, stock mass. |

Order of precedence. The STEP AP242 solid governs geometry; the drawing + SOW govern

tolerances, notes, finish, and material; where geometry and the tolerance package disagree, the **SOW

controls** and the bidder shall raise an RFI before cutting metal. All GD&T is interpreted per

ASME Y14.5-2018; general tolerances per ISO 2768-mK; fits per ISO 286.

---

## 3. Line-item summary (source: `partspec.parts_for('BP-01')` + `cut_list.csv`)

| Part no. | Name | Stock (plate) | Qty | Stock mass | Finish | Drawing | cut_list row |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NW-MH-001 | RA (polar) axis housing | 203.2 mm [8.000 in] × 203.2 mm [8.000 in] × 76.2 mm [3.000 in] | 1 | 8.50 kg | Type III hardcoat anodize | NW-MH-001 | row 2 |
| NW-MH-002 | DEC axis housing + Losmandy-D saddle | 152.4 mm [6.000 in] × 152.4 mm [6.000 in] × 63.5 mm [2.500 in] | 1 | 3.98 kg | Type III hardcoat anodize | NW-MH-002 | row 3 |
| NW-MH-003 | DEC saddle clamp bar | 101.6 mm [4.000 in] × 76.2 mm [3.000 in] × 25.4 mm [1.000 in] | 1 | 0.53 kg | Type III hardcoat anodize | NW-MH-003 | row 4 |

Stock mass is the quantity ordered (stock volume × 6061-T6 density), not finished net mass. Cut

allowance is 3.0 mm on stock. Material for all three: **6061-T6 aluminium plate per ASTM B209 /

AMS-QQ-A-250/11**.

---

## 4. Cross-package interfaces the shop must preserve

The bearing seats and drive registers are mating features to other packages. The shop machines the

BP-01 side; the datums must be held so the mating COTS/turned parts assemble:

| BP-01 feature | Mates to | Part |
| --- | --- | --- |
| NW-MH-001 bearing seat Ø68 H7 | Angular-contact 7008 DB pair (OD 68 mm) | NW-CO-003 (BP-05) |
| NW-MH-001 drive register Ø80 mm | CSF-32-100 harmonic drive (bore 80 mm) via RA spindle | NW-CO-001 / NW-TP-002 |
| NW-MH-002 bearing seat Ø55 H7 | Angular-contact 7006 DB pair (OD 55 mm) | NW-CO-004 (BP-05) |
| NW-MH-002 drive register Ø64 mm | CSF-25-80 harmonic drive (bore 64 mm) via DEC spindle | NW-CO-002 / NW-TP-003 |
| Axis (through-bore) | On-axis absolute encoder ring | NW-CO-005 (BP-05) |
| NW-MH-002 Losmandy-D saddle + NW-MH-003 clamp | OTA dovetail | (owner-supplied OTA) |

**Remediation context.** The bearing seats are sized for **angular-contact 7008 (RA) / 7006 (DEC)**

pairs in a **back-to-back (DB), preloaded** arrangement — the proven remediation of the deep-groove

6008/6006 baseline, which the stiffness proof showed to be ~98% of the pointing-deflection FAIL.

This is a **moment-stiffness** decision: seat coaxiality and bore-to-face perpendicularity are the

stiffness-critical callouts (see `SOW.md` §4 and MECHANICAL_DESIGN.md §9).

---

## 5. Bidder deliverables

Finished, anodized parts NW-MH-001 / -002 / -003 (qty 1 each).

Material certification / CoC for the 6061-T6 plate (ASTM B209 / AMS-QQ-A-250/11), with heat/lot

traceability and T6 temper confirmation.

Anodize certification — MIL-A-8625F Type III Class 1, coating thickness record.

First-Article Inspection (FAI) report per acceptance.md, including the CMM results for every

H7 bore and flatness callout.

RFI / nonconformance log for any ASSUMED value the shop needed resolved.

---

## 6. ASSUMED design-intent — bidder / PE to confirm (NOT final)

The following are carried as ASSUMED design-intent in the parts registry and must not be

treated as released dimensions. The bidder/PE shall confirm before production:

Flange bolt-circle diameters and patterns — NW-MH-001 Ø104.0 mm [4.094 in] × 8 holes; NW-MH-002

Ø83.0 mm [3.268 in] (DERIVED ~1.3× drive bore; not fixed in the design).

Losmandy-D saddle geometry on NW-MH-002 (76.2 mm [3.000 in] width, 15° dovetail) — ASSUMED to a

standard Losmandy-D profile; undercut/relief not dimensioned in the repo.

NW-MH-003 saddle clamp bar — the entire part is ASSUMED design-intent; the Losmandy-D clamp is

not dimensioned in the repo.

GD&T tolerance values — coaxiality, perpendicularity, and position values are ASSUMED pending PE.

Bearing-seat surface finish and preload method (shim vs. clamp) — ASSUMED, bidder/PE to detail.

Encoder-ring register location on the axis — ASSUMED; preserve the through-bore.

---

## 7. References

Parts registry: design/mechanical/tender/gen/partspec.py → parts_for('BP-01') (single source of truth).

BOM / cut list: design/mechanical/tender/bom/{master_bom,cut_list}.csv.

Control drawings: design/mechanical/tender/drawings/NW-MH-00{1,2,3}.svg.

Design basis: design/mechanical/MECHANICAL_DESIGN.md §9 (selected config + remediations);

design/mechanical/tradestudy/SECTION.md (selection rationale, item 8 bearing fix).

Standards register: MIL-STD-31000A, ASME Y14.5-2018 / Y14.100 / Y14.24 / Y14.1 / Y14.36, ASME B46.1,

ISO 286, ISO 2768, MIL-A-8625F, ASTM B209 / AMS-QQ-A-250/11.

# BP-01 — Statement of Work: Mount Head Machining (CNC 6061-T6)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-01 — Mount head machining |
| Parts | NW-MH-001 (RA housing), NW-MH-002 (DEC housing + saddle), NW-MH-003 (saddle clamp bar) |
| Process | CNC mill, 3-axis |
| Material | 6061-T6 aluminium plate per ASTM B209 / AMS-QQ-A-250/11 |
| Finish | MIL-A-8625F Type III hardcoat anodize, 0.002 in, Class 1 (clear) |
| Issue date / rev | 2026-08-06 / A |

Purpose. This SOW specifies the machining, tolerancing, finishing, and certification requirements

for the three fabricated mount-head parts. It is read with the STEP ISO 10303 AP242 solid master (CNC

authority), the NW-MH control drawings (PDF), and acceptance.md. All dimensions are dual-unit,

mm primary, inch in brackets, drawn from the parts registry (partspec.parts_for('BP-01')) and

cut_list.csv — no dimension herein is invented.

Standards applied. MIL-STD-31000A (TDP); ASME Y14.5-2018 (GD&T); ASME Y14.100 (drawing

practices), Y14.24 (drawing types), Y14.1 (sheet/title block); ASME Y14.36 & ASME B46.1 (surface

texture); ISO 286 (H7/js6 fits); ISO 2768-mK (general tolerances); MIL-A-8625F (hardcoat

anodize); ASTM B209 / AMS-QQ-A-250/11 (6061-T6 plate).

---

## 1. General requirements (all three parts)

Material & certification. 6061-T6 plate per ASTM B209 / AMS-QQ-A-250/11, T6 temper.

Furnish mill certification and Certificate of Conformance with heat/lot traceability; mark each

part with part number and revision per ASME Y14.100.

General tolerance. ISO 2768-mK (medium, fine machining class) on all dimensions not

otherwise toleranced. Break all sharp edges 0.3–0.5 mm [0.012–0.020 in] unless a sealing/mating

face is noted; no burrs.

GD&T. Interpret all geometric callouts per ASME Y14.5-2018. Datum reference frames are

defined per part below. Surface-texture symbols per ASME Y14.36, values per ASME B46.1.

Fits. Bearing seats and registers per ISO 286: bores at H7 (see per-part tables);

pilot/register bores at H8 unless the mating part dictates otherwise (**ASSUMED — bidder/PE to

confirm**).

Stress relief. Rough-machine, then stress-relieve before finish-machining the bearing seats to

hold the H7 tolerance through anodize (ASSUMED best practice — bidder to propose).

Finish sequence. Apply **Type III hardcoat anodize per MIL-A-8625F Class 1 (clear), 0.002 in

[~0.051 mm] *after* final machining. Mask** the bearing seats, drive registers, and threaded

holes. The hardcoat builds ~0.001 in [~0.025 mm] per side, which consumes the H7 band — so the

H7 bores shall be dimensioned and verified in the as-delivered (post-mask/post-anodize) state

(ASSUMED masking approach — bidder/PE to confirm; see acceptance.md).

Surface finish. Part-level surface finish per the control drawing: Ra 1.6 µm [63 µin] on

NW-MH-001 / NW-MH-002, Ra 3.2 µm [125 µin] on NW-MH-003. Bearing-seat bores are typically held

finer at Ra ≤ 0.8 µm [32 µin] (ASSUMED design-intent — bidder/PE to confirm).

---

## 2. NW-MH-001 — RA (polar) axis housing

Drawing: NW-MH-001 (rev A). Stock: plate **203.2 mm [8.000 in] × 203.2 mm [8.000 in] ×

76.2 mm [3.000 in], cut allowance 3.0 mm, stock mass 8.50 kg (cut_list.csv row 2). Wall:**

8.0 mm [0.315 in]. Pocket-lightening is permitted at the bidder's option **provided the bore and

flange datums are retained**.

Datum reference frame (ASME Y14.5-2018):

Datum A — primary flange / mounting face (planar; controls the housing to the pier-adapter and

DEC-head interface).

Datum B — bearing-seat bore axis, Ø68 H7 (the axis of rotation).

Datum C — drive-register bore or a designated flange hole, for clocking the bolt pattern.

Critical features:

| Feature | Nominal (mm [in]) | Tolerance / fit | GD&T (per Y14.5) | Ra |
| --- | --- | --- | --- | --- |
| Bearing seat bore (7008) | Ø 68.000 – 68.030 [Ø2.677] | H7 per ISO 286 (+0.030 / 0) | Ⓐ datum B; cylindricity *(value ASSUMED)* | ≤0.8 µm (ASSUMED) |
| Bore-to-flange perpendicularity | — | — | ⟂ bore axis to Datum A *(value ASSUMED — PE)* | — |
| Two-seat coaxiality (bearing span 76.2 mm [3.000 in]) | — | — | ◎ seats coaxial *(value ASSUMED — PE)* | — |
| Drive register bore (CSF-32) | Ø 80.0 [3.150] | H8 pilot (ASSUMED) | positional to B | 1.6 µm |
| Flange face flatness | — | — | ▱ 0.05 mm to Datum A | 1.6 µm |
| Flange bolt circle | Ø 104.0 [4.094], 8 holes | position *(ASSUMED)* | ⊕ to B/C *(ASSUMED)* | — |
| Corner mounting holes | 4 × M6 | ISO 2768-mK | — | — |

Provenance / flags. Outer/wall/depth = P.RA_HOUSING (SOURCED); bearing seat = 7008 remediation;

**flange PCD Ø104 mm and 8-hole pattern are DERIVED (~1.3× bore) → ASSUMED design-intent, bidder/PE

to confirm.** Perpendicularity + coaxiality are the stiffness-critical callouts (§4).

Interfaces: bearing seat ← NW-CO-003 (7008 DB pair, OD 68); drive register ← NW-CO-001 (CSF-32,

bore 80) via NW-TP-002; through-bore ← NW-CO-005 encoder ring.

---

## 3. NW-MH-002 — DEC axis housing + Losmandy-D saddle

Drawing: NW-MH-002 (rev A). Stock: plate **152.4 mm [6.000 in] × 152.4 mm [6.000 in] ×

63.5 mm [2.500 in], cut allowance 3.0 mm, stock mass 3.98 kg (cut_list.csv row 3). Wall:**

8.0 mm [0.315 in]. Integral Losmandy-D dovetail saddle.

Datum reference frame (ASME Y14.5-2018):

Datum A — flange / mounting face (interfaces to the RA head).

Datum B — bearing-seat bore axis, Ø55 H7 (DEC axis of rotation).

Datum C — Losmandy-D saddle dovetail centre-plane.

Critical features:

| Feature | Nominal (mm [in]) | Tolerance / fit | GD&T (per Y14.5) | Ra |
| --- | --- | --- | --- | --- |
| Bearing seat bore (7006) | Ø 55.000 – 55.030 [Ø2.165] | H7 per ISO 286 (+0.030 / 0) | Ⓐ datum B; cylindricity *(ASSUMED)* | ≤0.8 µm (ASSUMED) |
| Bore-to-flange perpendicularity | — | — | ⟂ bore axis to Datum A *(ASSUMED — PE)* | — |
| Two-seat coaxiality (bearing span 63.5 mm [2.500 in]) | — | — | ◎ seats coaxial *(ASSUMED — PE)* | — |
| Drive register bore (CSF-25) | Ø 64.0 [2.520] | H8 pilot (ASSUMED) | positional to B | 1.6 µm |
| Flange face flatness | — | — | ▱ 0.05 mm to Datum A | 1.6 µm |
| Flange bolt circle | Ø 83.0 [3.268] | position *(ASSUMED)* | ⊕ to B/C *(ASSUMED)* | — |
| Losmandy-D saddle width | 76.2 [3.000] | ISO 2768-mK *(profile ASSUMED)* | profile to Datum C *(ASSUMED)* | 1.6 µm |
| Dovetail angle | 15° | ± *(ASSUMED)* | — | 1.6 µm |

Provenance / flags. Outer/wall/depth = P.DEC_HOUSING (SOURCED); bearing seat = 7006 remediation;

**Losmandy-D saddle geometry (76.2 mm width, 15° dovetail, undercut/relief) is ASSUMED to a standard

Losmandy-D profile — bidder/PE to confirm against a reference dovetail.** Flange PCD Ø83 mm is

ASSUMED design-intent.

Interfaces: bearing seat ← NW-CO-004 (7006 DB pair, OD 55); drive register ← NW-CO-002 (CSF-25,

bore 64) via NW-TP-003; saddle + NW-MH-003 clamp ← OTA dovetail.

---

## 4. NW-MH-003 — DEC saddle clamp bar

Drawing: NW-MH-003 (rev A). Stock: plate **101.6 mm [4.000 in] × 76.2 mm [3.000 in] ×

25.4 mm [1.000 in]**, cut allowance 3.0 mm, stock mass 0.53 kg (cut_list.csv row 4).

Datum reference frame: Datum A = clamp mating face; Datum B = dovetail bevel face.

| Feature | Nominal (mm [in]) | Tolerance | Ra |
| --- | --- | --- | --- |
| Length | 101.6 [4.000] | ISO 2768-mK | 3.2 µm |
| Width | 76.2 [3.000] | ISO 2768-mK | 3.2 µm |
| Thickness | 25.4 [1.000] | ISO 2768-mK | 3.2 µm |
| Clamp screws | 2 × M8 | ISO 2768-mK | — |
| Dovetail bevel | 15° (matching NW-MH-002) | ± *(ASSUMED)* | 3.2 µm |

**ASSUMED design-intent — bidder/PE to confirm.** The **entire NW-MH-003 clamp bar** is carried as

ASSUMED design-intent: the Losmandy-D clamp is not dimensioned in the repository. It pairs with the

NW-MH-002 saddle to clamp the OTA dovetail; the shop shall confirm the mating profile and clamp

travel before production.

---

## 5. Bearing-seat callout block (stiffness remediation — grounding)

The two housing bearing seats (Ø68 H7 on NW-MH-001, Ø55 H7 on NW-MH-002) are sized for

**matched angular-contact bearing pairs — 7008 (RA, OD 68 mm) and 7006 (DEC, OD 55 mm) — in a

back-to-back (DB), preloaded arrangement** (NW-CO-003 / NW-CO-004, BP-05). This is the proven

remediation of the deep-groove 6008/6006 baseline, which the stiffness/deflection proof identified

as ~98% of the 43.5″ pointing-deflection FAIL against the 5″ target (MECHANICAL_DESIGN.md §9; trade

study item 8).

Because moment stiffness — not load rating — governs, the machining controls that matter are:

Coaxiality of the two end seats over the bearing span (76.2 mm RA / 63.5 mm DEC) — GD&T value

ASSUMED, PE to set.

Perpendicularity of each seat axis to the flange mounting face (Datum A) — ASSUMED, PE to set.

H7 bore roundness/cylindricity and Ra ≤ 0.8 µm for correct outer-ring seating.

Preload method (ground spacer/shim set vs. clamped ring) — **ASSUMED design-intent; bidder/PE to

detail.** The housing shall provide an axial shoulder or clamp land per the released design.

---

## 6. Finishing

Type III hardcoat anodize per MIL-A-8625F Class 1 (clear), 0.002 in [~0.051 mm] on all external

surfaces after final machining.

Mask: bearing seats (Ø68 H7, Ø55 H7), drive registers (Ø80, Ø64), and all threaded holes.

Post-anodize, re-verify the masked H7 bores are within tolerance (see acceptance.md).

Furnish an anodize certificate with coating-thickness record.

---

## 7. Submittals & deliverables

Finished, anodized parts (qty 1 each): NW-MH-001, NW-MH-002, NW-MH-003.

Material cert / CoC (ASTM B209 / AMS-QQ-A-250/11) with heat/lot traceability.

Anodize certificate (MIL-A-8625F Type III).

First-Article Inspection report per acceptance.md (CMM for every H7 bore + flatness).

RFI log resolving every ASSUMED value before production.

---

## 8. ASSUMED design-intent register (this SOW)

| Item | Part(s) | Status |
| --- | --- | --- |
| Flange PCD & bolt pattern (Ø104/8-hole, Ø83) | NW-MH-001, -002 | ASSUMED — bidder/PE to confirm |
| GD&T coaxiality / perpendicularity / position values | NW-MH-001, -002 | ASSUMED — PE to set |
| Bearing-seat surface finish (Ra ≤ 0.8 µm) & preload method | NW-MH-001, -002 | ASSUMED — bidder/PE to detail |
| Drive-register fit class (H8 pilot) | NW-MH-001, -002 | ASSUMED — bidder/PE to confirm |
| Losmandy-D saddle profile / undercut / 15° dovetail | NW-MH-002 | ASSUMED — confirm vs reference dovetail |
| Entire saddle clamp bar geometry | NW-MH-003 | ASSUMED design-intent |
| Encoder-ring register location | NW-MH-001, -002 | ASSUMED — preserve through-bore |
| Post-anodize masking approach on H7 bores | all | ASSUMED — bidder/PE to confirm |

# BP-01 — Dimensional Acceptance Plan: Mount Head Machining

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-01 — Mount head machining |
| Parts | NW-MH-001, NW-MH-002, NW-MH-003 |
| Method | CMM dimensional acceptance of the H7 bearing-seat bores + flange flatness; profilometer for Ra |
| Issue date / rev | 2026-08-06 / A |

Scope. This plan defines the inspection method and accept/reject criteria for BP-01. Because each

part has quantity 1, the First-Article Inspection (FAI) *is* the production acceptance. The H7

bearing seats and the flange flatness are the critical characteristics and receive **100% CMM

verification; general dimensions are verified to ISO 2768-mK** on the FAI. All limits are dual-unit

and derived from partspec / the NW-MH control drawings — nothing invented.

Standards. ASME Y14.5-2018 (datum alignment / GD&T interpretation); ISO 286 (H7 limits); ISO 2768

(general tolerance); ASME B46.1 (surface texture measurement); ISO 1 (20 °C reference temperature).

---

## 1. Inspection method

CMM for all bores, flatness, and located hole patterns. Datum alignment shall follow the part's

datum reference frame in SOW.md (Datum A flange face, Datum B bore axis, Datum C register/saddle).

Metrology environment: temperature-controlled at 20 °C per ISO 1; parts thermally soaked

before measurement (ASSUMED soak time — bidder to state).

Measurement uncertainty: CMM + fixturing uncertainty shall be ≤ 10% of the tolerance band

for the H7 bores (gauge R&R / MSA evidence on request) — **ASSUMED acceptance gate, bidder/PE to

confirm**.

Bore evaluation: each H7 seat probed with ≥ 8 points per circle at 3 axial depths; report

least-squares diameter, roundness, and cylindricity.

Surface finish: profilometer per ASME B46.1 on bore walls and flange faces.

State of measurement: the H7 bores are measured as delivered (post-mask / post-anodize) —

see SOW.md §1.6/§6.

---

## 2. Acceptance criteria — NW-MH-001 (RA housing)

| Characteristic | Nominal (mm [in]) | Accept limits | Method | Class |
| --- | --- | --- | --- | --- |
| Bearing seat bore Ø68 H7 | Ø68.000 [2.677] | Ø68.000 – 68.030 mm (+0.030/0) | CMM, ≥8 pts × 3 depths | Critical — 100% |
| Bearing seat roundness / cylindricity | — | per PE GD&T *(value ASSUMED)* | CMM | Critical |
| Bore-to-flange perpendicularity | — | per PE GD&T *(ASSUMED)* | CMM (B to A) | Critical |
| Two-seat coaxiality over 76.2 mm [3.000 in] span | — | per PE GD&T *(ASSUMED)* | CMM | Critical |
| Flange face flatness | — | ≤ 0.05 mm [0.0020 in] | CMM plane fit | Critical — 100% |
| Drive register bore Ø80 (CSF-32) | Ø80.0 [3.150] | H8 pilot *(ASSUMED)* | CMM | Major |
| Flange bolt circle Ø104, 8 holes | Ø104.0 [4.094] | position *(ASSUMED)* | CMM | Major |
| Corner holes 4 × M6 | — | ISO 2768-mK | thread gauge | Minor |
| Bore surface finish | — | Ra ≤ 0.8 µm [32 µin] *(ASSUMED)* | profilometer | Major |
| General surface finish | — | Ra 1.6 µm [63 µin] | profilometer | Minor |
| Envelope 203.2 × 203.2 × 76.2 | [8.000×8.000×3.000] | ISO 2768-mK | calipers/CMM | Minor |

## 3. Acceptance criteria — NW-MH-002 (DEC housing + saddle)

| Characteristic | Nominal (mm [in]) | Accept limits | Method | Class |
| --- | --- | --- | --- | --- |
| Bearing seat bore Ø55 H7 | Ø55.000 [2.165] | Ø55.000 – 55.030 mm (+0.030/0) | CMM, ≥8 pts × 3 depths | Critical — 100% |
| Bearing seat roundness / cylindricity | — | per PE GD&T *(ASSUMED)* | CMM | Critical |
| Bore-to-flange perpendicularity | — | per PE GD&T *(ASSUMED)* | CMM (B to A) | Critical |
| Two-seat coaxiality over 63.5 mm [2.500 in] span | — | per PE GD&T *(ASSUMED)* | CMM | Critical |
| Flange face flatness | — | ≤ 0.05 mm [0.0020 in] | CMM plane fit | Critical — 100% |
| Drive register bore Ø64 (CSF-25) | Ø64.0 [2.520] | H8 pilot *(ASSUMED)* | CMM | Major |
| Flange bolt circle Ø83 | Ø83.0 [3.268] | position *(ASSUMED)* | CMM | Major |
| Losmandy-D saddle width | 76.2 [3.000] | ISO 2768-mK *(profile ASSUMED)* | CMM / profile gauge | Major |
| Dovetail angle | 15° | ± *(ASSUMED)* | angle gauge / CMM | Major |
| Bore surface finish | — | Ra ≤ 0.8 µm *(ASSUMED)* | profilometer | Major |
| General surface finish | — | Ra 1.6 µm [63 µin] | profilometer | Minor |
| Envelope 152.4 × 152.4 × 63.5 | [6.000×6.000×2.500] | ISO 2768-mK | calipers/CMM | Minor |

## 4. Acceptance criteria — NW-MH-003 (saddle clamp bar)

| Characteristic | Nominal (mm [in]) | Accept limits | Method | Class |
| --- | --- | --- | --- | --- |
| Length | 101.6 [4.000] | ISO 2768-mK | calipers/CMM | Minor |
| Width | 76.2 [3.000] | ISO 2768-mK | calipers/CMM | Minor |
| Thickness | 25.4 [1.000] | ISO 2768-mK | calipers/CMM | Minor |
| Clamp screws | 2 × M8 | ISO 2768-mK | thread gauge | Minor |
| Dovetail bevel | 15° (match NW-MH-002) | ± *(ASSUMED)* | angle gauge | Major |
| Surface finish | — | Ra 3.2 µm [125 µin] | profilometer | Minor |

The whole part is **ASSUMED design-intent** (Losmandy-D clamp not dimensioned in the repo); acceptance

limits above are provisional pending PE release.

---

## 5. Sampling

Critical characteristics (H7 bores, flange flatness, and the stiffness-critical coaxiality /

perpendicularity callouts): 100% — each part is qty 1, so FAI = production acceptance.

Major / Minor characteristics: verified on the FAI to ISO 2768-mK.

Post-anodize re-check: the H7 bores are re-verified after masking/anodize (per SOW.md §6).

## 6. Documentation & sign-off

The bidder shall deliver, per part:

FAI report — every characteristic in §2–§4 with measured value vs. limit and pass/fail.

CMM raw output — probe data + datum alignment record (Y14.5 frame).

Material certificate (ASTM B209 / AMS-QQ-A-250/11) with heat/lot traceability.

Anodize certificate (MIL-A-8625F Type III) with coating-thickness record.

Nonconformance / RFI dispositions for any ASSUMED value or out-of-tolerance condition.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Bidder QA |  |  |  |
| Owner / PE review |  |  |  |

---

## 7. ASSUMED-value register (do NOT treat as final)

The following acceptance values are ASSUMED design-intent — bidder/PE to confirm before they can

be applied as pass/fail gates:

| # | ASSUMED value | Part(s) |
| --- | --- | --- |
| 1 | All GD&T coaxiality / perpendicularity / position tolerances | NW-MH-001, -002 |
| 2 | Bearing-seat surface finish Ra ≤ 0.8 µm | NW-MH-001, -002 |
| 3 | Drive-register fit class (H8 pilot) | NW-MH-001, -002 |
| 4 | Flange PCD & pattern (Ø104/8-hole, Ø83) | NW-MH-001, -002 |
| 5 | Losmandy-D saddle profile & 15° dovetail | NW-MH-002 |
| 6 | Entire saddle clamp bar geometry | NW-MH-003 |
| 7 | CMM uncertainty gate (≤10% of tol band), soak time | all |
| 8 | Post-anodize masking / re-check approach | all |

# Part II — BP-02 turned parts

# BP-02 — Precision Turned Parts (303 SS) — Bidder README

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-02 — Precision turned parts |
| Trade | CNC / manual turning (303 stainless steel), single-point turning + light milling |
| Parts | NW-TP-001, NW-TP-002, NW-TP-003 (3 fabricated line items) |
| Branch / project | design/mechanical-tender — NIGHTWATCH Observatory Mount & Roll-off Tender |
| Issue date | 2026-08-06 |
| Revision | A |
| Governing TDP standard | MIL-STD-31000A (Technical Data Package) |

This README is the entry point for the turning shop bidding BP-02. It defines the scope, the

data package the shop receives, the bidder deliverables, and the items still carried as

ASSUMED design-intent. Read it with SOW.md (the per-part turning specification) and

acceptance.md (the dimensional / concentricity acceptance plan) in this same folder.

---

## 1. Scope

BP-02 covers the three turned 303 stainless-steel parts that couple the harmonic drives to the

right-ascension (RA) and declination (DEC) axes and carry the angular-contact bearing inner races —

plus the optional counterweight shaft. The shop:

Procures 303 stainless round bar to spec (ASTM A582), with material certification.

Turns (and lightly mills the bolt patterns / wrench flats on) the three parts to the STEP

master and the NW-TP control drawings, holding the bearing-race journals and the

harmonic-drive registers to their ISO 286 fit classes.

Applies passivation per ASTM A967 (nitric or citric).

Inspects per acceptance.md and delivers finished, passivated, first-article-inspected parts.

Out of scope for BP-02 (separate packages — the turned parts *interface* to these but the shop

does not supply them):

| Interface | Supplied under | Notes |
| --- | --- | --- |
| RA / DEC axis housings, dovetail saddle | BP-01 (6061-T6 machining) | The bearing outer races seat in the BP-01 housing bores (Ø68 H7 / Ø55 H7); the BP-02 journals carry the inner races. |
| Concrete pier, top plate, mount adapter | BP-03 (pier & foundation) | Not a turned-part interface. |
| Roll-off roof steelwork | BP-04 | Not a turned-part interface. |
| Harmonic drives, angular-contact bearings, on-axis encoders, counterweights, fasteners | BP-05 (COTS) | See §4 interface list. |

---

## 2. Data package the shop receives (per MIL-STD-31000A)

| Item | Format / standard | Role |
| --- | --- | --- |
| 3-D solid master | STEP ISO 10303 AP242 | CNC authority — governs as-modelled geometry. |
| Control drawings NW-TP-001 / -002 / -003 | PDF (drawing practices per ASME Y14.100; drawing types Y14.24; sheet & title block Y14.1) | Envelope + title block + key dimensions & features; bid control drawing. |
| SOW.md | Markdown | Per-part turning spec: journals to ISO 286 fits, CSF registers, concentricity/TIR, passivation, certs. |
| acceptance.md | Markdown | Dimensional acceptance of the journal fits + concentricity/run-out + passivation verification; FAI. |
| cut_list.csv (rows for NW-TP-001/002/003) | CSV/XLSX | Stock size, cut allowance, stock mass. |

Order of precedence. The STEP AP242 solid governs geometry; the drawing + SOW govern

tolerances, notes, finish, and material; where geometry and the tolerance package disagree, the **SOW

controls** and the bidder shall raise an RFI before cutting metal. All GD&T is interpreted per

ASME Y14.5-2018; general tolerances per ISO 2768-mK; fits per ISO 286; surface texture per

ASME Y14.36 / ASME B46.1.

---

## 3. Line-item summary (source: `partspec.parts_for('BP-02')` + `cut_list.csv`)

| Part no. | Name | Stock (round bar) | Qty | Stock mass | Finish | Drawing | cut_list row |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NW-TP-001 | Counterweight shaft (OPTIONAL — see §6) | Ø31.75 mm [1.250 in] × 457.2 mm [18.000 in] | 1 | 2.90 kg | Passivate ASTM A967 | NW-TP-001 | row 5 |
| NW-TP-002 | RA drive spindle / drawbar adapter | Ø88.9 mm [3.500 in] × 101.6 mm [4.000 in] | 1 | 5.05 kg | Passivate ASTM A967 | NW-TP-002 | row 6 |
| NW-TP-003 | DEC drive spindle / saddle stub | Ø76.2 mm [3.000 in] × 88.9 mm [3.500 in] | 1 | 3.24 kg | Passivate ASTM A967 | NW-TP-003 | row 7 |

Stock mass is the quantity ordered (stock volume × 303-SS density 8000 kg/m³), not finished net

mass. Cut allowance is 3.0 mm on stock. Material for all three: 303 stainless per ASTM A582.

The NW-TP-001 stock diameter is Ø31.75 mm (= 1.250 in exactly); the generated control sheet and

`cut_list.csv` display the mm value rounded to **Ø31.8 mm** — the same diameter.

---

## 4. Cross-package interfaces the shop must preserve

The bearing-race journals and the harmonic-drive registers are mating features to other

packages. The shop turns the BP-02 side; the fits and concentricity must be held so the mating

COTS/housing parts assemble and preload correctly:

| BP-02 feature | Nominal | Fit / carries | Mates to |
| --- | --- | --- | --- |
| NW-TP-002 bearing journal | Ø 40.0 mm [1.575 in] | j6 (ISO 286) — inner race of 7008 DB pair | NW-CO-003 (bore 40) → seats in NW-MH-001 bore Ø68 H7 |
| NW-TP-002 CSF-32 register | Ø 80.0 mm [3.150 in] | locating fit to CSF-32 output | NW-CO-001 (bore 80) → drive register in NW-MH-001 |
| NW-TP-002 bolt pattern | 8 × M4 on Ø104 PCD | bolts spindle to CSF-32 output flange | matches NW-MH-001 flange PCD (BP-01) |
| NW-TP-003 bearing journal | Ø 30.0 mm [1.181 in] | j6 (ISO 286) — inner race of 7006 DB pair | NW-CO-004 (bore 30) → seats in NW-MH-002 bore Ø55 H7 |
| NW-TP-003 CSF-25 register | Ø 64.0 mm [2.520 in] | locating fit to CSF-25 output | NW-CO-002 (bore 64) → drive register in NW-MH-002 |
| NW-TP-003 bolt pattern | 8 × M4 on Ø83 PCD | bolts spindle to CSF-25 output flange | matches NW-MH-002 flange PCD (BP-01) |
| NW-TP-001 stud / safety-stop | M12 stud (× 40) + M12 safety-stop | carries the counterweight stack | NW-CO-009 counterweights (OPTIONAL) |

**Remediation context.** The journals carry the inner races of **angular-contact 7008 (RA) / 7006

(DEC)** pairs in a **back-to-back (DB), preloaded** arrangement — the proven remediation of the

deep-groove 6008/6006 baseline. The stiffness/deflection proof showed the two deep-groove pairs

contributing **14.21″ (RA, 6008 @ 76.2 mm span) + 28.43″ (DEC, 6006 @ 63.5 mm span) = 42.64″ of the

43.52″ static pointing deflection — ~98% of the 5″-target FAIL**. Because **moment stiffness** (not

load rating) governs, the **journal fit, journal-shoulder squareness, and journal-to-register

concentricity** are the stiffness-critical turned features (see `SOW.md` §5 and MECHANICAL_DESIGN.md

§9; trade study item 8).

---

## 5. Bidder deliverables

Finished, passivated parts NW-TP-002 / -003 (qty 1 each), and NW-TP-001 **only if the

counterweighted variant is bid** (see §6).

Material certification / CoC for the 303 SS bar (ASTM A582), with heat/lot traceability and

chemistry (incl. sulphur — relevant to passivation, §6 / SOW.md §6).

Passivation certification — ASTM A967, method and acceptance test used.

First-Article Inspection (FAI) report per acceptance.md, including the journal-diameter

measurements, journal-to-register concentricity / TIR, and thread verification.

RFI / nonconformance log for any ASSUMED value the shop needed resolved.

---

## 6. ASSUMED design-intent — bidder / PE to confirm (NOT final)

The following are carried as ASSUMED design-intent in the parts registry and must not be

treated as released dimensions. The bidder/PE shall confirm before production:

Bearing-race journal fit class. The race journals are shown at j6 (Ø40 on NW-TP-002, Ø30 on

NW-TP-003) while the drawing's general note reads "journal diameters h6." Because the shaft

(inner ring) rotates relative to the gravity load, bearing-maker practice would call for a light

transition/interference fit (j6/k5/k6) rather than a clearance h6. The **exact grade (j6 vs h6 vs

k6) and the resulting preload are a PE call** — bidder/PE to confirm.

Spindle body diameters — NW-TP-002 Ø88.9 mm [3.500 in] and NW-TP-003 Ø76.2 mm [3.000 in] are

ASSUMED (registry provenance: "Body dia ASSUMED"); they set only the stock size and the flange

OD, not a mating fit.

Bolt patterns (8 × M4 on Ø104 / Ø83 PCD) — DERIVED to match the BP-01 housing flange PCDs, which

are themselves ASSUMED design-intent; confirm against the released CSF output-flange pattern.

CSF register fit & form — whether the Ø80 / Ø64 register is an OD pilot or a bore, and its fit

class to the harmonic-drive output (H7/h6 locating assumed) — ASSUMED, bidder/PE to confirm against

the CSF-32 / CSF-25 datasheet.

"Drawbar adapter" thread on NW-TP-002 — the drawtube/drawbar thread implied by the part name is

not dimensioned in the repo — ASSUMED design-intent.

Journal-shoulder axial location & squareness / preload land — the shoulder that sets DB preload

and its perpendicularity to the journal axis — ASSUMED, PE to set.

Passivation method & acceptance test — ASTM A967 nitric vs citric, and the verification test

(water-immersion / high-humidity / salt-spray / copper-sulphate) — ASSUMED; note 303 is a

free-machining, high-sulphur grade that passivates less readily than 304 (SOW.md §6).

Bearing-journal surface finish — part-level Ra 0.8 µm is on the sheet; bearing-race seats may

need Ra ≤ 0.4 µm — ASSUMED, bidder/PE to confirm.

NW-TP-001 inclusion — the selected counterweight-FREE GEM (torque proof, SF 2.5/2.6) omits

the counterweight shaft entirely; NW-TP-001 is OPTIONAL and bid only for the counterweighted

variant.

---

## 7. References

Parts registry: design/mechanical/tender/gen/partspec.py → parts_for('BP-02') (single source of truth).

BOM / cut list: design/mechanical/tender/bom/{master_bom,cut_list}.csv.

Control drawings: design/mechanical/tender/drawings/NW-TP-00{1,2,3}.svg.

Design basis: design/mechanical/MECHANICAL_DESIGN.md §9 (selected config + remediations; bearings

7008/7006 fix); design/mechanical/tradestudy/SECTION.md (selection rationale, item 8 bearing fix).

Master dossier: packages/BP-00_master_dossier/ (ITB, general SOW, standards & drawing registers).

Standards register: MIL-STD-31000A, ASME Y14.5-2018 / Y14.100 / Y14.24 / Y14.1 / Y14.36, ASME B46.1,

ISO 286, ISO 2768, ASTM A582 (303 SS), ASTM A967 (passivation).

# BP-02 — Statement of Work: Precision Turned Parts (303 SS)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-02 — Precision turned parts |
| Parts | NW-TP-001 (counterweight shaft, OPTIONAL), NW-TP-002 (RA drive spindle), NW-TP-003 (DEC drive spindle) |
| Process | CNC / manual turning (single-point) + light milling (bolt patterns, flats) |
| Material | 303 stainless steel per ASTM A582 |
| Finish | Passivate per ASTM A967 (nitric or citric) |
| Issue date / rev | 2026-08-06 / A |

Purpose. This SOW specifies the turning, tolerancing, finishing, and certification requirements for

the three turned parts. It is read with the STEP ISO 10303 AP242 solid master (CNC authority), the

NW-TP control drawings (PDF), and acceptance.md. All dimensions are dual-unit, **mm primary, inch in

brackets**, drawn from the parts registry (partspec.parts_for('BP-02')) and cut_list.csv — no

dimension herein is invented.

Standards applied. MIL-STD-31000A (TDP); ASME Y14.5-2018 (GD&T); ASME Y14.100 (drawing

practices), Y14.24 (drawing types), Y14.1 (sheet/title block); ASME Y14.36 & ASME B46.1 (surface

texture); ISO 286 (j6 / h6 / H7 fits); ISO 2768-mK (general tolerances); ASTM A582 (303

free-machining stainless bar); ASTM A967 (passivation of stainless).

---

## 1. General requirements (all parts)

Material & certification. 303 stainless bar per ASTM A582 (free-machining austenitic).

Furnish mill certification and Certificate of Conformance with heat/lot traceability and full

chemistry (the sulphur content governs passivation, §6). Mark each part with part number and

revision per ASME Y14.100.

General tolerance. ISO 2768-mK (medium, fine machining class) on all dimensions not

otherwise toleranced. Break sharp edges 0.3–0.5 mm [0.012–0.020 in]; deburr all threads and

cross-holes; no burrs into bearing seats.

Journal fits. Bearing-race journals and drive registers to ISO 286 — see per-part tables.

The general note is journal diameters h6; the two bearing-race journals are shown at j6 (a

transition fit to retain the rotating inner ring). See §5 and the ASSUMED-value register (§8).

Concentricity / run-out. The turned features share one datum axis: **journal-to-register (and

journal-to-journal) run-out shall not exceed 0.02 mm [0.0008 in] TIR** (registry _TOL_TURN

SOURCED value). Turn the mating diameters in one setup / between centres wherever practical to

hold it. The datum-axis assignment (which feature is Datum A) is ASSUMED — bidder/PE to confirm.

GD&T. Interpret all geometric callouts per ASME Y14.5-2018. Surface-texture symbols per

ASME Y14.36, values per ASME B46.1.

Stress / distortion. 303 work-hardens and can move on the last cut; **finish the bearing

journals last, in a light final pass, to hold the j6/h6 band and the 0.02 TIR (ASSUMED best

practice — bidder to propose**).

Surface finish. Part-level Ra 0.8 µm [32 µin] per the control drawing. Bearing-race journals

are typically held finer at Ra ≤ 0.4 µm [16 µin] (**ASSUMED design-intent — bidder/PE to

confirm**; see acceptance.md).

Finish sequence. Turn/mill complete, deburr, then passivate per ASTM A967 (§6). No plating.

---

## 2. NW-TP-002 — RA drive spindle / drawbar adapter

Drawing: NW-TP-002 (rev A). Stock: 303-SS round bar **Ø88.9 mm [3.500 in] × 101.6 mm

[4.000 in], cut allowance 3.0 mm, stock mass 5.05 kg (cut_list.csv row 6). Process: CNC turn +

mill**.

Function. Couples the CSF-32-100 harmonic-drive output to the RA axis and **carries the inner

race of the 7008 angular-contact pair**.

Datum reference frame (ASME Y14.5-2018, ASSUMED — PE to confirm):

Datum A — bearing-journal axis (the axis of rotation, Ø40 j6).

Datum B — CSF-32 register face (axial seat against the drive output).

Datum C — a designated bolt hole, for clocking the 8 × M4 pattern.

Critical features:

| Feature | Nominal (mm [in]) | Fit / tolerance | ISO 286 limits (representative) | Ra |
| --- | --- | --- | --- | --- |
| Bearing journal (7008 inner race) | Ø 40.0 [1.575] | j6 (ASSUMED grade) per ISO 286 | Ø39.995 – 40.011 (j6) *(h6 alt: 39.984 – 40.000)* | ≤0.4 µm (ASSUMED) |
| Journal-to-register concentricity | — | 0.02 mm TIR (SOURCED) | run-out to Datum A/B | — |
| Journal-shoulder squareness / preload land | — | ⟂ to Datum A *(value ASSUMED — PE)* | — | — |
| CSF-32 wave-gen / output register | Ø 80.0 [3.150] | locating fit (H7/h6 ASSUMED) | per CSF-32 datasheet | 0.8 µm |
| Body dia (flange OD) | Ø 88.9 [3.500] | ISO 2768-mK *(ASSUMED)* | — | 0.8 µm |
| Length | 101.6 [4.000] | ISO 2768-mK | — | 0.8 µm |
| Bolt pattern | 8 × M4 on Ø104 PCD | position *(ASSUMED)* | matches NW-MH-001 flange | — |
| Drawbar / drawtube thread | *(not dimensioned)* | ASSUMED design-intent | — | — |

Provenance / flags. Journal Ø40 = 7008 bore (remediation); CSF-32 register Ø80 =

P.RA_DRIVE.bore_m (SOURCED); body dia Ø88.9 ASSUMED; bolt pattern DERIVED to the NW-MH-001

flange PCD (itself ASSUMED). The journal fit grade (j6 vs h6) and the drawbar thread are

ASSUMED — bidder/PE to confirm.

Interfaces: journal → NW-CO-003 (7008 DB pair, bore 40) seating in NW-MH-001 bore Ø68 H7; register

→ NW-CO-001 (CSF-32, bore 80); bolt pattern → NW-MH-001 flange.

---

## 3. NW-TP-003 — DEC drive spindle / saddle stub

Drawing: NW-TP-003 (rev A). Stock: 303-SS round bar **Ø76.2 mm [3.000 in] × 88.9 mm

[3.500 in], cut allowance 3.0 mm, stock mass 3.24 kg (cut_list.csv row 7). Process: CNC turn +

mill**.

Function. Couples the CSF-25-80 harmonic-drive output to the DEC axis / saddle side and

carries the inner race of the 7006 angular-contact pair.

Datum reference frame (ASME Y14.5-2018, ASSUMED — PE to confirm):

Datum A — bearing-journal axis (DEC axis of rotation, Ø30 j6).

Datum B — CSF-25 register face.

Datum C — a designated bolt hole for clocking the 8 × M4 pattern.

Critical features:

| Feature | Nominal (mm [in]) | Fit / tolerance | ISO 286 limits (representative) | Ra |
| --- | --- | --- | --- | --- |
| Bearing journal (7006 inner race) | Ø 30.0 [1.181] | j6 (ASSUMED grade) per ISO 286 | Ø29.996 – 30.009 (j6) *(h6 alt: 29.987 – 30.000)* | ≤0.4 µm (ASSUMED) |
| Journal-to-register concentricity | — | 0.02 mm TIR (SOURCED) | run-out to Datum A/B | — |
| Journal-shoulder squareness / preload land | — | ⟂ to Datum A *(value ASSUMED — PE)* | — | — |
| CSF-25 wave-gen / output register | Ø 64.0 [2.520] | locating fit (H7/h6 ASSUMED) | per CSF-25 datasheet | 0.8 µm |
| Body dia (flange OD) | Ø 76.2 [3.000] | ISO 2768-mK *(ASSUMED)* | — | 0.8 µm |
| Length | 88.9 [3.500] | ISO 2768-mK | — | 0.8 µm |
| Bolt pattern | 8 × M4 on Ø83 PCD | position *(ASSUMED)* | matches NW-MH-002 flange | — |

Provenance / flags. Journal Ø30 = 7006 bore (remediation); CSF-25 register Ø64 =

P.DEC_DRIVE.bore_m (SOURCED); body dia Ø76.2 ASSUMED; bolt pattern DERIVED to the NW-MH-002

flange PCD (itself ASSUMED). The journal fit grade (j6 vs h6) is ASSUMED — bidder/PE to confirm.

Interfaces: journal → NW-CO-004 (7006 DB pair, bore 30) seating in NW-MH-002 bore Ø55 H7; register

→ NW-CO-002 (CSF-25, bore 64); bolt pattern → NW-MH-002 flange.

---

## 4. NW-TP-001 — Counterweight shaft (OPTIONAL)

Drawing: NW-TP-001 (rev A). Stock: 303-SS round bar **Ø31.75 mm [1.250 in] × 457.2 mm

[18.000 in]** (sheet displays Ø31.8 mm), cut allowance 3.0 mm, stock mass 2.90 kg (cut_list.csv

row 5). Process: CNC turn.

**OPTIONAL PART.** The selected topology is the **counterweight-FREE GEM** (torque proof SF 2.5/2.6;

deletes 15.4 kg + 29% RA inertia — MECHANICAL_DESIGN.md §9). NW-TP-001 (and its COTS counterweights

NW-CO-009) are supplied **only if the counterweighted variant is bid**. Price it as a separately

deletable line item.

Datum reference frame: Datum A = shaft OD axis.

| Feature | Nominal (mm [in]) | Tolerance | Ra |
| --- | --- | --- | --- |
| Shaft diameter | Ø 31.75 [1.250] | ISO 2768-mK | 0.8 µm |
| Length | 457.2 [18.000] | ISO 2768-mK | 0.8 µm |
| Stud end | M12 × 40 | 6g thread (ISO 2768) | — |
| Safety-stop thread | M12 | 6g thread | — |
| Root fillet | R3.0 [0.118] | — | — |

Provenance / flags. Diameter/length = P.COUNTERWEIGHTS (SOURCED); stud (M12 × 40), safety-stop

(M12), and root fillet (R3.0) are on the sheet. Thread class (6g) and the safety-stop feature detail

are ASSUMED — bidder/PE to confirm.

Interfaces: M12 stud → DEC-axis counterweight boss; carries NW-CO-009 counterweights (cast iron,

5 kg × 2 + 2.5 kg × 1). Safety-stop retains the weight stack against drop.

---

## 5. Bearing-journal callout block (stiffness remediation — grounding)

The two spindle journals (Ø40 j6 on NW-TP-002, Ø30 j6 on NW-TP-003) carry the inner races of the

**matched angular-contact pairs — 7008 (RA, bore 40 mm) and 7006 (DEC, bore 30 mm) in a back-to-back

(DB), preloaded arrangement (NW-CO-003 / NW-CO-004, BP-05). This is the proven remediation of the

deep-groove 6008/6006 baseline: the stiffness/deflection proof attributed 14.21″ (RA 6008 pair,

76.2 mm span) + 28.43″ (DEC 6006 pair, 63.5 mm span) = 42.64″ of the 43.52″ static pointing deflection

(~98%) — the dominant term in the 5″-target FAIL** (MECHANICAL_DESIGN.md §9; trade study item 8).

Because moment stiffness — not load rating — governs, the turned controls that matter are:

Journal fit to the inner race — a snug transition/interference (**j6 shown; grade ASSUMED, PE to

set**) so the rotating inner ring does not creep or lose preload.

Journal-shoulder squareness to the journal axis, and the axial location of the shoulder that

sets the DB preload — ASSUMED, PE to set.

Journal-to-register / journal-to-journal concentricity ≤ 0.02 mm TIR (SOURCED) and Ra ≤ 0.4 µm

(ASSUMED) on the race seats — turn in one setup / between centres to hold it.

Preload method (ground spacer/shim vs. clamped nut) — the housing (BP-01) and spindle shoulders

together set it; ASSUMED design-intent, bidder/PE to detail.

---

## 6. Finishing — passivation

Passivate per ASTM A967 after all machining and deburring. Nitric or citric process acceptable;

state the process on the certificate.

303 is a free-machining, high-sulphur grade: the manganese-sulphide inclusions passivate less

readily than 304/316 and can leave active sites. Use a process qualified for free-machining grades

and verify by an ASTM A967 acceptance test (water-immersion / high-humidity / salt-spray /

copper-sulphate) — the specific test is ASSUMED, bidder/PE to confirm.

Mask nothing that must stay dimensional — passivation is not a coating and does not build

thickness, so the j6/h6 journals are unaffected; still re-verify per acceptance.md.

Furnish a passivation certificate stating process, solution, and the acceptance test used.

---

## 7. Submittals & deliverables

Finished, passivated parts: NW-TP-002, NW-TP-003 (qty 1 each); NW-TP-001 only if bid.

Material cert / CoC (ASTM A582) with heat/lot traceability and chemistry.

Passivation certificate (ASTM A967) with process + acceptance test.

First-Article Inspection report per acceptance.md (journal diameters, concentricity/TIR, threads).

RFI log resolving every ASSUMED value before production.

---

## 8. ASSUMED design-intent register (this SOW)

| Item | Part(s) | Status |
| --- | --- | --- |
| Bearing-race journal fit grade (j6 shown vs h6 general note; k5/k6 alt for rotating inner ring) | NW-TP-002, -003 | ASSUMED — PE to set |
| Bearing-journal surface finish (Ra ≤ 0.4 µm) | NW-TP-002, -003 | ASSUMED — bidder/PE to confirm |
| Journal-shoulder squareness / axial preload land | NW-TP-002, -003 | ASSUMED — PE to set |
| Datum-axis assignment for the 0.02 TIR run-out | NW-TP-002, -003 | ASSUMED — bidder/PE to confirm |
| Spindle body diameters (Ø88.9 / Ø76.2) | NW-TP-002, -003 | ASSUMED design-intent |
| Bolt patterns (8 × M4 on Ø104 / Ø83 PCD) | NW-TP-002, -003 | DERIVED/ASSUMED — confirm vs CSF flange |
| CSF register form & fit class (OD pilot vs bore; H7/h6) | NW-TP-002, -003 | ASSUMED — confirm vs CSF datasheet |
| Drawbar / drawtube thread | NW-TP-002 | ASSUMED design-intent (not dimensioned) |
| Thread class (6g) & safety-stop detail | NW-TP-001 | ASSUMED — bidder/PE to confirm |
| Passivation method (nitric/citric) & acceptance test | all | ASSUMED — bidder/PE to confirm |
| NW-TP-001 inclusion (counterweight-free build omits it) | NW-TP-001 | OPTIONAL — bid separately deletable |

# BP-02 — Dimensional Acceptance Plan: Precision Turned Parts

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-02 — Precision turned parts |
| Parts | NW-TP-001 (OPTIONAL), NW-TP-002, NW-TP-003 |
| Method | Dimensional acceptance of the bearing-race journals + journal-to-register concentricity/run-out; thread gauging; passivation verification |
| Issue date / rev | 2026-08-06 / A |

Scope. This plan defines the inspection method and accept/reject criteria for BP-02. Because each

part has quantity 1, the First-Article Inspection (FAI) *is* the production acceptance. The

bearing-race journals (Ø40 j6 / Ø30 j6), the journal-to-register concentricity (0.02 mm TIR),

and the harmonic-drive registers (Ø80 / Ø64) are the critical characteristics and receive

100% verification; general dimensions are verified to ISO 2768-mK on the FAI. All limits are

dual-unit and derived from partspec / the NW-TP control drawings — nothing invented.

Standards. ASME Y14.5-2018 (datum alignment / GD&T interpretation); ISO 286 (j6 / h6 / H7 limits);

ISO 2768 (general tolerance & threads); ASME B46.1 (surface texture measurement); ASTM A967

(passivation verification); ISO 1 (20 °C reference temperature).

---

## 1. Inspection method

Diameters. Bearing journals and registers measured with **CMM or bench-centre + calibrated bore

micrometer / air gauge**, ≥ 3 axial stations × ≥ 4 angular positions; report least-squares diameter,

roundness, and taper.

Concentricity / run-out. Part supported between centres (or in matched V-blocks); journal

and register total indicated run-out (TIR) read with a dial/probe against the datum axis

(SOW.md §4). Datum-axis assignment per the FAI datum frame (ASSUMED — see §7).

Threads (NW-TP-001). M12 stud and safety-stop verified with go/no-go ring/plug gauges

(class 6g ASSUMED); root fillet R3.0 by radius gauge / optical comparator.

Surface finish. Profilometer per ASME B46.1 on journals, registers, and general OD.

Metrology environment: temperature-controlled at 20 °C per ISO 1; parts thermally soaked

before measurement (ASSUMED soak time — bidder to state).

Measurement uncertainty: CMM/gauge + fixturing uncertainty ≤ 10% of the tolerance band for

the j6 journals (gauge R&R / MSA evidence on request) — **ASSUMED acceptance gate, bidder/PE to

confirm**.

State of measurement: passivation is not a coating and does not build thickness; journals are

measured as delivered (post-passivation).

---

## 2. Acceptance criteria — NW-TP-002 (RA drive spindle)

| Characteristic | Nominal (mm [in]) | Accept limits | Method | Class |
| --- | --- | --- | --- | --- |
| Bearing journal Ø40 j6 (7008 race) | Ø40.0 [1.575] | Ø39.995 – 40.011 mm (j6, ASSUMED grade) | CMM / air gauge | Critical — 100% |
| Journal-to-register concentricity | — | ≤ 0.02 mm [0.0008 in] TIR | between centres, dial/probe | Critical — 100% |
| Journal roundness / taper | — | within the j6 band | CMM | Critical |
| Journal-shoulder squareness / preload land | — | per PE GD&T *(value ASSUMED)* | CMM | Critical |
| CSF-32 register Ø80 | Ø80.0 [3.150] | locating fit *(H7/h6 ASSUMED)* | CMM / micrometer | Major |
| Bolt pattern 8 × M4 on Ø104 PCD | Ø104.0 [4.094] | position *(ASSUMED)* | CMM | Major |
| Body dia Ø88.9 | Ø88.9 [3.500] | ISO 2768-mK *(ASSUMED)* | micrometer | Minor |
| Length | 101.6 [4.000] | ISO 2768-mK | calipers/CMM | Minor |
| Journal surface finish | — | Ra ≤ 0.4 µm [16 µin] *(ASSUMED)* | profilometer | Major |
| General surface finish | — | Ra 0.8 µm [32 µin] | profilometer | Minor |

## 3. Acceptance criteria — NW-TP-003 (DEC drive spindle)

| Characteristic | Nominal (mm [in]) | Accept limits | Method | Class |
| --- | --- | --- | --- | --- |
| Bearing journal Ø30 j6 (7006 race) | Ø30.0 [1.181] | Ø29.996 – 30.009 mm (j6, ASSUMED grade) | CMM / air gauge | Critical — 100% |
| Journal-to-register concentricity | — | ≤ 0.02 mm [0.0008 in] TIR | between centres, dial/probe | Critical — 100% |
| Journal roundness / taper | — | within the j6 band | CMM | Critical |
| Journal-shoulder squareness / preload land | — | per PE GD&T *(value ASSUMED)* | CMM | Critical |
| CSF-25 register Ø64 | Ø64.0 [2.520] | locating fit *(H7/h6 ASSUMED)* | CMM / micrometer | Major |
| Bolt pattern 8 × M4 on Ø83 PCD | Ø83.0 [3.268] | position *(ASSUMED)* | CMM | Major |
| Body dia Ø76.2 | Ø76.2 [3.000] | ISO 2768-mK *(ASSUMED)* | micrometer | Minor |
| Length | 88.9 [3.500] | ISO 2768-mK | calipers/CMM | Minor |
| Journal surface finish | — | Ra ≤ 0.4 µm [16 µin] *(ASSUMED)* | profilometer | Major |
| General surface finish | — | Ra 0.8 µm [32 µin] | profilometer | Minor |

## 4. Acceptance criteria — NW-TP-001 (counterweight shaft, OPTIONAL)

Inspect **only if the counterweighted variant is bid** (§ `SOW.md` §4). The selected build is

counterweight-free.

| Characteristic | Nominal (mm [in]) | Accept limits | Method | Class |
| --- | --- | --- | --- | --- |
| Shaft diameter | Ø31.75 [1.250] | ISO 2768-mK | micrometer | Minor |
| Length | 457.2 [18.000] | ISO 2768-mK | tape/CMM | Minor |
| Stud end thread | M12 × 40 | 6g go/no-go *(ASSUMED)* | ring gauge | Major |
| Safety-stop thread | M12 | 6g go/no-go *(ASSUMED)* | ring gauge | Major |
| Root fillet | R3.0 [0.118] | radius gauge | comparator | Minor |
| Surface finish | — | Ra 0.8 µm [32 µin] | profilometer | Minor |

---

## 5. Passivation verification (all parts)

| Characteristic | Requirement | Method | Class |
| --- | --- | --- | --- |
| Passivation | Per ASTM A967 (nitric or citric) | certificate + acceptance test | Critical — 100% |
| Free-iron / passivity check | Pass the stated ASTM A967 test | water-immersion / high-humidity / salt-spray / copper-sulphate *(specific test ASSUMED — bidder/PE to confirm)* | Critical |

**303 note.** Because 303 is a **free-machining, high-sulphur** grade, verify passivity with a test

qualified for free-machining stainless; report the process (solution, concentration, time,

temperature) and the acceptance-test result on the certificate (`SOW.md` §6).

---

## 6. Sampling & documentation

Critical characteristics (j6 journals, journal-to-register concentricity, registers, passivation):

100% — each part is qty 1, so FAI = production acceptance.

Major / Minor characteristics: verified on the FAI to ISO 2768-mK.

The bidder shall deliver, per part:

FAI report — every characteristic in §2–§5 with measured value vs. limit and pass/fail.

CMM / gauge raw output — probe data + datum alignment record (Y14.5 frame) + run-out traces.

Material certificate (ASTM A582) with heat/lot traceability and chemistry.

Passivation certificate (ASTM A967) with process + acceptance-test result.

Nonconformance / RFI dispositions for any ASSUMED value or out-of-tolerance condition.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Bidder QA |  |  |  |
| Owner / PE review |  |  |  |

---

## 7. ASSUMED-value register (do NOT treat as final)

The following acceptance values are ASSUMED design-intent — bidder/PE to confirm before they can be

applied as pass/fail gates:

| # | ASSUMED value | Part(s) |
| --- | --- | --- |
| 1 | Journal fit grade (j6 shown vs h6 general note; k5/k6 alt for rotating inner ring) | NW-TP-002, -003 |
| 2 | Bearing-journal surface finish Ra ≤ 0.4 µm | NW-TP-002, -003 |
| 3 | Journal-shoulder squareness / axial preload land | NW-TP-002, -003 |
| 4 | Datum-axis assignment for the 0.02 mm TIR run-out | NW-TP-002, -003 |
| 5 | CSF register fit class (H7/h6) and form (OD pilot vs bore) | NW-TP-002, -003 |
| 6 | Bolt-pattern position (8 × M4 on Ø104 / Ø83 PCD) | NW-TP-002, -003 |
| 7 | Spindle body diameters (Ø88.9 / Ø76.2) | NW-TP-002, -003 |
| 8 | Drawbar / drawtube thread | NW-TP-002 |
| 9 | Thread class (6g) & safety-stop detail | NW-TP-001 |
| 10 | Passivation method (nitric/citric) & specific acceptance test | all |
| 11 | CMM/gauge uncertainty gate (≤ 10% of tol band), soak time | all |

# Part II — BP-03 pier foundation

# BP-03 — Pier & Foundation (Reinforced Concrete + Structural Steel) — Bidder README

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-03 — Pier & foundation |
| Trade | Reinforced concrete (cast-in-place) + structural steel + light CNC |
| Parts | NW-PF-001, NW-PF-002, NW-PF-003, NW-PF-004 (4 line items; 3 fabrication control drawings) |
| Branch / project | design/mechanical-tender — NIGHTWATCH Observatory Mount & Roll-off Tender |
| Issue date | 2026-08-06 |
| Revision | A |
| Governing TDP standard | MIL-STD-31000A (Technical Data Package) |

This README is the entry point for the concrete/foundation contractor bidding BP-03. It defines the

scope, the data package the contractor receives, the bidder deliverables, the **PE-STAMP

GATE, and the items carried as ASSUMED design-intent**. Read it with SOW.md (per-part

specification) and acceptance.md (cylinder breaks, anchor pull, plumb/level) in this same folder.

---

## 0. PE-STAMP GATE — READ FIRST (this package is NOT releasable for construction)

**⚠ THE PIER AND FOUNDATION ARE ISSUED FOR PE REVIEW ONLY.**

**A licensed Professional Engineer, registered in the jurisdiction of the build site, MUST review,

size, and STAMP the reinforced-concrete pier, its reinforcement, its embedment, and the anchor

bolts BEFORE any permit is drawn or any concrete is placed.** Nothing in this package — dimensions,

rebar schedule, anchor sizing, embedment — is a released structural design. Every structural

quantity herein is either **SOURCED from the proven parametric model** (envelope geometry, f'c,

embedment) or **ASSUMED design-intent** (rebar schedule, anchor grade/count, cover, seismic

detailing) and is presented **for the PE to confirm, complete, and stamp** under the governing

building code and the referenced load standard.

Why a stamp is mandatory. The build site is a remote, seismically-active, high-desert Nevada

location (site datum 38.9 °N / −117.4 °W, elevation ~1800 m [~5900 ft]). Three structural loads

govern and are owner/PE responsibilities under ASCE 7:

| Load | Basis (design study) | What it drives |
| --- | --- | --- |
| Wind | ASCE 7 basic wind ~105 mph 3-sec gust, Risk Category I (survival, roof closed) | roof/enclosure hold-down, pier overturning |
| Snow | ~25 psf ground snow, high-desert @ ~1800 m | enclosure (BP-04), not the pier directly |
| Seismic | S_DS ≈ 0.5 g (Walker Lane vicinity) | pier base shear, anchorage, embedment |

The wind basic speed (105 mph) and seismic S_DS (0.5 g) are ASSUMED in the design study because

the repository was silent on them — they are **exactly the values the PE must set from the site's

ASCE 7 hazard data and stamp.** See MECHANICAL_DESIGN.md §7 (wind — FAIL/remediated) and §8

(pier — PASS) for the computed basis.

**No concrete is placed, and no anchor is cast, until the stamped drawings and the PE-approved

Inspection & Test Plan (acceptance.md) are in hand.**

---

## 1. Scope

BP-03 covers the telescope pier and its foundation interface — the cast-in-place reinforced-concrete

pier, the steel top plate grouted to it, the aluminium adapter plate that orients the mount to site

latitude, and the cast-in anchor-bolt set with its setting template. The contractor:

Places a cast-in-place reinforced-concrete pier (NW-PF-001) to f'c = 4000 psi (27.6 MPa) per

ACI 318 / ACI 301, with a rebar cage per the PE-stamped schedule (baseline 6 × #4 vertical +

#3 ties per ASTM A615 Gr60), structurally isolated from any building slab or footing.

Casts the anchor-bolt set (NW-PF-004, ASTM F1554 Gr36, per ACI 318 Ch.17) into the wet

pier via a fabricated setting template so the projecting bolts match the top-plate pattern.

Supplies the galvanized steel top plate (NW-PF-002, ASTM A36, hot-dip galv per ASTM A123)

and the anodized aluminium adapter plate (NW-PF-003, 6061-T6 per ASTM B209, Type III

hardcoat per MIL-A-8625F), or subcontracts their cut/machine scope.

Grouts, levels, and plumbs the plate stack, then inspects per acceptance.md (concrete cylinder

breaks, anchor proof/pull, plumb/level) and delivers a certified, PE-signed foundation.

Out of scope for BP-03 (separate packages — the pier *interfaces* to these but the contractor does

not supply them):

| Interface | Supplied under | Notes |
| --- | --- | --- |
| RA (polar) axis housing NW-MH-001 | BP-01 (mount head) | Bolts to the adapter plate NW-PF-003 (4 × M6). |
| Roll-off roof steelwork + wind hold-down anchor brackets NW-RR-006 | BP-04 | The 4× survival-wind roof hold-downs anchor the enclosure/building foundation, not the telescope pier (the pier is isolated). See §4. |
| Harmonic drives, bearings, encoders, fasteners | BP-05 (COTS) | Not a pier interface. |
| Enclosure/building foundation | Owner / site civil (not in this tender scope) | The pier passes through but is isolated from the building slab. |

---

## 2. Data package the contractor receives (per MIL-STD-31000A)

| Item | Format / standard | Role |
| --- | --- | --- |
| 3-D solid master (pier + plates) | STEP ISO 10303 AP242 | As-modelled geometry master. |
| Control drawings NW-PF-001 / -002 / -003 | PDF (drawing practices ASME Y14.100; drawing types Y14.24; sheet & title block Y14.1) | Envelope + title block + key dimensions; bid control drawing. |
| PE-stamped structural drawings | PDF (issued by owner's PE) | Governs for construction — supersedes the ASSUMED rebar/anchor/embedment values herein. |
| SOW.md | Markdown | Per-part spec: concrete, rebar, anchors, isolation, embedment, finishes. |
| acceptance.md | Markdown | Concrete cylinder breaks, anchor pull/proof, plumb/level, placement inspection. |
| cut_list.csv (rows NW-PF-001/002/003) | CSV/XLSX | Stock size, cut allowance, stock mass. |
| cots_schedule.csv (row NW-PF-004) | CSV/XLSX | Anchor-bolt buy item + template. |

Order of precedence. For the fabricated plates (NW-PF-002/-003) the **STEP AP242 solid

governs geometry; the drawing + SOW govern tolerances, finish, and material. For the

reinforced-concrete pier, the reinforcement, the embedment, and the anchor bolts, the PE-STAMPED

STRUCTURAL DRAWINGS GOVERN and supersede every number in this package.** Where any document disagrees,

the PE-stamped set controls and the bidder shall raise an RFI before placing concrete. General

tolerances per ISO 2768; plate GD&T per ASME Y14.5-2018; fits per ISO 286.

---

## 3. Line-item summary (source: `partspec.parts_for('BP-03')` + BOM/cut list)

| Part no. | Name | Material | Stock / size | Qty | Stock mass | Finish | Fab drawing |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NW-PF-001 | Reinforced-concrete telescope pier | Cast-in-place concrete f'c = 4000 psi (27.6 MPa) per ACI 318 / ACI 301 | Round pier Ø304.8 mm [12.000 in] × 1828.8 mm [72.000 in] overall | 1 | 320.26 kg (≈0.13 m³ [≈4.7 ft³ / ≈0.18 yd³] concrete) | none (formed) | NW-PF-001 |
| NW-PF-002 | Pier top plate | ASTM A36 structural steel | Plate 304.8 mm [12.000 in] × 304.8 mm [12.000 in] × 9.5 mm [0.375 in] | 1 | 6.94 kg | Hot-dip galvanize per ASTM A123 | NW-PF-002 |
| NW-PF-003 | Pier-to-mount adapter plate | 6061-T6 aluminium per ASTM B209 | Plate 254.0 mm [10.000 in] × 254.0 mm [10.000 in] × 19.1 mm [0.750 in] | 1 | 3.32 kg | Type III hardcoat anodize per MIL-A-8625F | NW-PF-003 |
| NW-PF-004 | Anchor-bolt set + template | ASTM F1554 Gr36 galvanized | 4 × Ø19.05 mm [0.750 in] × 304.8 mm [12.000 in] anchor bolts + setting template | 1 | — (buy + fabricate) | Hot-dip galvanize per ASTM A123 | none (buy item; template bidder-detailed) |

Pier stock mass is the quantity ordered (stock envelope volume × concrete density 2400 kg/m³),

not a formed-net figure; the ≈0.13 m³ concrete volume is a **pour-planning estimate derived from the

Ø304.8 × 1828.8 mm envelope** — confirm against the stamped forming detail. Plate cut allowance is

3.0 mm on stock. NW-PF-004 carries no fabrication control drawing — the bolts are purchased to

ASTM F1554 and the setting template is fabricated by the bidder to the stamped top-plate/adapter hole

pattern (see SOW.md §5).

---

## 4. Cross-package interfaces the contractor must preserve

The plate stack chains the pier up to the mount head. Bottom-to-top:

| Level | Feature | Mates to | Part |
| --- | --- | --- | --- |
| Pier top | 4 × cast-in anchor bolts, projection 50.0 mm [1.969 in] | Top-plate anchor holes | NW-PF-004 → NW-PF-002 |
| Top plate | 4 × Ø20.6 mm [Ø0.81 in] anchor holes (clearance for Ø0.75 F1554) | Cast-in anchors NW-PF-004 | NW-PF-002 |
| Top plate → adapter | Centre hole pattern 4 × Ø11.2 mm [Ø0.44 in] | Adapter pier-plate pattern | NW-PF-002 ↔ NW-PF-003 |
| Adapter → RA housing | 4 × M6 pattern + centre bore Ø90.0 mm [3.543 in] | RA (polar) axis housing | NW-PF-003 → NW-MH-001 (BP-01) |
| Adapter wedge | Latitude tilt to 38.9° (wedge/shim, bidder to detail) | Sets polar axis to site latitude | NW-PF-003 |

**Wind hold-down clarification (important).** The **9.2 kN survival-wind roof uplift** is resisted by

the **4× wind hold-down anchor brackets NW-RR-006 (BP-04)**, which anchor the **enclosure/building

foundation** — because the design study assumes the **telescope pier is structurally isolated from

the enclosure** (standard observatory practice, to keep vibration off the optics). The BP-03

anchor-bolt set NW-PF-004 casts into the **pier** and resists the **mount overturning + seismic**

demand (pier proof §8). The registry nonetheless **sizes NW-PF-004 against the ~9.2 kN uplift number

as a bounding case** — see §6 and `SOW.md` §5. **Where each anchor group lands, and the final anchor

capacity, are PE coordination items — PE to confirm.**

---

## 5. Bidder deliverables

Finished pier (NW-PF-001), top plate (NW-PF-002), adapter plate (NW-PF-003), and cast anchor set +

template (NW-PF-004), installed, grouted, leveled, and plumbed.

Concrete submittals — approved mix design (f'c = 4000 psi per ACI 301), batch tickets, and

cylinder break reports (7-day and 28-day) per acceptance.md.

Reinforcement certs — mill certs for the #4 / #3 bar (ASTM A615 Gr60) and a rebar-placement /

cover inspection record against the stamped cage.

Anchor-bolt certs — mill cert / CoC for the ASTM F1554 Gr36 bolts, galvanize cert (ASTM A123),

and the anchor proof/pull test record per acceptance.md.

Steel & aluminium plate certs — A36 material cert + galvanize (ASTM A123) coating-thickness

record for NW-PF-002; 6061-T6 cert (ASTM B209) + Type III anodize cert (MIL-A-8625F) for NW-PF-003.

Plumb / level survey — pier plumb ≤ 1:200 and top-of-plate level ≤ 0.5° per acceptance.md.

PE sign-off — the PE-stamped structural drawings and the PE's field-inspection/hold-point

sign-offs (rebar, embedment, pour, anchor set).

RFI / nonconformance log resolving every ASSUMED value before it is built.

---

## 6. ASSUMED design-intent — bidder / PE to confirm (NOT final)

Carried as ASSUMED design-intent in the parts registry; not released dimensions. The PE shall

confirm/complete and stamp before construction:

Rebar schedule — baseline 6 × #4 vertical + #3 ties @ 12 in [304.8 mm] oc (ASTM A615 Gr60)

is ASSUMED design-intent; bar size/count, tie spacing, seismic hoop detailing, splices, and

concrete cover (ASSUMED ~76 mm [3 in] cast against earth per ACI 318) are PE to set.

Anchor-bolt sizing — 4 × Ø0.75 in [19.05 mm] F1554 Gr36, embedment 304.8 mm [12.000 in],

projection 50.0 mm [1.969 in], is ASSUMED per ACI 318 Ch.17; final diameter, grade, embedment,

edge distance, and count are **PE to size for the governing wind/seismic uplift (~9.2 kN roof-uplift

bounding case; net anchor demand 7.4 kN → 4× 2 klbf gives SF 3.9).**

Embedment vs frost — 914.4 mm [36.000 in] embedment is SOURCED; it exceeds the ASSUMED

central-NV frost line of 0.3–0.6 m [12–24 in] (SF ≈ 1.52). PE to confirm the site frost depth and

any bearing/bell-footing detail.

Latitude wedge on NW-PF-003 — the 38.9° polar-axis tilt (wedge or shim set) is **ASSUMED

design-intent; adapter geometry is not fixed in the repo** — bidder to detail, PE to confirm.

Wind speed / seismic parameters — basic wind 105 mph and S_DS 0.5 g are **ASSUMED (ASCE 7);

PE to set from site hazard data.**

Grout, leveling nuts, and isolation gap detail between pier and any building slab — ASSUMED;

bidder/PE to detail (the pier must not bear on or bond to the slab).

---

## 7. References

Parts registry: design/mechanical/tender/gen/partspec.py → parts_for('BP-03') (single source of truth).

BOM / cut list / COTS: design/mechanical/tender/bom/{master_bom,cut_list,cots_schedule}.csv.

Control drawings: design/mechanical/tender/drawings/NW-PF-00{1,2,3}.svg.

Design basis: design/mechanical/MECHANICAL_DESIGN.md §7 (wind loads — FAIL/remediated),

§8 (pier/foundation — PASS, governing SF 6.8); design/mechanical/tradestudy/SECTION.md item 5

(pier — Concrete Sonotube baseline retained).

Standards register: MIL-STD-31000A; ACI 318 (Ch.17 anchoring), ACI 301 (concrete spec); ASCE 7

(wind/snow/seismic); ASTM A615 Gr60 (rebar), ASTM F1554 Gr36 (anchor bolts), ASTM A36 (steel),

ASTM A123 (hot-dip galvanize), ASTM B209 (6061-T6), MIL-A-8625F (Type III anodize);

ASME Y14.5-2018 / Y14.100 / Y14.24 / Y14.1; ISO 286; ISO 2768.

# BP-03 — Statement of Work: Pier & Foundation (Reinforced Concrete + Structural Steel)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-03 — Pier & foundation |
| Parts | NW-PF-001 (RC pier), NW-PF-002 (top plate), NW-PF-003 (adapter plate), NW-PF-004 (anchor set + template) |
| Process | Cast-in-place reinforced concrete; laser/waterjet + drill (steel plate); CNC mill (aluminium plate); buy + template (anchors) |
| Site datum | 38.9 °N / −117.4 °W, elevation ~1800 m [~5900 ft], remote high-desert Nevada, seismically active |
| Issue date / rev | 2026-08-06 / A |

## PE-STAMP GATE

**The reinforced-concrete pier (NW-PF-001), its reinforcement, its embedment, and the anchor-bolt set

(NW-PF-004) are ISSUED FOR PE REVIEW.** A **licensed Professional Engineer**, registered in the

build-site jurisdiction, **must review, size, complete, and STAMP** these items under the governing

building code and **ASCE 7** (wind/snow/seismic) **before any permit is issued or any concrete is

placed.** All structural quantities below are **SOURCED envelope/material values** or **ASSUMED

design-intent** presented for the PE — none is a released structural design.

Purpose. This SOW specifies the concrete, reinforcement, anchorage, isolation, embedment,

finishing, and certification requirements for the four BP-03 parts. It is read with the PE-stamped

structural drawings (which govern for construction), the STEP ISO 10303 AP242 solids (plate

geometry), the NW-PF control drawings (PDF), and acceptance.md. All dimensions are dual-unit,

mm primary, inch in brackets, drawn from the parts registry (partspec.parts_for('BP-03')) and

the BOM/cut list — no dimension herein is invented.

Standards applied. MIL-STD-31000A (TDP); ACI 318 (structural concrete, incl. Ch.17

anchoring-to-concrete); ACI 301 (specifications for structural concrete); ASCE 7

(wind/snow/seismic loads); ASTM A615 Gr60 (deformed reinforcing bar); ASTM F1554 Gr36 (anchor

bolts); ASTM A36 (structural steel); ASTM A123 (hot-dip galvanize); ASTM B209 (6061-T6

plate); MIL-A-8625F (Type III hardcoat anodize); ASME Y14.5-2018 / Y14.100 / Y14.24 / Y14.1

(plate drawings); ISO 286 (fits); ISO 2768 (general tolerances). Concrete field/lab test

methods are those invoked by ACI 301 — see acceptance.md.

---

## 1. General requirements (all parts)

PE authority. The PE-stamped structural drawings supersede every rebar, anchor, embedment, and

reinforcement value in this SOW. Where this SOW and the stamped set disagree, **the stamped set

controls**; the bidder shall RFI before placing concrete.

Materials & certification. Furnish mill certs / CoC with heat/lot traceability for: the concrete

mix (ACI 301 approved mix design, f'c = 4000 psi), the reinforcing bar (ASTM A615 Gr60), the anchor

bolts (ASTM F1554 Gr36), the A36 plate, and the 6061-T6 plate (ASTM B209). Mark fabricated plates

with part number and revision per ASME Y14.100.

General tolerance. Plate dimensions to ISO 2768-mK; concrete workmanship tolerances per

ACI 117 as invoked by ACI 301 (ASSUMED — PE/bidder to confirm the tolerance class).

Isolation (MANDATORY). The pier is structurally isolated from any building slab, footing, or

floor — no bearing, no bond, no shared reinforcement. Maintain an isolation gap/joint (compressible

filler) around the pier where it passes any slab (detail bidder/PE to confirm). This keeps floor

footfall and enclosure vibration off the optical train.

Embedment vs frost. Pier embedment 914.4 mm [36.000 in] (SOURCED) shall be verified by the PE

to exceed the site frost depth (ASSUMED 0.3–0.6 m [12–24 in] for central-NV high desert;

SF ≈ 1.52) and to satisfy seismic/overturning fixity.

Cold-joint / lift control, curing, and hot/cold-weather placement per ACI 301.

---

## 2. NW-PF-001 — Reinforced-concrete telescope pier

Drawing: NW-PF-001 (rev A). Envelope: round pier **Ø304.8 mm [12.000 in] × 1828.8 mm

[72.000 in]** overall (height above grade 914.4 mm [36.000 in] + embedment 914.4 mm [36.000 in]).

Stock/pour mass: 320.26 kg (≈0.13 m³ [≈4.7 ft³ / ≈0.18 yd³] concrete — pour-planning estimate

from the envelope; cut_list.csv row NW-PF-001). Material: cast-in-place concrete **f'c = 4000 psi

(27.6 MPa) per ACI 318 / ACI 301**.

Controlling dimensions (SOURCED = P.PIER):

| Feature | Nominal (mm [in]) | Source |
| --- | --- | --- |
| Diameter | Ø 304.8 [12.000] | SOURCED |
| Height above grade | 914.4 [36.000] | SOURCED |
| Embedment | 914.4 [36.000] | SOURCED |
| Overall length | 1828.8 [72.000] | SOURCED |
| f'c | 4000 psi (27.6 MPa) | SOURCED |

Reinforcement schedule (ASSUMED design-intent — PE to confirm/complete/stamp):

| Item | Baseline callout | Bar dia (mm [in]) | Standard | Status |
| --- | --- | --- | --- | --- |
| Vertical bars | 6 × #4 | Ø12.7 [0.500] | ASTM A615 Gr60 | ASSUMED — PE to set count/size |
| Ties / hoops | #3 @ 12 in [304.8 mm] oc | Ø9.5 [0.375] | ASTM A615 Gr60 | ASSUMED — PE to set spacing + seismic hoop detail |
| Clear cover | ~76 mm [3.00 in] cast against earth | — | ACI 318 §20.5 | ASSUMED — PE to confirm |
| Splices / development / hooks | per ACI 318 Ch.25 | — | ACI 318 | PE to detail |

**ASSUMED design-intent — bidder/PE to confirm.** The rebar cage (6 × #4 vertical, #3 ties), cover,

tie spacing, seismic hoop confinement, and lap splices are **ASSUMED**. In a Walker-Lane-vicinity

seismic zone (S_DS ≈ 0.5 g, ASSUMED) the transverse reinforcement/confinement detailing is a

**PE-stamped** decision. The design study models the pier as an unreinforced circular cantilever for

tilt/frequency (concrete SF 111 compression / 13.8 tension) — reinforcement is required by code for

ductility/anchorage regardless of the low computed stress.

Structural basis (from MECHANICAL_DESIGN.md §8 — pier PASS, governing SF 6.8):

| Quantity | Value | Note |
| --- | --- | --- |
| Pier pointing tilt @ 35 mph gust | 0.70″ | vs 5″ budget → SF 7.2 |
| Pier first mode | 151.9 Hz | vs 10 Hz target → SF 15.2 |
| Seismic overturning SF (embed + weight) | 7.0 | dead-weight-only 0.81 → embedment governs |
| Sliding SF (passive / base shear) | 6.8 | governing SF |
| Concrete net compression / f'c | SF 111 | — |
| Concrete net tension / modulus of rupture | SF 13.8 | f_r = 0.62√f'c = 3.26 MPa (ASSUMED code value) |
| Embedment / frost depth | SF 1.52 | 0.914 m vs ASSUMED 0.6 m frost |

Workmanship tolerances (drawing): plumb ≤ 1:200; top-of-pier level ≤ 0.5°. Anchor cage +

setting template (NW-PF-004) cast integrally — see §5.

Provenance / flags. Ø/height/embed/f'c = P.PIER (SOURCED); rebar schedule **ASSUMED

design-intent (PE to confirm). REQUIRES PE STAMP.**

---

## 3. NW-PF-002 — Pier top plate

Drawing: NW-PF-002 (rev A). Stock: A36 plate **304.8 mm [12.000 in] × 304.8 mm [12.000 in] ×

9.5 mm [0.375 in]**, cut allowance 3.0 mm, stock mass 6.94 kg (cut_list.csv row NW-PF-002).

Process: laser/waterjet cut + drill. Finish: hot-dip galvanize per ASTM A123 (after all

cutting/drilling).

| Feature | Nominal (mm [in]) | Tolerance | Note |
| --- | --- | --- | --- |
| Side (square) | 304.8 [12.000] | ISO 2768-mK | matches pier diameter |
| Thickness | 9.5 [0.375] | ISO 2768-mK | A36 plate |
| Anchor holes | 4 × Ø20.6 [Ø0.81] | ± 0.25 mm pattern | clearance for Ø0.75 F1554 (NW-PF-004) |
| Centre pattern | 4 × Ø11.2 [Ø0.44] | ± 0.25 mm pattern | matches NW-PF-003 adapter |
| Surface finish | Ra 3.2 µm [125 µin] | — | cut faces |

Notes. Grouted onto the pier over the cast-in anchor bolts, then leveled and torqued with

leveling/plate nuts (bidder to detail; leveling-nut vs full-grout method ASSUMED — PE to confirm).

Galvanize per ASTM A123 with coating-thickness record; ream/retap holes after galvanize as needed to

clear the anchors and the Ø0.44 pattern.

Provenance / flags. Side/thickness = P.PIER (SOURCED); hole patterns DERIVED to match

NW-PF-004 (Ø0.81) and NW-PF-003 (Ø0.44) → hole positions **ASSUMED design-intent, bidder/PE to

confirm** against the stamped anchor layout.

---

## 4. NW-PF-003 — Pier-to-mount adapter plate

Drawing: NW-PF-003 (rev A). Stock: 6061-T6 plate **254.0 mm [10.000 in] × 254.0 mm [10.000 in]

× 19.1 mm [0.750 in]**, cut allowance 3.0 mm, stock mass 3.32 kg (cut_list.csv row NW-PF-003).

Process: CNC mill. Finish: **Type III hardcoat anodize, 0.002 in, Class 1 (clear) per

MIL-A-8625F** (after machining; mask bores/threads).

| Feature | Nominal (mm [in]) | Tolerance | Note |
| --- | --- | --- | --- |
| Side (square) | 254.0 [10.000] | ISO 2768-mK | — |
| Thickness | 19.1 [0.750] | ISO 2768-mK | — |
| RA-housing pattern | 4 × M6 | position *(ASSUMED)* | matches NW-MH-001 (BP-01) |
| Pier-plate pattern | 4 × Ø11.2 [Ø0.44] | position *(ASSUMED)* | matches NW-PF-002 |
| Centre bore | Ø 90.0 [3.543] | H8 pilot *(ASSUMED)* | cable/drawbar clearance |
| Face flatness | ▱ 0.05 mm to mounting face | per Y14.5 | mount seating |
| Surface finish | Ra 3.2 µm [125 µin] | — | — |

**ASSUMED design-intent — bidder/PE to confirm.** The adapter **bridges the 12×12 in pier plate to

the 8×8 in RA housing and provides the latitude wedge to orient the polar (RA) axis to the site

latitude 38.9°** (wedge plate or shim set). **Adapter geometry (patterns, centre bore, wedge angle)

is not fixed in the repository** — it is ASSUMED design-intent; the bidder details the wedge/shim and

the PE confirms. Preserve the 4 × M6 RA-housing pattern and the 4 × Ø0.44 pier-plate pattern so the

stack assembles.

Provenance / flags. ASSUMED design-intent — adapter geometry not in repo (bridges 12×12 plate to

8×8 housing). Levels/orients the RA axis to site latitude 38.9° (wedge or shim set, bidder to detail).

---

## 5. NW-PF-004 — Anchor-bolt set + setting template

Buy + fabricate (no fabrication control drawing SVG). Anchors: **4 × Ø19.05 mm [0.750 in] ×

304.8 mm [12.000 in], ASTM F1554 Gr36, hot-dip galvanized per ASTM A123**, cast into the wet

pier per ACI 318 Ch.17 (anchoring to concrete). Projection 50.0 mm [1.969 in] above the pier

top. Template: rigid setting template (ASSUMED 0.25 in [6.35 mm] plywood/ply-steel), hole position

tolerance 0.02 (drawing callout), matching the NW-PF-002 anchor pattern.

| Feature | Nominal (mm [in]) | Standard | Status |
| --- | --- | --- | --- |
| Bolt diameter | Ø 19.05 [0.750] | ASTM F1554 Gr36 | ASSUMED — PE to size |
| Embedment (into pier) | 304.8 [12.000] | ACI 318 Ch.17 | ASSUMED — PE to size |
| Projection | 50.0 [1.969] | — | for plate + nut stack |
| Count | 4 | — | ASSUMED — PE to set |
| Template hole tolerance | ± 0.02 mm pattern | — | so bolts drop through NW-PF-002 |

**Anchor sizing tied to the wind-uplift number — PE to confirm (per task + registry provenance).**

The registry sizes NW-PF-004 against the governing **survival-wind roof-uplift** case from

`MECHANICAL_DESIGN.md` §7: **roof gross uplift 9.2 kN (9163 N)** minus roof self-weight 1765 N →

**net anchor demand 7.4 kN (7398 N)**; **4× 2 klbf [≈8.9 kN] anchors → capacity 35.6 kN → SF 3.9**

(the wind remediation). **However:** the design study assumes the **telescope pier is isolated from

the enclosure**, so the **9.2 kN roof uplift is actually carried by the enclosure/building hold-downs

(NW-RR-006, BP-04), not the pier.** The pier anchors NW-PF-004 resist the **mount overturning +

seismic** demand (base shear 1008 N, overturning 673.8 Nm; embedment governs). The 9.2 kN figure is

retained as the **bounding tension case** for anchor selection. **Final anchor diameter, grade,

embedment, edge distance, count, and the pier-vs-enclosure anchor split are ASSUMED design-intent —

the PE shall size and stamp them per ACI 318 Ch.17 and ASCE 7.**

Setting procedure. Position the template on the form; hang the 4 anchors plumb at the specified

projection; verify pattern against NW-PF-002 before the pour; place concrete; do not disturb until

initial set; strip template after cure. Cast integrally with the pier — no post-installed anchors

unless the PE approves and re-specifies to ACI 318 Ch.17 post-installed provisions.

Provenance / flags. ASSUMED design-intent per ACI 318 Ch.17 (PE to size for wind/seismic uplift

~9.2 kN). Cast into pier via template; sizing tied to the wind proof roof/pier uplift — **PE to

confirm.**

---

## 6. Finishing

| Part | Finish | Standard | Notes |
| --- | --- | --- | --- |
| NW-PF-001 pier | formed concrete, cured | ACI 301 | rub/patch form-tie holes; no coating unless PE specifies |
| NW-PF-002 top plate | hot-dip galvanize | ASTM A123 | after cut/drill; coating-thickness record; clear holes post-dip |
| NW-PF-003 adapter | Type III hardcoat anodize 0.002 in, Class 1 (clear) | MIL-A-8625F | after machining; mask centre bore + threads |
| NW-PF-004 anchors | hot-dip galvanize | ASTM A123 | full-length; protect threads/projection during pour |

---

## 7. Submittals & deliverables

Installed pier + plate stack + cast anchor set (NW-PF-001..004), leveled and plumbed.

Concrete: ACI 301 approved mix design, batch tickets, 7-day + 28-day cylinder break reports

(acceptance.md), slump/air records.

Reinforcement: ASTM A615 Gr60 mill certs + rebar-placement/cover inspection record vs the

stamped cage.

Anchors: ASTM F1554 Gr36 mill cert/CoC, ASTM A123 galvanize cert, **anchor proof/pull test

record**.

Plates: A36 cert + ASTM A123 coating-thickness (NW-PF-002); 6061-T6 cert (ASTM B209) + Type III

anodize cert (NW-PF-003).

Plumb/level survey (≤ 1:200 plumb; ≤ 0.5° top level).

PE-stamped structural drawings + PE field hold-point sign-offs (rebar, embedment, anchor set,

pour).

RFI/NCR log resolving every ASSUMED value before construction.

---

## 8. ASSUMED design-intent register (this SOW)

| # | Item | Part(s) | Status |
| --- | --- | --- | --- |
| 1 | Rebar schedule (6 × #4 vert + #3 ties), cover, seismic hoop detailing, splices | NW-PF-001 | ASSUMED — PE to set & stamp |
| 2 | Anchor sizing (Ø0.75 F1554 Gr36, embed, projection, count) vs ~9.2 kN uplift | NW-PF-004 | ASSUMED — PE to size (ACI 318 Ch.17) |
| 3 | Pier-vs-enclosure anchor split (9.2 kN roof uplift lands on BP-04 hold-downs) | NW-PF-004 / NW-RR-006 | ASSUMED — PE coordination |
| 4 | Site frost depth vs embedment; bearing/bell detail | NW-PF-001 | ASSUMED — PE to confirm |
| 5 | Wind speed (105 mph) / seismic S_DS (0.5 g) | all | ASSUMED (ASCE 7) — PE to set |
| 6 | Latitude wedge angle + adapter geometry (patterns, centre bore) | NW-PF-003 | ASSUMED — bidder to detail, PE to confirm |
| 7 | Grout/leveling-nut method + pier-slab isolation gap detail | NW-PF-001/002 | ASSUMED — bidder/PE to detail |
| 8 | Top-plate hole positions (Ø0.81 anchor, Ø0.44 adapter) | NW-PF-002 | ASSUMED — confirm vs stamped anchor layout |
| 9 | Concrete workmanship tolerance class (ACI 117) | NW-PF-001 | ASSUMED — PE/bidder to confirm |

# BP-03 — Inspection & Test / Acceptance Plan: Pier & Foundation

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-03 — Pier & foundation |
| Parts | NW-PF-001 (RC pier), NW-PF-002 (top plate), NW-PF-003 (adapter plate), NW-PF-004 (anchor set) |
| Method | Concrete cylinder breaks + slump/air; anchor proof/pull test; plumb/level survey; rebar-placement & cover inspection; galvanize/anodize coating verification; plate dimensional check |
| Issue date / rev | 2026-08-06 / A |

## PE-STAMP GATE — this plan is not executable until the PE approves it

**The reinforced-concrete pier and anchor set are ISSUED FOR PE REVIEW.** This Inspection & Test Plan

(ITP) and its accept/reject limits are **provisional pending the PE-stamped structural drawings.**

The PE sets the final f'c acceptance basis, the reinforcement/cover inspection criteria, the anchor

proof load, and owns the **field hold points** below. **No concrete is placed and no anchor is cast

until the stamped drawings and the PE-approved ITP are in hand.**

Scope. This plan defines the inspection methods and accept/reject criteria for BP-03. The concrete

strength (cylinder breaks), the anchor proof/pull, and the pier plumb/level are the **critical

characteristics**. All limits are dual-unit and derived from partspec / the NW-PF control drawings —

nothing invented. Concrete field/lab test methods are those invoked by ACI 301; where a specific

ASTM C-series method is named it is the method ACI 301 calls up (flagged PE to confirm if outside

the tender's standards register).

Standards. ACI 318 (structural concrete; Ch.17 anchoring); ACI 301 (concrete spec, invokes the

field/lab test methods and ACI 117 tolerances); ASCE 7 (loads — PE); ASTM A615 Gr60 (rebar);

ASTM F1554 Gr36 (anchors); ASTM A123 (galvanize coating thickness); ASTM B209 (6061-T6);

MIL-A-8625F (anodize); ASME Y14.5-2018 (plate GD&T); ISO 286 / ISO 2768 (fits / general tolerance);

ISO 1 (20 °C metrology reference for the plates).

---

## 1. Field hold points (PE / owner sign-off required to proceed)

| # | Hold point | Verify before proceeding | Sign-off |
| --- | --- | --- | --- |
| H1 | Excavation / embedment | Depth ≥ 914.4 mm [36.000 in] and ≥ site frost depth; bearing soil per PE | PE |
| H2 | Rebar cage set | Bar size/count/spacing, cover, splices, seismic hoops vs stamped cage | PE |
| H3 | Anchor template set | 4 × F1554 plumb, projection 50.0 mm [1.969 in], pattern vs NW-PF-002 | PE |
| H4 | Pre-pour | Forms, isolation gap from any slab, cleanliness, mix delivered = approved mix | PE / owner |
| H5 | Pour + cylinders cast | Placement, consolidation, cylinders fabricated & cured | Inspector |
| H6 | Strip / cure complete | Form strip, cure duration, surface finish | Bidder QA |
| H7 | 28-day strength + anchor proof | f'c met; anchor proof/pull passed; plumb/level survey | PE |

---

## 2. Concrete — cylinder breaks & fresh-concrete tests (NW-PF-001)

Specified strength: f'c = 4000 psi (27.6 MPa) at 28 days, per ACI 318 / ACI 301.

| Test | Method (invoked by ACI 301) | Frequency | Accept criterion |
| --- | --- | --- | --- |
| Compressive strength | cast + cure standard cylinders; lab break (ACI 301 → ASTM C31 fabrication, ASTM C39 test) *(method PE to confirm)* | min. 1 set (pier is a single small pour); set = 2× 28-day + 1× 7-day + 1 spare | ACI 318 §26.12: avg of any 3 consecutive tests ≥ f'c and no single test < f'c − 500 psi [3.4 MPa] *(PE to confirm basis for a single-pour element)* |
| 7-day break (info) | as above, 7-day | 1 cylinder | typically ≥ 65–70% f'c *(ASSUMED — trend indicator, not accept gate)* |
| Slump | ACI 301 → ASTM C143 | each load | per approved mix design ± tolerance *(PE to set)* |
| Air content | ACI 301 → ASTM C231 | each load (if air-entrained) | per approved mix *(PE to set — may be N/A)* |
| Temperature | ACI 301 (fresh-concrete temp) | each load | within hot/cold-weather limits (ACI 301) |

Notes. Cylinders cured and broken by an approved testing lab. Because the pier is a **single small

pour (≈0.13 m³ [≈4.7 ft³])**, the sampling frequency and the single-element acceptance basis are

PE to confirm (a small element may use a reduced set with the PE accepting the risk). **Concrete

below f'c → PE disposition** (core testing per ASTM C42, load evaluation, or reject) — no

self-disposition by the bidder.

---

## 3. Reinforcement placement & cover (NW-PF-001)

| Characteristic | Criterion | Method | Class |
| --- | --- | --- | --- |
| Bar size / grade | #4 vertical, #3 ties, ASTM A615 Gr60 (or PE-stamped substitute) | mill cert + tape/gauge | Critical |
| Bar count | 6 × vertical (or PE-stamped) | count at H2 | Critical |
| Tie spacing | #3 @ 12 in [304.8 mm] oc (or PE-stamped) | tape at H2 | Major |
| Clear cover | ~76 mm [3.00 in] cast against earth *(ASSUMED — PE to set)* | cover meter / spacers | Critical |
| Splices / hooks / development | per ACI 318 Ch.25 (PE-stamped) | visual at H2 | Critical |
| Seismic hoop/confinement detail | per PE (S_DS ≈ 0.5 g ASSUMED) | visual at H2 | Critical |

The full reinforcement schedule is **ASSUMED design-intent**; the accept criteria above become

gates **only when the PE stamps the cage.**

---

## 4. Anchor-bolt set — proof / pull test (NW-PF-004)

Anchors: 4 × Ø19.05 mm [0.750 in] × 304.8 mm [12.000 in] ASTM F1554 Gr36, galvanized, cast per

ACI 318 Ch.17.

| Characteristic | Criterion | Method | Class |
| --- | --- | --- | --- |
| Material / grade | ASTM F1554 Gr36 | mill cert / CoC | Critical |
| Galvanize | ASTM A123 coating-thickness record | magnetic gauge | Major |
| Projection | 50.0 mm [1.969 in] ± *(PE)* | scale | Major |
| Pattern (as-cast) | matches NW-PF-002 4 × Ø0.81 holes; template tol ± 0.02 mm | template / bolts drop through plate | Critical |
| Plumb | vertical within *(PE tol)* | level | Major |
| Proof / pull test | apply PE-specified proof load and hold; no slip, no concrete cracking/breakout | calibrated hydraulic ram + reaction frame *(protocol PE to confirm)* | Critical |

Proof-load basis (PE to set). Tie the proof load to the governing tension demand. Bounding wind

case (MECHANICAL_DESIGN.md §7): roof gross uplift 9.2 kN, net anchor demand 7.4 kN across the

4-anchor group → ~1.85 kN/anchor service demand; 4× 2 klbf [≈8.9 kN] capacity → SF 3.9. The

field proof load per anchor is PE-specified (commonly a factor of the service/design tension) and

ASSUMED here pending PE. Cast-in anchors are primarily accepted by **material cert + placement

inspection (H3); the proof/pull test is the PE/owner-specified confirmation** requested for this

package. **Do not exceed a load that would damage the anchor or the young concrete — schedule after the

28-day strength is confirmed (H7).**

**PE coordination.** Per the isolation assumption, the **9.2 kN roof uplift is carried by the

enclosure hold-downs (NW-RR-006, BP-04)**, not the pier; the pier anchors resist mount overturning +

seismic. The proof-load target and the anchor split are **PE to confirm.**

---

## 5. Plumb / level & dimensional (NW-PF-001, NW-PF-002)

| Characteristic | Nominal | Accept limit | Method | Class |
| --- | --- | --- | --- | --- |
| Pier plumb (verticality) | vertical | ≤ 1:200 (5 mm/m) | plumb bob / total station | Critical |
| Top-of-pier / plate level | level | ≤ 0.5° | precision level / total station | Critical |
| Pier height above grade | 914.4 mm [36.000 in] | per ACI 117 *(PE tol)* | tape / survey | Major |
| Pier diameter | Ø304.8 mm [12.000 in] | per ACI 117 *(PE tol)* | tape | Minor |
| Top-plate flatness after grout | flat | plate bears fully on grout, no rock | feeler / straightedge | Major |

---

## 6. Fabricated-plate acceptance (NW-PF-002, NW-PF-003)

Environment: 20 °C per ISO 1 for the machined-plate checks. Datum/GD&T per ASME Y14.5-2018.

### 6.1 NW-PF-002 — top plate (A36, galvanized)

| Characteristic | Nominal (mm [in]) | Accept limit | Method | Class |
| --- | --- | --- | --- | --- |
| Side (square) | 304.8 [12.000] | ISO 2768-mK | tape/CMM | Minor |
| Thickness | 9.5 [0.375] | ISO 2768-mK | caliper | Minor |
| Anchor holes | 4 × Ø20.6 [Ø0.81] | ± 0.25 mm pattern | CMM/gauge | Major |
| Adapter pattern | 4 × Ø11.2 [Ø0.44] | ± 0.25 mm pattern | CMM/gauge | Major |
| Galvanize coating | ASTM A123 | thickness per A123 table *(grade PE/spec)* | magnetic gauge | Major |
| Surface finish | Ra 3.2 µm [125 µin] | — | comparator | Minor |

### 6.2 NW-PF-003 — adapter plate (6061-T6, anodized)

| Characteristic | Nominal (mm [in]) | Accept limit | Method | Class |
| --- | --- | --- | --- | --- |
| Side (square) | 254.0 [10.000] | ISO 2768-mK | caliper/CMM | Minor |
| Thickness | 19.1 [0.750] | ISO 2768-mK | caliper | Minor |
| RA-housing pattern | 4 × M6 | position *(ASSUMED — PE)* | CMM / thread gauge | Major |
| Pier-plate pattern | 4 × Ø11.2 [Ø0.44] | position *(ASSUMED)* | CMM/gauge | Major |
| Centre bore | Ø90.0 [3.543] | H8 pilot *(ASSUMED)* | CMM/plug | Major |
| Mounting-face flatness | ≤ 0.05 mm [0.0020 in] | CMM plane fit | CMM | Major |
| Latitude wedge angle | to 38.9° *(ASSUMED — bidder detail)* | angle gauge / CMM | Major |  |
| Anodize | MIL-A-8625F Type III, 0.002 in | thickness record | eddy-current gauge | Major |
| Surface finish | Ra 3.2 µm [125 µin] | — | profilometer | Minor |

The adapter geometry (patterns, centre bore, wedge angle) is **ASSUMED design-intent** — accept

limits above are provisional pending PE release.

---

## 7. Sampling & documentation

Critical characteristics (concrete strength, anchor proof/pull, plumb/level, reinforcement,

wedge/pattern): 100% — the pier and each plate are qty 1, so first-article inspection = production

acceptance.

Major / Minor: verified on the acceptance record to ISO 2768-mK (plates) / ACI 117 (concrete).

The bidder shall deliver:

Concrete test reports — mix design (ACI 301), batch tickets, 7-/28-day cylinder breaks, slump/air.

Reinforcement — ASTM A615 Gr60 mill certs + rebar-placement/cover record (H2).

Anchors — ASTM F1554 Gr36 cert/CoC, ASTM A123 galvanize cert, anchor proof/pull record.

Plates — A36 cert + A123 coating record (NW-PF-002); 6061-T6 cert + MIL-A-8625F anodize record

(NW-PF-003); dimensional/FAI.

Plumb/level survey (≤ 1:200; ≤ 0.5°).

PE-stamped drawings + PE hold-point sign-offs (H1–H7).

NCR / RFI dispositions for any ASSUMED value or out-of-tolerance condition.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Bidder QA |  |  |  |
| Testing lab (concrete) |  |  |  |
| Owner / PE (stamp + hold points) |  |  |  |

---

## 8. ASSUMED-value register (do NOT treat as final)

| # | ASSUMED value | Part(s) |
| --- | --- | --- |
| 1 | Rebar schedule, cover (~76 mm), tie spacing, seismic hoops, splices | NW-PF-001 |
| 2 | Single-pour cylinder sampling frequency & single-element f'c acceptance basis | NW-PF-001 |
| 3 | Slump/air targets (per approved mix) | NW-PF-001 |
| 4 | Anchor sizing + field proof/pull load (tied to ~9.2 kN uplift bounding case) | NW-PF-004 |
| 5 | Pier-vs-enclosure anchor split (9.2 kN roof uplift → BP-04 hold-downs) | NW-PF-004 / NW-RR-006 |
| 6 | Site frost depth vs 914.4 mm embedment | NW-PF-001 |
| 7 | Wind 105 mph / seismic S_DS 0.5 g | all |
| 8 | Latitude wedge angle (38.9°) + adapter patterns/centre bore | NW-PF-003 |
| 9 | Grout/leveling-nut method + pier-slab isolation gap detail | NW-PF-001/002 |
| 10 | Concrete workmanship tolerance class (ACI 117) | NW-PF-001 |

# Part II — BP-04 rolloff roof

# BP-04 — Roll-off Roof "Disappearing Turret" (Structural Steel + Rail/Drive) — Bidder README

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-04 — Roll-off roof ("disappearing turret") |
| Trade | Structural steel fabrication (welded, AWS D1.1) + rail/drive install |
| Parts | NW-RR-001, -002, -003, -004, -005, -006 (6 fabricated line items; 6 control drawings) |
| Branch / project | design/mechanical-tender — NIGHTWATCH Observatory Mount & Roll-off Tender |
| Issue date | 2026-08-06 |
| Revision | A |
| Governing TDP standard | MIL-STD-31000A (Technical Data Package) |

This README is the entry point for the steel fabricator / gate-and-rail installer bidding BP-04. It

defines the scope, the data package the shop receives, the bidder deliverables, the

PE-STAMP GATE, and the items carried as ASSUMED design-intent. Read it with SOW.md (per-part

specification), weld_map.md (the joint schedule with AWS symbols), and acceptance.md (weld

visual/NDE, rail alignment, drive-cycle test, hold-down pull) in this same folder.

---

## 0. PE-STAMP GATE — READ FIRST (this package is NOT releasable for construction)

**⚠ THE ROLL-OFF ROOF AND ITS SUPPORTING STEEL ARE A STRUCTURE. THEY ARE ISSUED FOR PE REVIEW ONLY.**

**A licensed Professional Engineer, registered in the jurisdiction of the build site, MUST review,

size, and STAMP every structural member (frame, purlins, rail beams, brackets), every weld size, and

every hold-down/rail anchor BEFORE any steel is cut or any anchor is set.** Nothing in this package —

member sizes, weld sizes, anchor sizing — is a released structural design. The controlling **section

sizes are ASSUMED design-intent**; they are presented **for the PE to confirm, complete, and stamp**

against the governing building code and ASCE 7 load cases.

Why a stamp is mandatory. The building shell and its moving roof carry code-level loads. Two load

cases govern this package and are owner/PE responsibilities under ASCE 7:

| Load case | Basis (design proof) | What it drives | Proof status |
| --- | --- | --- | --- |
| Snow (structural) | ~25 psf [1197 Pa] ground snow, high-desert @ ~1800 m; closed flat roof carries 10.8 kN [2.42 klbf] (≈6.1× the roof's own 1.8 kN [397 lbf] dead weight; ≈1.1 t of snow) | roof frame + purlin sizing, panel; snow interlock | §10 PASS + FINDING — snow is the roof's design driver |
| Survival wind (105 mph [46.9 m/s]) | q = 1131 Pa; gross roof uplift 9.2 kN [2.06 klbf] vs 1.8 kN self-weight → SF 0.19 FAIL; net anchor demand 7.4 kN [1.66 klbf] | 4× wind hold-down anchors (NW-RR-006) | §7 FAIL → remediated: 4× ≥2 klbf → SF 3.9 |

The wind basic speed (105 mph) and ground snow load (25 psf) are ASSUMED in the design study

because the repository was silent on roof structure — they are **exactly the values the PE must set

from the site's ASCE 7 hazard data and stamp.** See MECHANICAL_DESIGN.md §7 (wind — FAIL/remediated)

and §10 (roll-off drive + snow — PASS + finding).

**No steel is cut, and no anchor is set, until the stamped structural drawings, the PE-approved

weld/NDE plan, and the PE-approved Inspection & Test Plan (acceptance.md) are in hand.**

---

## 1. Scope

BP-04 covers the roll-off "disappearing turret" roof and its track/drive — a rectangular welded

steel roof frame that rolls its own full length clear of the aperture on a **box-track rail run

twice the roof length**, driven by a COTS gate operator, held closed against survival wind by

mandatory hold-down anchors, and interlocked against wind and snow. The shop:

Fabricates the welded steel roof frame + purlins (NW-RR-001, -002) per AWS D1.1 (weld

symbols per AWS A2.4), sized to carry the closed-roof snow case.

Fabricates/installs the box-track rail beams (NW-RR-003), each 2× the roof length so the

roof fully clears the aperture, with end stops.

Fabricates the wheel axle brackets (NW-RR-004) that carry the COTS V-groove wheels, the

drive bracket + end stops (NW-RR-005) that mount the COTS gate operator, and the **MANDATORY

4× wind hold-down anchor brackets** (NW-RR-006).

Hot-dip galvanizes all steel per ASTM A123 (after welding), weatherproofs the closed roof,

and commissions the drive with its wind + snow interlocks.

Inspects per acceptance.md (weld VT/NDE, rail alignment, drive-cycle test, hold-down pull) and

delivers a certified, PE-signed assembly.

Out of scope for BP-04 (separate packages — the roof *interfaces* to these but the shop does not

supply them, except where noted "install"):

| Interface | Supplied under | Notes |
| --- | --- | --- |
| V-groove track wheels (NW-CO-010, ×8) | BP-05 (COTS) | Shop installs them on the NW-RR-004 brackets. |
| Roof drive — gate operator / rack (NW-CO-011) | BP-05 (COTS) | Shop installs + commissions it on NW-RR-005; see §6 for the suggested product category. |
| Metal roofing panel + flashing (NW-CO-012) | BP-05 (COTS) | Weatherproof skin; shop installs + seals over the purlins. |
| Telescope pier NW-PF-001, anchor set NW-PF-004 | BP-03 | The pier is structurally isolated from the enclosure; roof uplift lands on the building/enclosure foundation, not the pier. See §4. |
| Mount head, optics, electronics | BP-01 / BP-02 / BP-05 | Not a roof interface. |
| Enclosure walls / building shell / enclosure foundation | Owner / site civil (coordinated, PE-stamped) | The roof rides on this shell; the hold-down anchors land in it. |

---

## 2. Data package the shop receives (per MIL-STD-31000A)

| Item | Format / standard | Role |
| --- | --- | --- |
| 3-D solid master (frame + brackets) | STEP ISO 10303 AP242 | As-modelled geometry master (weldment + brackets). |
| Flat-pattern cut files (plate brackets NW-RR-004/-005/-006) | DXF / DWG | Laser/waterjet flat patterns. |
| Control drawings NW-RR-001…-006 | PDF (drawing practices ASME Y14.100; drawing types Y14.24; sheet & title block Y14.1) | Envelope + title block + key dims; bid control drawing. |
| PE-stamped structural drawings | PDF (issued by owner's PE) | Governs for construction — supersedes the ASSUMED member/weld/anchor values herein. |
| SOW.md | Markdown | Per-part spec: members, welds (AWS D1.1/A2.4), rail run, drive, hold-downs, galvanize, weatherproofing. |
| weld_map.md | Markdown | Joint schedule: joint type, AWS A2.4 weld symbol, ASSUMED size, process, NDE. |
| acceptance.md | Markdown | Weld VT/NDE, rail alignment, drive-cycle test, hold-down pull, weatherproofing. |
| cut_list.csv (rows NW-RR-001…-006) | CSV/XLSX | Stock size, cut allowance, stock mass. |

Order of precedence. For the fabricated brackets (NW-RR-004/-005/-006) the **STEP AP242 solid

governs geometry**; the DXF/DWG governs flat patterns; the drawing + SOW govern tolerances, finish, and

material. **For the structural steel (frame, purlins, rail beams), the member sizing, the weld sizing,

and the anchorage, the PE-STAMPED STRUCTURAL DRAWINGS GOVERN and supersede every number in this

package. Where any document disagrees, the PE-stamped set controls** and the bidder shall raise an

RFI before cutting steel. Welding, weld procedures (WPS/PQR) and welder qualification (WPQ) per

AWS D1.1; weld & NDE symbols per AWS A2.4; general tolerances per ISO 2768; bracket GD&T per

ASME Y14.5-2018; fits per ISO 286.

---

## 3. Line-item summary (source: `partspec.parts_for('BP-04')` + `cut_list.csv`)

| Part no. | Name | Material | Stock / size | Qty | Stock mass | Finish | Drawing |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NW-RR-001 | Roof frame perimeter (HSS) | ASTM A500 Gr B HSS | HSS 50.8 mm [2.000 in] sq × 3.2 mm [0.125 in] wall × 12000.0 mm [472.441 in] total (4 sides of the 3.0 m [9.843 ft] square perimeter) | 1 | 56.98 kg | Galvanize ASTM A123 | NW-RR-001 |
| NW-RR-002 | Roof rafters / purlins | ASTM A500 Gr B HSS | HSS 38.1 mm [1.500 in] sq × 3.2 mm [0.125 in] wall × 15000.0 mm [590.551 in] total (5 purlins × 3000 mm [118.110 in] span @ 600 mm [23.622 in] o.c.) | 5 | 261.14 kg | Galvanize ASTM A123 | NW-RR-002 |
| NW-RR-003 | Track rail beams (box track) | ASTM A36 structural steel | Box track 63.5 mm [2.500 in] sq × 4.0 mm [0.157 in] wall × 6000.0 mm [236.220 in] each (2 rails; run = 2× roof length) | 2 | 179.36 kg | Galvanize ASTM A123 | NW-RR-003 |
| NW-RR-004 | Wheel axle brackets | ASTM A36 structural steel | Plate 101.6 mm [4.000 in] × 76.2 mm [3.000 in] × 9.5 mm [0.375 in] | 8 | 4.63 kg | Galvanize ASTM A123 | NW-RR-004 |
| NW-RR-005 | Drive bracket + end stops | ASTM A36 structural steel | Plate/angle assembly 150.0 mm [5.906 in] × 100.0 mm [3.937 in] × 9.5 mm [0.375 in] | 4 | 4.49 kg | Galvanize ASTM A123 | NW-RR-005 |
| NW-RR-006 | Wind hold-down anchor brackets (REMEDIATION — MANDATORY) | ASTM A36 structural steel | Plate 127.0 mm [5.000 in] × 101.6 mm [4.000 in] × 12.7 mm [0.500 in] | 4 | 5.15 kg | Galvanize ASTM A123 | NW-RR-006 |

Stock mass is the quantity ordered (stock envelope volume × steel density), not finished net mass;

cut allowance is 3.0 mm on stock. Rail run per rail is **6000.0 mm [236.220 in] = 2 × the 3000.0 mm

[118.110 in] roof length**, so the roof travels its full length off the aperture. Total roof assembly

mass basis for the drive/wheel sizing is 180 kg [397 lb] (P.ENCLOSURE.roof_mass_kg, ASSUMED).

**Member-callout reconciliation (ASSUMED).** On NW-RR-002 the nominal member designation in the

registry key-dims (**"HSS 2×1×1/8"**, a rectangular section) differs from the modelled/ordered stock

envelope (**38.1 mm [1.500 in] square × 3.2 mm wall**). Both are **ASSUMED design-intent**; the PE

shall reconcile the purlin section against the ASCE 7 snow demand and issue the released size.

---

## 4. Cross-package interfaces the shop must preserve

| Interface | Feature | Mates to | Part |
| --- | --- | --- | --- |
| Roof → rail | 8 × V-groove wheels on NW-RR-004 brackets | Box-track rail running surface | NW-CO-010 (BP-05) → NW-RR-003 |
| Roof → drive | Drive bracket + rack/pinion pickup | Gate operator + gear rack | NW-CO-011 (BP-05) → NW-RR-005 |
| Roof → weather | Purlin top flanges | Metal roofing panel + flashing | NW-CO-012 (BP-05) → NW-RR-002 |
| Rail → structure | Rail-beam anchorage | Enclosure/building foundation (PE-designed) | NW-RR-003 → owner civil |
| Roof/rail → structure | 4× hold-down anchor brackets | Ø0.75 in [19.05 mm] F1554 anchors into the enclosure foundation | NW-RR-006 → owner civil |
| End of travel | 4× end stops + rubber bump pads | Rail ends + drive limit | NW-RR-005 / NW-RR-003 |

**Wind hold-down clarification (important).** The **9.2 kN [2.06 klbf] survival-wind roof uplift** is

resisted by the **4× wind hold-down anchor brackets NW-RR-006 (this package)**, which anchor the

**enclosure/building foundation** — because the telescope pier (BP-03) is **structurally isolated**

from the enclosure (standard observatory practice, to keep vibration off the optics). The BP-03

anchor set NW-PF-004 casts into the **pier** and resists the mount overturning + seismic demand, a

**separate** load path. **Where each hold-down lands, the anchor edge distance/embedment into the

building foundation, and the final anchor capacity are PE coordination items — anchorage into

concrete per ACI 318 Ch.17; PE to confirm.**

---

## 5. Bidder deliverables

Finished, galvanized, weatherproofed assembly: frame (NW-RR-001), purlins (NW-RR-002 ×5), rail

beams (NW-RR-003 ×2), wheel brackets (NW-RR-004 ×8), drive bracket + stops (NW-RR-005 ×4), and the

4× wind hold-down brackets (NW-RR-006) — installed, aligned, and commissioned.

Material / mill certs — ASTM A500 Gr B (HSS) and ASTM A36 (plate/rail), heat/lot traceable.

Welding submittals — WPS + supporting PQR and welder qualification records (WPQ) per AWS D1.1;

weld map (weld_map.md) marked up with as-built weld sizes; CWI weld inspection report.

NDE reports — visual (VT) 100% + magnetic-particle (MT)/dye-penetrant (PT) on the critical

hold-down, wheel-bracket, and rail-splice welds per acceptance.md (extent ASSUMED — PE/CWI to set).

Galvanize cert — ASTM A123 coating mass/thickness record; vent/drain-hole detail for the HSS;

field-repair procedure for damaged galvanize (bidder-proposed; the recognized repair standard is

ASTM A780, supplementary to the register).

Rail-alignment survey — gauge, straightness, level/co-planarity, splice flushness (acceptance.md).

Drive-cycle + interlock commissioning report — full open/close travel within timeout, tractive

load/current, soft-start/stop, end-stop engagement, manual release, and the wind + snow interlocks.

Hold-down pull-test record — each anchor proofed to the PE-set load (≥2 klbf [8.9 kN] baseline).

Weatherproofing test — roof-closed water/rain test, flashing/gasket, drainage.

PE sign-off — stamped structural drawings + field hold-point sign-offs (fit-up, weld, anchor set).

RFI / nonconformance log resolving every ASSUMED value before it is built.

---

## 6. Suggested COTS product categories (procured under BP-05 — named, not specified)

The task's two long-lead COTS items map to well-established commercial product categories. These are

suggested categories to guide the BP-05 buy, not a released product spec — final selection and

sizing are the bidder's/PE's, confirmed against the loads below.

Track rail + wheels → sliding-gate "V-groove box track" hardware (steel). The **box-track rail

NW-RR-003 (2.5 in [63.5 mm] class) and the 8× V-groove wheels NW-CO-010** correspond to the

steel V-groove gate-track + V-groove wheel-with-preattached-steel-box category used on slide

gates and DIY roll-off observatories. Steel 4 in [101.6 mm] V-groove wheels are commonly rated to

~3,000 lb [~13 kN] each; with 8 wheels for the 180 kg [397 lb] roof + snow, capacity is not the

constraint — alignment and straightness are (see acceptance.md). Size wheels for ≥4× the

wheel share of roof + snow (per NW-RR-004 note).

Roof drive → rack-and-pinion "slide-gate operator" (light-commercial class). The **roof drive

NW-CO-011 corresponds to a rack-and-pinion sliding-gate operator**. The proof requires only

235 N [52.8 lbf] tractive force (rolling 88 N [19.8 lbf] + 35 mph [15.6 m/s] wind 147 N

[33.1 lbf]) → SF 2.1 vs a ~500 N [112 lbf] garage-door-class drive; light-commercial slide-gate

operators rated for gate weights of ~270–500 kg [~600–1,100 lb] give ample margin and provide the

needed soft-start/soft-stop, manual release, and photo-beam/limit interlocks. Because **wind is

62% of the tractive load, the drive is WIND-sized — spec a positive, fail-safe close against the

35 mph gust**.

**Sizing anchors (from the proofs, for the BP-05 buyer).** Move force 235 N [52.8 lbf]; drive torque

11.77 Nm [8.68 lbf·ft] @ 50 mm [1.969 in] wheel; roof speed 0.067 m/s (3 m in 45 s) < 0.30 m/s

ceiling; open time 45 s < 60 s motor timeout. **Snow interlock is MANDATORY:** a fully snow-laden

roof needs **627 N [141 lbf]** to roll — it **exceeds** the ~500 N drive, so the roof must **never**

be commanded open under snow load (`MECHANICAL_DESIGN.md` §10).

Sources for the named categories (BP-05 to confirm): [Steel Supply LP — V-groove track & wheels](https://www.steelsupplylp.com/ornamental-iron/store/gate-door-hardware/v-groove-tracks-wheels-boxes),

[Hoover Fence — V-groove wheel w/ preattached steel box](https://www.hooverfence.com/v-groove-wheel-with-preattached-steel-box),

[Cloudy Nights — roll-off roof roller/rail systems](https://www.cloudynights.com/topic/812178-recommend-a-low-friction-rollerrail-system-for-8x10/),

[FAAC 844 ER rack-and-pinion slide-gate operator](https://www.affordableopeners.com/faac-usa-844-er-rack-and-pinion-slide-gate-operator.html),

[LiftMaster rack-and-pinion slide-gate operator](https://www.asapgaragedoorandgaterepair.com/portfolio/liftmaster-residential-rack-pinion-drive-slide-gate-operator/).

---

## 7. ASSUMED design-intent — bidder / PE to confirm (NOT final)

Carried as ASSUMED design-intent in the parts registry; not released dimensions. The PE shall

confirm/complete and stamp before construction:

All structural member sizes — frame HSS 2×2×1/8 (NW-RR-001), purlin HSS (NW-RR-002, incl. the

2×1 vs 1.5-sq reconciliation of §3), box-track section 2.5 in class (NW-RR-003), and bracket

thicknesses — are **ASSUMED design-intent; PE to confirm vs the ASCE 7 snow (10.8 kN [2.42 klbf]

closed-roof) + survival-wind cases.**

All weld sizes and joint types — every weld leg/throat and CJP/PJP call in weld_map.md is

ASSUMED; PE/CWI to size per AWS D1.1 minimum-fillet tables and the computed demand.

Hold-down anchor sizing — 4× Ø0.75 in [19.05 mm] F1554, capacity ≥2 klbf [8.9 kN] each, is the

REMEDIATION basis (survival uplift 9.2 kN → SF 3.9). Final diameter, grade, embedment, and edge

distance into the enclosure foundation are PE to set per ACI 318 Ch.17.

Rail support / anchorage spacing and the rail-to-foundation connection (weld vs bolt) — ASSUMED;

PE to detail for the roof + snow + wind reactions.

Roof geometry (3.0 × 3.0 m [9.843 × 9.843 ft], 180 kg [397 lb]) — ASSUMED footprint/mass

(P.ENCLOSURE, flagged); confirm against the released enclosure.

Snow interlock and wind interlock logic — MANDATORY per §10/§7; interlock thresholds

(25 mph [11.2 m/s] park, 35 mph [15.6 m/s] close, snow hold-closed) SOURCED, but the sensor/logic

implementation is ASSUMED — bidder/PE to detail.

Surface finish / GD&T values on the brackets — ASSUMED; PE to set.

Weatherproofing detail (panel lap, flashing, gasket, drainage) — ASSUMED; bidder to detail with

the NW-CO-012 panel.

---

## 8. References

Parts registry: design/mechanical/tender/gen/partspec.py → parts_for('BP-04') (single source of truth).

BOM / cut list / COTS: design/mechanical/tender/bom/{master_bom,cut_list,cots_schedule}.csv.

Control drawings: design/mechanical/tender/drawings/NW-RR-00{1..6}.svg.

Design basis: design/mechanical/MECHANICAL_DESIGN.md §7 (wind — FAIL/remediated, hold-downs),

§10 (roll-off drive + snow — PASS + snow-interlock finding), §9 (selected config + the 5 remediations);

design/mechanical/tradestudy/SECTION.md (enclosure = roll-off + active thermal; anchors = 4× 2 klbf).

Standards register: MIL-STD-31000A; AWS D1.1 (structural steel welding, WPS/PQR/WPQ), AWS A2.4

(weld & NDE symbols); ASTM A500 Gr B (HSS), ASTM A36 (steel), ASTM A123 (hot-dip galvanize),

ASTM F1554 Gr36 (anchor bolts), ASTM A574 (SHCS); ACI 318 Ch.17 (anchoring), ASCE 7 (wind/snow/seismic);

ASME Y14.5-2018 / Y14.100 / Y14.24 / Y14.1; ISO 286; ISO 2768; STEP ISO 10303 AP242; DXF/DWG.

</content>

</invoke>

# BP-04 — Statement of Work: Roll-off Roof "Disappearing Turret" (Structural Steel + Rail/Drive)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-04 — Roll-off roof ("disappearing turret") |
| Parts | NW-RR-001 (frame), -002 (purlins), -003 (rail beams), -004 (wheel brackets), -005 (drive bracket + stops), -006 (wind hold-down brackets) |
| Process | Structural steel cut + weld (AWS D1.1); laser-cut plate brackets; rail/drive install |
| Material | ASTM A500 Gr B HSS (frame/purlins); ASTM A36 (rail beams, brackets) |
| Finish | Hot-dip galvanize per ASTM A123 (after fabrication) |
| Issue date / rev | 2026-08-06 / A |

Purpose. This SOW specifies the fabrication, welding, tolerancing, finishing, rail/drive

installation, and commissioning requirements for the roll-off roof and its track/drive. It is read with

the STEP ISO 10303 AP242 solid master (weldment/bracket geometry authority), the DXF/DWG flat patterns

(plate brackets), the NW-RR control drawings (PDF), weld_map.md (joint schedule), and acceptance.md.

All dimensions are dual-unit, mm primary, inch in brackets, drawn from the parts registry

(partspec.parts_for('BP-04')) and cut_list.csv — no dimension herein is invented.

Standards applied. MIL-STD-31000A (TDP); AWS D1.1 (structural steel welding, incl. WPS/PQR and

welder qualification WPQ); AWS A2.4 (weld & NDE symbols); ASTM A500 Gr B (HSS), ASTM A36

(steel), ASTM A123 (hot-dip galvanize), ASTM F1554 Gr36 (anchor bolts), ASTM A574 (SHCS);

ACI 318 Ch.17 (anchorage into concrete/foundation); ASCE 7 (wind/snow/seismic loads);

ASME Y14.5-2018 (bracket GD&T), Y14.100/Y14.24/Y14.1 (drawing practices); ISO 286 (fits);

ISO 2768 (general tolerances).

**PE-STAMP GATE (see README §0).** The roof and its supporting steel are a **structure**. Member

sizes, weld sizes, and anchorage in this SOW are **ASSUMED design-intent** and are **not** releasable

for construction until a licensed PE confirms them against the **ASCE 7 snow (10.8 kN [2.42 klbf]

closed-roof) and survival-wind (9.2 kN [2.06 klbf] uplift)** cases and **stamps** the drawings.

---

## 1. General requirements (all parts)

Material & certification. HSS to ASTM A500 Gr B; plate and rail to ASTM A36. Furnish

mill certification / CoC with heat/lot traceability; mark each member with part number and

revision per ASME Y14.100.

General tolerance. ISO 2768-mK on plate features; frame/rail geometric tolerances per the

per-part tables (§2–§7). Break sharp edges; no burrs on plate brackets.

Welding. All welds per AWS D1.1. The bidder shall submit WPS supported by PQR, and

welder qualification records (WPQ) for each process/position, before production welding.

Prequalified joints per AWS D1.1 are acceptable where applicable; all others require a qualified WPS.

Weld & NDE symbols on the drawings and in weld_map.md are interpreted per AWS A2.4.

Weld sizes are ASSUMED design-intent. Every weld leg/throat and every CJP/PJP designation in

weld_map.md is ASSUMED — PE/CWI to size per the AWS D1.1 minimum-fillet-weld tables (governed

by the thinner part joined) and the PE's computed member forces. **Do not treat any weld size herein

as released.**

GD&T. Bracket geometric callouts per ASME Y14.5-2018; hole-pattern position per the drawing

(bracket hole patterns held to 0.25 mm [0.010 in], cut_list/drawing).

Fabrication sequence. Weld → dimensional/weld inspection → **hot-dip galvanize (ASTM A123, after

all welding) → install wheels/drive → align → commission. Provide vent and drain holes** on all

closed HSS sections for the galvanizing bath (locations ASSUMED — bidder to detail, must not

fall on a stiffness-critical face).

Finish. Hot-dip galvanize per ASTM A123 on all steel after fabrication. Field-repair of

galvanize damaged by field welding/handling per the bidder's approved procedure (recognized

repair standard ASTM A780, supplementary to the register). Coating mass/thickness recorded.

Fasteners. Structural bolting and bracket fasteners per ASTM A574 (SHCS) where used; anchors

per ASTM F1554 Gr36 (see §7). Fastener schedule consolidated under BP-05 (NW-CO-014).

---

## 2. NW-RR-001 — Roof frame perimeter (HSS)

Drawing: NW-RR-001 (rev A). Stock: HSS 50.8 mm [2.000 in] sq × 3.2 mm [0.125 in] wall,

total 12000.0 mm [472.441 in] (four sides of the 3000.0 mm [118.110 in] × 3000.0 mm [118.110 in]

square perimeter), cut allowance 3.0 mm, stock mass 56.98 kg (cut_list.csv). Process: cut + weld

(AWS D1.1). Tolerance: frame square 3 mm/m, diagonal 5 mm [0.197 in] across the frame.

| Feature | Value (mm [in]) | Spec |
| --- | --- | --- |
| Perimeter span × length | 3000.0 [118.110] × 3000.0 [118.110] | ASSUMED footprint (P.ENCLOSURE) |
| Member | HSS 2×2×1/8 (50.8 sq × 3.2 wall) | ASSUMED design-intent — PE to size vs snow/wind |
| Corner joints | fully welded, gusseted | AWS D1.1; size in weld_map.md (ASSUMED) |
| Frame square / diagonal | 3 mm/m; diagonal 5 mm [0.197 in] | acceptance datum |

Function. The frame carries the purlins + roofing panel and transfers the **closed-roof snow load

(10.8 kN [2.42 klbf]) and survival-wind uplift (9.2 kN [2.06 klbf])** into the wheels/hold-downs.

Corner joints are fully welded and gusseted. Member size ASSUMED — PE to confirm vs ASCE 7.

Provenance / flags. Roof span/length = P.ENCLOSURE (ASSUMED footprint); member size ASSUMED

design-intent; corner-weld size ASSUMED (weld_map.md J1).

---

## 3. NW-RR-002 — Roof rafters / purlins

Drawing: NW-RR-002 (rev A). Stock: HSS 38.1 mm [1.500 in] sq × 3.2 mm [0.125 in] wall,

total 15000.0 mm [590.551 in] (5 purlins × 3000.0 mm [118.110 in] span), cut allowance 3.0 mm,

stock mass 52.23 kg (cut_list.csv). Qty 5, spaced 600.0 mm [23.622 in] o.c. Process:

cut + weld to the frame (AWS D1.1). Finish: galvanize ASTM A123.

| Feature | Value (mm [in]) | Spec |
| --- | --- | --- |
| Span (each) | 3000.0 [118.110] | ASSUMED (P.ENCLOSURE) |
| Spacing | 600.0 [23.622] o.c. | ASSUMED design-intent |
| Count | 5 | ASSUMED design-intent |
| Member | HSS 2×1×1/8 or 38.1 sq × 3.2 wall | ASSUMED — reconcile (see below) |
| Purlin-to-frame joint | fillet both sides (or bolted clip) | AWS D1.1; weld_map.md J2 (ASSUMED) |

**Member-callout reconciliation (ASSUMED design-intent).** The registry names the member **"HSS

2×1×1/8"** (rectangular) while the modelled/ordered stock is **38.1 mm [1.500 in] square × 3.2 mm

wall**. Both are carried as ASSUMED; **the PE shall reconcile the purlin section** against the ASCE 7

**snow case (10.8 kN [2.42 klbf] over the 9 m² [96.9 ft²] roof, ≈6.1× the roof dead weight)**, which

is the **governing design driver** for the purlins and panel (`MECHANICAL_DESIGN.md` §10), and issue

the released size.

Function. Purlins carry the metal roofing panel (NW-CO-012, BP-05) and the snow load. A

sloped/pitched, slippery metal roof sheds most snow (ASCE 7 slope factor Cs → ~0 for a steep metal

roof); a flat roll-off roof must carry the full load and needs the snow interlock (§6).

---

## 4. NW-RR-003 — Track rail beams (box track)

Drawing: NW-RR-003 (rev A). Stock: box track **63.5 mm [2.500 in] sq × 4.0 mm [0.157 in]

wall, 6000.0 mm [236.220 in] each, 2 rails**, cut allowance 3.0 mm, stock mass 89.68 kg

(cut_list.csv). Process: cut + weld / bolt to the rail supports. Tolerance: rail straightness

3 mm [0.118 in] over the run; gauge 2 mm [0.079 in].

| Feature | Value (mm [in]) | Spec |
| --- | --- | --- |
| Rail length (each) | 6000.0 [236.220] = 2× roof length | so the roof fully clears the aperture |
| Gauge (rail spacing) | 3000.0 [118.110] | = roof span; hold to ±2 mm [0.079 in] |
| Section | box track, 2.5 in [63.5 mm] class | ASSUMED; brand/section = COTS (BP-05) |
| Straightness | 3 mm [0.118 in] over run | acceptance datum |
| End stops | required, both ends, both rails | part of NW-RR-005 |

Function. The "disappearing turret" travels its own full length off the building — hence the

rail run = 2× the roof length (6000 mm [236.220 in]). Each rail carries the roof + snow reaction on

the V-groove wheels. Splices (if the rail is furnished in shorter lengths) shall be **CJP groove

butt welds with backing, ground flush on the running surface** (weld_map.md J6, size/NDE ASSUMED).

Rail brand/section is a suggested COTS category (steel V-groove box track, README §6); the shop may

furnish proprietary track in lieu of fabricated box track subject to PE approval. **End stops are

MANDATORY** at both ends of both rails.

---

## 5. NW-RR-004 — Wheel axle brackets

Drawing: NW-RR-004 (rev A). Stock: plate **101.6 mm [4.000 in] × 76.2 mm [3.000 in] × 9.5 mm

[0.375 in], qty 8, cut allowance 3.0 mm, stock mass 4.63 kg. Process:** laser cut + weld.

Tolerance: hole pattern 0.25 mm [0.010 in].

| Feature | Value | Spec |
| --- | --- | --- |
| Count | 8 (4 per side) | ASSUMED design-intent |
| Wheel bore | for Ø101.6 mm [4.000 in] V-groove wheel (COTS, NW-CO-010) | shop installs the wheel |
| Axle | M16 | ASSUMED; bidder/PE to confirm shear/bending |
| Bracket-to-frame weld | fillet both sides, gusseted | AWS D1.1; weld_map.md J3 (ASSUMED, CRITICAL) |

Function. The brackets carry the COTS V-groove wheels (NW-CO-010, BP-05) and transmit the roof

weight into the rails. Size the wheels for ≥4× the wheel share of the roof (180 kg [397 lb]) + snow.

4 in [101.6 mm] steel V-groove wheels are commonly rated ~3,000 lb [~13 kN] each, so **alignment and

weld integrity — not wheel capacity — govern** (acceptance.md). Bracket-to-frame welds are

load-critical and receive VT 100% + MT/PT (extent ASSUMED, §acceptance.md).

---

## 6. NW-RR-005 — Drive bracket + end stops (and the drive/interlock scope)

Drawing: NW-RR-005 (rev A). Stock: plate/angle **150.0 mm [5.906 in] × 100.0 mm [3.937 in] ×

9.5 mm [0.375 in], qty 4, cut allowance 3.0 mm, stock mass 4.49 kg. Process:** laser cut + weld.

| Feature | Value | Spec |
| --- | --- | --- |
| Drive | rack-and-pinion / gate operator (COTS, NW-CO-011) | shop installs + commissions |
| End stops | 4 + rubber bump pads | hard limits, both ends both rails |
| Drive-bracket weld | fillet, gusseted | AWS D1.1; weld_map.md J4 (ASSUMED) |

Drive sizing (from the proof — MECHANICAL_DESIGN.md §10). The drive moves the 180 kg [397 lb]

roof against rolling 88 N [19.8 lbf] + 35 mph [15.6 m/s] wind 147 N [33.1 lbf] = **235 N

[52.8 lbf] tractive force (11.77 Nm [8.68 lbf·ft] @ 50 mm [1.969 in] wheel) → SF 2.1 vs a

~500 N [112 lbf] garage-door-class drive. Because wind is 62% of the tractive load, the drive is

WIND-sized — specify a positive, fail-safe close against the gust**. Suggested COTS category:

light-commercial rack-and-pinion slide-gate operator (README §6).

Interlocks (MANDATORY — REMEDIATION/finding).

Wind interlock: park at 25 mph [11.2 m/s] (roof stays open only below this), emergency close

at 35 mph [15.6 m/s] gust; open time 45 s < 60 s motor timeout.

Snow interlock (MANDATORY): a fully snow-laden roof needs 627 N [141 lbf] to roll — which

exceeds the ~500 N drive — so the roof must never be commanded open under snow load. The

safety monitor shall hold the roof CLOSED while snow-loaded (MECHANICAL_DESIGN.md §10). A

pitched shedding roof is the design alternative.

Provide soft-start/soft-stop, manual release, photo-beam/limit safety, and interlock with the

building/telescope safety monitor. Interlock sensor/logic detail is ASSUMED — bidder/PE to detail.

Control power. The drive + interlocks draw from the site power system — grid + UPS (v1) or the

48 V LiFePO4 pack (v2, NW-CO-013, REMEDIATION of the power/autonomy FAIL); power source is a BP-05

coordination item.

---

## 7. NW-RR-006 — Wind hold-down anchor brackets (REMEDIATION — MANDATORY)

Drawing: NW-RR-006 (rev A). Stock: plate **127.0 mm [5.000 in] × 101.6 mm [4.000 in] × 12.7 mm

[0.500 in], qty 4, cut allowance 3.0 mm, stock mass 5.15 kg. Process:** laser cut + weld.

Tolerance: hole pattern 0.25 mm [0.010 in].

| Feature | Value | Spec |
| --- | --- | --- |
| Count | 4 | REMEDIATION basis |
| Anchor | Ø0.75 in [19.05 mm] F1554 Gr36 (to enclosure foundation) | ACI 318 Ch.17; PE to size |
| Capacity (each) | ≥2 klbf [8.9 kN] | proof-test target |
| Bracket weld | CJP or heavy fillet, gusseted | AWS D1.1; weld_map.md J5 (ASSUMED, CRITICAL) |

**REMEDIATION — MANDATORY (do not value-engineer out).** The survival-wind proof (`MECHANICAL_DESIGN.md`

§7) found **gross roof uplift 9.2 kN [2.06 klbf]** vs **1.8 kN [397 lbf]** self-weight → **SF 0.19 —

FAIL.** Net anchor demand is **7.4 kN [1.66 klbf]**. **Four hold-down brackets at ≥2 klbf [8.9 kN]

each (35.6 kN [8 klbf] total) restore SF 3.9.** These brackets **clamp the roof/building against the

105 mph [46.9 m/s] survival uplift and are interlocked with the drive** (the roof cannot be driven

while a hold-down is engaged, and must re-engage on close).

Anchorage. The brackets anchor into the enclosure/building foundation (the telescope pier is

isolated — README §4). **Final anchor diameter, grade, embedment, and edge distance are PE to set per

ACI 318 Ch.17; each anchor is proof-pull-tested** per acceptance.md.

---

## 8. Weatherproofing

Install the COTS metal roofing panel + flashing (NW-CO-012, BP-05) over the purlins: lapped/sealed

panel, ridge and edge flashing, and perimeter gaskets at the roof-to-wall closure when shut.

Provide drainage/weeps so the closed roof sheds water; detail the wall-top weather seal that

the roof lands on. Panel lap, flashing, gasket, and drainage details are ASSUMED — bidder to detail

with the panel supplier; verify by the roof-closed water test (acceptance.md).

A pitched panel is preferred (sheds snow per §3/§6); a flat panel triggers the snow interlock.

---

## 9. Submittals & deliverables

Finished, galvanized, weatherproofed, commissioned assembly (all six NW-RR parts).

Material / mill certs (A500 Gr B, A36) with heat/lot traceability.

WPS + PQR + welder qualification (WPQ) per AWS D1.1; as-built weld_map.md; CWI weld report.

NDE reports (VT 100% + MT/PT on critical welds; extent ASSUMED per acceptance.md).

Galvanize cert (ASTM A123 coating mass/thickness) + vent/drain detail + galv-repair procedure.

Rail-alignment survey (gauge, straightness, level, splice flushness).

Drive-cycle + interlock commissioning report (travel, tractive load/current, wind + snow interlocks).

Hold-down pull-test record (each anchor to the PE-set proof load).

Weatherproofing (water) test record.

PE sign-off — stamped structural drawings + field hold-point sign-offs.

RFI / nonconformance log resolving every ASSUMED value before it is built.

---

## 10. ASSUMED design-intent register (this SOW)

| # | ASSUMED value | Part(s) | Status |
| --- | --- | --- | --- |
| 1 | Frame HSS 2×2×1/8 member size | NW-RR-001 | ASSUMED — PE to size vs ASCE 7 snow/wind |
| 2 | Purlin section (HSS 2×1×1/8 vs 38.1 sq), spacing 600 mm, count 5 | NW-RR-002 | ASSUMED — PE to reconcile & size (snow-governed) |
| 3 | Box-track section (2.5 in class), rail supports/anchorage spacing | NW-RR-003 | ASSUMED — PE to detail; COTS track alt allowed |
| 4 | All weld sizes & joint types (CJP/PJP/fillet legs) | all | ASSUMED — PE/CWI to size per AWS D1.1 |
| 5 | Wheel axle M16; wheel bore/rating | NW-RR-004 | ASSUMED — size wheels ≥4× wheel share |
| 6 | Drive product + interlock sensor/logic | NW-RR-005 | ASSUMED — light-commercial rack-and-pinion (README §6) |
| 7 | Hold-down anchor Ø0.75 F1554, ≥2 klbf, embedment/edge | NW-RR-006 | ASSUMED REMEDIATION — PE per ACI 318 Ch.17 |
| 8 | Roof geometry 3.0×3.0 m / 180 kg | all | ASSUMED footprint (P.ENCLOSURE) |
| 9 | Galvanize vent/drain holes; galv field-repair (A780) | all | ASSUMED — bidder to detail |
| 10 | Weatherproofing detail (panel lap, flashing, gasket, drainage) | roof | ASSUMED — bidder to detail |
| 11 | Bracket GD&T / surface-finish values | NW-RR-004/-005/-006 | ASSUMED — PE to set |

</content>

# BP-04 — Acceptance & Inspection Plan: Roll-off Roof (Structural Steel + Rail/Drive)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-04 — Roll-off roof ("disappearing turret") |
| Parts | NW-RR-001, -002, -003, -004, -005, -006 |
| Method | Weld VT/NDE (AWS D1.1) · frame & rail dimensional survey · drive-cycle + interlock test · hold-down proof-pull · roof-closed water test |
| Issue date / rev | 2026-08-06 / A |

Scope. This plan defines the inspection methods and accept/reject criteria for BP-04. Welds are

inspected per AWS D1.1 (symbols per AWS A2.4); the rail run and frame are dimensionally

surveyed; the drive and its wind + snow interlocks are cycle-tested; the mandatory 4× hold-downs

are proof-pull-tested; and the closed roof is water-tested. All limits are dual-unit and derived from

partspec / the NW-RR control drawings and the design proofs — nothing invented. Because this is a

structure, the plan is executed under the PE-approved ITP and the PE's field hold-points.

Standards. AWS D1.1 (weld acceptance, WPS/PQR/WPQ) & AWS A2.4 (symbols); ASTM A123 (galvanize);

ASTM A500 Gr B / A36 (materials); ASTM F1554 Gr36 (anchors) & ACI 318 Ch.17 (anchorage); ASCE 7

(load basis); ISO 2768 (general tolerance); ASME Y14.5-2018 (bracket GD&T).

---

## 1. Weld visual & NDE acceptance (AWS D1.1)

Qualification gate. Before any acceptance, verify the WPS + PQR and **welder qualification

(WPQ)** are on file per AWS D1.1; production welding by unqualified procedure/welder is rejectable.

Visual (VT) — 100% of all welds by an AWS Certified Welding Inspector (CWI) to the AWS D1.1

visual acceptance criteria (statically-loaded, unless the PE classifies a joint cyclic): no cracks;

full fusion; undersize, undercut, porosity, and profile within the D1.1 limits; weld sizes match the

as-built weld_map.md.

Surface NDE — critical joints. MT (magnetic-particle) or PT (dye-penetrant) per the

weld_map.md extents: J3 (wheel brackets) 100%, J5 (hold-downs) 100%, **J6 (rail splices)

100% PT, sampling elsewhere. UT on CJP groove welds (J5/J6) if required by the PE**.

*(NDE method + extent are ASSUMED — PE/CWI to confirm; see §8.)*

Reject/repair. Reweld and re-inspect per AWS D1.1; log every disposition.

| Weld group | Method | Extent | Accept criterion |
| --- | --- | --- | --- |
| J1 frame corners | VT (+MT) | 100% VT / 25% MT | AWS D1.1 visual; no cracks; size per as-built |
| J2 purlin-to-frame | VT | 100% | AWS D1.1 visual |
| J3 wheel brackets | VT + MT | 100% / 100% | AWS D1.1; no surface indications |
| J4 drive bracket | VT (+MT) | 100% / 25% | AWS D1.1 visual |
| J5 hold-downs | VT + MT (UT if CJP) | 100% / 100% | AWS D1.1; CRITICAL — no indications |
| J6 rail splices | VT + PT (UT per PE) | 100% / 100% | flush-ground running surface; no indications |
| J7 end stops / J8 rail supports / J9 gussets | VT | 100% | AWS D1.1 visual (J8 torque-check if bolted) |

---

## 2. Material & galvanize acceptance

| Characteristic | Requirement | Method | Class |
| --- | --- | --- | --- |
| HSS material | ASTM A500 Gr B mill cert, heat/lot traceable | certificate review | Critical |
| Plate / rail material | ASTM A36 mill cert, heat/lot traceable | certificate review | Critical |
| Galvanize | ASTM A123 coating mass/thickness | magnetic thickness gauge + cert | Major |
| Vent/drain holes | present on all closed HSS (ASSUMED locations) | visual | Major |
| Galv field-repair | bidder procedure (ASTM A780, supplementary) | visual + thickness | Major |

---

## 3. Frame & bracket dimensional acceptance

| Characteristic | Nominal (mm [in]) | Accept limit | Method | Class |
| --- | --- | --- | --- | --- |
| Frame perimeter | 3000.0 [118.110] × 3000.0 [118.110] | ISO 2768 + frame-square | tape/total station | Major |
| Frame square | — | ≤ 3 mm/m | diagonal check | Critical |
| Frame diagonal difference | — | ≤ 5 mm [0.197 in] | cross-diagonal tape | Critical |
| Purlin spacing | 600.0 [23.622] o.c., ×5 | ISO 2768 | tape | Minor |
| Bracket plate envelope (NW-RR-004/-005/-006) | per §3 SOW | ISO 2768-mK | calipers | Minor |
| Bracket hole pattern | — | ≤ 0.25 mm [0.010 in] | CMM / gauge | Major |

---

## 4. Rail alignment survey (NW-RR-003)

The rail run is the wheel path — alignment and straightness govern, not wheel capacity.

| Characteristic | Nominal (mm [in]) | Accept limit | Method | Class |
| --- | --- | --- | --- | --- |
| Rail length (each) | 6000.0 [236.220] = 2× roof length | ISO 2768 | tape/total station | Major |
| Gauge (rail spacing) | 3000.0 [118.110] | ± 2 mm [0.079 in] over the run | total station / trammel | Critical |
| Straightness | — | ≤ 3 mm [0.118 in] over the run | string-line / laser | Critical |
| Level / co-planarity of the two rails | — | per PE *(ASSUMED — e.g. ≤ 3 mm)* | level / total station | Critical |
| Splice flushness (J6) on running surface | — | flush, ground — no step at the wheel path | straightedge / feeler | Critical |
| End stops present + engaged | 4, both ends both rails | hard stop + rubber pad | function check | Major |

---

## 5. Drive-cycle & interlock test (NW-RR-005 + NW-CO-011)

| Test | Requirement | Method | Class |
| --- | --- | --- | --- |
| Full open travel | Roof clears the aperture (travels its full length, 3000 mm [118.110 in]) | run to open end stop | Critical |
| Open/close time | ≤ 45 s each (< 60 s motor timeout) | stopwatch | Major |
| Roof speed | ≈ 0.067 m/s (< 0.30 m/s ceiling) | travel/time | Minor |
| Tractive load / drive margin | Move force ≈ 235 N [52.8 lbf]; drive SF ≥ 2.0 vs the drive rating | inline load / motor current | Critical |
| Soft-start / soft-stop | smooth ramp; end-stop engagement without slam | observe | Major |
| Manual release | disengages drive; roof movable by hand; re-engages | function | Critical (safety) |
| Photo-beam / limit safety | reverses/stops on obstruction; limits stop travel | function | Critical (safety) |
| Wind interlock | park ≤ 25 mph [11.2 m/s]; emergency close ≤ 35 mph [15.6 m/s] gust; positive close against gust | simulate signal | Critical (safety) |
| Snow interlock (MANDATORY) | roof held CLOSED while snow-loaded — cannot be commanded open (snow-laden roll force 627 N [141 lbf] > drive) | simulate snow signal | Critical (safety) |
| Drive ↔ hold-down interlock | drive inhibited while a hold-down is engaged; hold-downs re-engage on close | function | Critical (safety) |

**Why the interlocks are mandatory (grounding).** The drive is **WIND-sized** — at 35 mph the wind is

**62%** of the 235 N tractive load, so a positive close against the gust is the governing requirement

(`MECHANICAL_DESIGN.md` §10). A **fully snow-laden** roof needs **627 N [141 lbf]** to roll, which

**exceeds the ~500 N [112 lbf] drive**, so opening under snow is prohibited by interlock.

---

## 6. Hold-down proof-pull test (NW-RR-006 — MANDATORY / REMEDIATION)

| Characteristic | Requirement | Method | Class |
| --- | --- | --- | --- |
| Anchor count | 4 hold-downs installed & interlocked | visual | Critical |
| Proof load per anchor | ≥ 2 klbf [8.9 kN] (PE to set the proof value) | calibrated hydraulic pull / load cell | Critical |
| Group capacity vs demand | 4× ≥ 2 klbf = 35.6 kN [8 klbf] vs net uplift 7.4 kN [1.66 klbf] → SF 3.9 | calc + test | Critical |
| Anchorage (into enclosure foundation) | per ACI 318 Ch.17; embedment/edge PE-set | PE field inspection | Critical |
| No slip / no concrete cone / no bracket yield at proof | pass | observe + measure | Critical |

**Grounding.** Survival-wind proof (`MECHANICAL_DESIGN.md` §7): **gross roof uplift 9.2 kN

[2.06 klbf]** vs **1.8 kN [397 lbf]** self-weight → **SF 0.19 FAIL**; the **4× hold-downs restore

SF 3.9**. This is the **REMEDIATION** and is **not** value-engineerable out. Anchors land in the

**enclosure/building foundation** (the pier is isolated — README §4).

---

## 7. Weatherproofing (roof-closed water test)

| Characteristic | Requirement | Method | Class |
| --- | --- | --- | --- |
| Roof-closed rain test | no ingress at panel laps, ridge/edge flashing, perimeter gasket | spray/hose test | Major |
| Drainage / weeps | closed roof sheds water; no ponding | visual under test | Major |
| Wall-top weather seal | roof lands on and seals to the wall-top | visual + water test | Major |

---

## 8. Sampling, documentation & sign-off

Critical characteristics (frame square/diagonal, rail gauge/straightness/splice, drive travel +

all safety interlocks, hold-down proof, critical welds J3/J5/J6) receive 100% inspection.

Major / Minor verified to ISO 2768 / drawing on the acceptance record.

The bidder shall deliver:

CWI weld report — VT + MT/PT/UT results keyed to the as-built weld_map.md, with dispositions.

WPS / PQR / WPQ records (AWS D1.1).

Material & galvanize certs (A500 Gr B, A36, A123 coating record).

Frame + rail dimensional survey (square, diagonal, gauge, straightness, splice flushness).

Drive-cycle + interlock commissioning report (travel, time, tractive load, wind + snow + hold-down interlocks, safeties).

Hold-down proof-pull record (each anchor, proof load, SF).

Weatherproofing (water) test record.

PE field hold-point sign-offs (fit-up, weld, galvanize, anchor set, commissioning) + stamped drawings.

RFI / nonconformance dispositions for every ASSUMED value.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Bidder QA |  |  |  |
| CWI (weld) |  |  |  |
| Owner / PE review |  |  |  |

---

## 9. ASSUMED-value register (do NOT treat as final)

| # | ASSUMED acceptance value | Part(s) / joint(s) |
| --- | --- | --- |
| 1 | All weld sizes & the NDE method/extent (VT/MT/PT/UT %) | all welds (weld_map.md) |
| 2 | Member sizes the dimensional checks verify against | NW-RR-001/-002/-003 |
| 3 | Rail level / co-planarity limit | NW-RR-003 |
| 4 | Drive rating (→ the SF ≥ 2.0 gate) & interlock thresholds/logic | NW-RR-005 / NW-CO-011 |
| 5 | Hold-down proof load & anchorage (embedment/edge, ACI 318 Ch.17) | NW-RR-006 |
| 6 | Wheel axle / wheel rating (≥4× wheel share) | NW-RR-004 / NW-CO-010 |
| 7 | Weatherproofing detail & water-test method | roof / NW-CO-012 |
| 8 | Galvanize vent/drain + field-repair (A780) acceptance | all steel |
| 9 | Bracket GD&T / surface-finish acceptance values | NW-RR-004/-005/-006 |

</content>

# BP-04 — Weld Map / Joint Schedule (Roll-off Roof)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-04 — Roll-off roof ("disappearing turret") |
| Welding standard | AWS D1.1 (structural steel; WPS/PQR + welder qualification WPQ) |
| Symbol standard | AWS A2.4 (weld & NDE symbols) |
| Base metals | ASTM A500 Gr B HSS (frame/purlins); ASTM A36 (rail beams, brackets) |
| Finish | Hot-dip galvanize per ASTM A123 (weld before galvanizing) |
| Issue date / rev | 2026-08-06 / A |

This joint schedule enumerates the weld groups of BP-04, the AWS A2.4 weld symbol to apply, the

joint type, the ASSUMED weld size, the process, and the NDE. It is read with SOW.md and

acceptance.md, and it is marked up as-built by the fabricator for the CWI report.

**⚠ ALL WELD SIZES AND JOINT TYPES BELOW ARE ASSUMED DESIGN-INTENT — PE/CWI TO CONFIRM.** No weld

leg, throat, or CJP/PJP designation herein is a released value. The PE/CWI shall size each weld per

the **AWS D1.1 minimum-fillet-weld tables** (governed by the **thinner part joined** — HSS walls are

3.2 mm [0.125 in]/4.0 mm [0.157 in]; brackets 9.5 mm [0.375 in]/12.7 mm [0.500 in]) and the PE's

computed member forces for the **ASCE 7 snow (10.8 kN [2.42 klbf]) and survival-wind (9.2 kN

[2.06 klbf] uplift)** cases. Prequalified WPS per AWS D1.1 are acceptable where applicable.

---

## 1. AWS A2.4 symbol legend (as used in this schedule)

| Symbol (text form) | AWS A2.4 meaning |
| --- | --- |
| ▷ fillet | Fillet weld; leg size to the left of the symbol (e.g. 6▷ = 6 mm leg). |
| ▷ (both sides) | Fillet weld both sides of the joint (symbol on both sides of the reference line). |
| V / CJP | Complete-joint-penetration groove weld (bevel/V), full throat. |
| PJP | Partial-joint-penetration groove weld; effective throat specified. |
| ○ weld-all-around | Weld-all-around flag at the reference-line elbow (perimeter joint). |
| ▶ field weld | Field-weld flag (filled triangle at the elbow) — welds made at site, not in shop. |
| Tail (VT), (MT), (PT), (UT) | NDE method called in the symbol tail (visual / mag-particle / dye-penetrant / ultrasonic). |

*(Rendered on the PDF control drawings and the STEP/weldment model as true AWS A2.4 graphic symbols;

the text forms above are the Markdown transcription.)*

---

## 2. Joint schedule

| Joint | Location / parts joined | Joint type | AWS A2.4 symbol (ASSUMED size) | Process (ASSUMED) | NDE (ASSUMED extent) | Criticality |
| --- | --- | --- | --- | --- | --- | --- |
| J1 | Frame corners — NW-RR-001 HSS-to-HSS mitred corners + corner gussets | Mitred T/corner, fully welded + gusset | ○ weld-all-around, CJP or 5▷ fillet all-around (VT) | GMAW / FCAW | VT 100% + MT 25% | High (frame integrity) |
| J2 | Purlin-to-frame — NW-RR-002 → NW-RR-001 (5 T-joints) | HSS-to-HSS T-joint | 5▷ (both sides) fillet (VT) *(bolted clip alt. permitted)* | GMAW / FCAW | VT 100% | Medium (snow path) |
| J3 | Wheel-bracket-to-frame — NW-RR-004 → NW-RR-001 (8×) | Plate-to-HSS, gusseted | 6▷ (both sides) fillet (VT)(MT) | GMAW / FCAW | VT 100% + MT 100% | CRITICAL (carries roof + snow into wheels) |
| J4 | Drive-bracket-to-frame — NW-RR-005 → NW-RR-001 (drive mount) | Plate-to-HSS, gusseted | 6▷ (both sides) fillet (VT) | GMAW / FCAW | VT 100% + MT 25% | Medium (drive reaction) |
| J5 | Hold-down bracket welds — NW-RR-006 → frame/roof structure (4×) | Plate-to-HSS/plate, gusseted | CJP or 8▷ (both sides) fillet (VT)(MT) | GMAW / FCAW / SMAW | VT 100% + MT 100% (UT if CJP) | CRITICAL — REMEDIATION (survival-wind uplift) |
| J6 | Rail splices — NW-RR-003 box-track length-to-length (if spliced) | Butt joint, running surface | CJP groove, backing, ground flush on wheel path (VT)(PT) | GMAW / SMAW | VT 100% + PT 100% (UT per PE) | CRITICAL (wheel running surface) |
| J7 | End stops — stop blocks → NW-RR-003 rail ends / NW-RR-005 (4×) | Plate/block-to-rail | 6▷ fillet, weld-all-around (VT) | GMAW / FCAW | VT 100% | Medium (impact) |
| J8 | Rail-to-support / foundation connection — NW-RR-003 → rail support | Plate-to-HSS or bolted | 6▷ (both sides) fillet (VT) or ASTM A574 bolting | GMAW / FCAW / bolt | VT 100% (torque check if bolted) | High (rail reactions) |
| J9 | Corner gussets / stiffeners — gusset plates at J1/J3/J5 | Plate-to-HSS | 5▷ fillet, weld-all-around (VT) | GMAW / FCAW | VT 100% | Supports J1/J3/J5 |

Field vs shop. J1–J7 and J9 are shop welds (weld → inspect → galvanize). J8 and any hold-down

attachment made at site are field welds (▶ flag) — field-welded galvanized steel requires **galv

field-repair** per the bidder's approved procedure (ASTM A780, supplementary to the register).

---

## 3. Welding controls (AWS D1.1)

WPS / PQR / WPQ. Submit a Welding Procedure Specification for each joint/process/position,

supported by a Procedure Qualification Record (or invoke a prequalified WPS where AWS D1.1

allows), and Welder Qualification records (WPQ) for every welder before production welding.

Filler / preheat. Filler metal, preheat, and interpass temperatures per the qualified WPS

(matching A500/A36 base metals) — ASSUMED to the WPS; bidder to state.

Sequence & distortion. Weld the frame (J1) and purlins (J2) with a sequence that holds the

frame-square 3 mm/m / diagonal 5 mm [0.197 in] tolerance (acceptance.md); back-gouge CJP roots

as required by the WPS.

Galvanizing interaction. Complete and inspect all shop welds before hot-dip galvanizing

(ASTM A123). Provide vent/drain holes for the bath on all closed HSS (locations ASSUMED — bidder

to detail, off stiffness-critical faces). Repair galvanize burned by field welds per §2 note.

CWI. An AWS Certified Welding Inspector performs/oversees the VT and the MT/PT/UT called

above and signs the weld report (acceptance.md).

---

## 4. ASSUMED-value register (this weld map)

| # | ASSUMED value | Joints | Status |
| --- | --- | --- | --- |
| 1 | Every fillet leg / throat size (5–8 mm shown) | J1–J9 | ASSUMED — PE/CWI per AWS D1.1 min-fillet tables |
| 2 | CJP vs PJP vs fillet choice at J1, J5, J6 | J1, J5, J6 | ASSUMED — PE to set from computed demand |
| 3 | NDE method + extent (VT/MT/PT/UT %) | all | ASSUMED — PE/CWI to set (critical joints 100%) |
| 4 | Welding process (GMAW/FCAW/SMAW) & filler/preheat | all | ASSUMED — per qualified WPS |
| 5 | Bolted vs welded alternative at J2, J8 | J2, J8 | ASSUMED — bidder option, PE to approve |
| 6 | Galv vent/drain-hole locations | HSS | ASSUMED — bidder to detail |
| 7 | Field-weld extent + galv repair (A780) | J8 + site | ASSUMED — bidder procedure |

</content>

# Part II — BP-05 cots schedule

# BP-05 — COTS Procurement Schedule (Buy-to-Print / Off-the-Shelf) — Buyer README

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-05 — COTS procurement schedule |
| Trade | Purchasing / integration (no fabrication; no fab control drawings) |
| Parts | NW-CO-001 … NW-CO-014 (14 catalogue line items; 0 fabrication drawings) |
| Branch / project | design/mechanical-tender — NIGHTWATCH Observatory Mount & Roll-off Tender |
| Issue date | 2026-08-06 |
| Revision | A |
| Governing TDP standard | MIL-STD-31000A (Technical Data Package) |

This README is the entry point for the purchasing agent / integrator bidding BP-05. It defines the

scope, the data package the buyer receives, the buyer deliverables, the **PROCUREMENT

GATE (mandatory design-remediation items), and the items carried as ASSUMED design-intent /

representative catalogue selections** the buyer must confirm. Read it with SCHEDULE.md (the purchase

table — item, part number, qty, key specs, supplier class + representative catalogue numbers) and

fastener_schedule.md (consolidated ASTM A574 SHCS + ASTM F1554 anchor buy) in this same folder.

BP-05 is a buy list, not a fabrication package — every line is COTS (drawing=False in the parts

registry; stock=('cots',)), so no NW-CO item carries a fabrication control drawing. Where a line

interfaces to a fabricated part (bearing seats, drive registers, wheel bores, anchor holes), the

mating dimension is fixed by the fabrication package (BP-01…BP-04) and repeated here for the

buyer's convenience — the buyer selects a catalogue item that fits that fixed interface.

---

## 0. PROCUREMENT GATE — READ FIRST (four items are MANDATORY design remediations)

**⚠ FOUR of the fourteen BP-05 lines are the physical embodiment of the design proof-out

remediations. They are NOT interchangeable with the cheaper baseline parts they replace. Buying the

baseline part instead re-opens a proof the design study recorded as FAIL.**

The trade study and proof modules (MECHANICAL_DESIGN.md §9, tradestudy/SECTION.md) disqualified the

repository's baseline component choices on four counts. BP-05 carries the remediated parts. These

four are the gate:

| # | Line | Remediation (buy this) | Replaces / fixes | Proof result |
| --- | --- | --- | --- | --- |
| 1 | NW-CO-003 / -004 | Angular-contact 7008 / 7006 super-precision pairs, back-to-back (DB) | deep-groove 6008 / 6006 | Bearing compliance was 98 % of the 43.5″ stiffness FAIL; angular-contact pairs restore moment stiffness. |
| 2 | NW-CO-005 | On-axis absolute encoder (BiSS-C ring, sub-arcsec), 2 off | motor-side-only encoding | Baseline 5.02″ RMS FAIL vs 1.0″ target; on-axis ring reaches 0.54″. |
| 3 | NW-CO-008 | Temperature-compensated focuser | passive (fixed) focus | 22 K night swing walks focus ~10× depth-of-focus. |
| 4 | NW-CO-013 | 48 V LiFePO4 battery pack (+ solar) | 12 V pack | 12 V gives 3.3 h vs 10 h night autonomy; 48 V gives 13.4 h. |

**Note on the 5th remediation.** The design study lists **five** proof-out remediations. The fifth —

the **4× survival-wind hold-down anchors (survival uplift 9.2 kN → SF 3.9)** — is a **fabricated

steel item, NW-RR-006, and lives in BP-04**, not here. Its anchor bolts are captured in

`fastener_schedule.md` (ASTM F1554) for a consolidated buy, but the brackets themselves are BP-04

scope. BP-05 therefore carries **4 of the 5 remediations**.

Gate rule. NW-CO-003, NW-CO-004, NW-CO-005 and NW-CO-008 are MANDATORY for the buildable v1.

NW-CO-013 (48 V pack) is MANDATORY only for the off-grid v2; v1 may run grid + UPS (see the

roadmap, MECHANICAL_DESIGN.md §9). A bid that substitutes a baseline part for any of the four v1

remediations shall be raised as an RFI/deviation and is not accepted without engineering sign-off.

Optional line. NW-CO-009 counterweights are OPTIONAL — the selected topology is the

counterweight-FREE GEM (torque proof SF 2.5/2.6; deletes 15.4 kg + 29 % RA inertia). Buy the

counterweight set only if the counterweighted variant is elected. See §6.

---

## 1. Scope

BP-05 covers every purchased (off-the-shelf) component in the NIGHTWATCH mount + roll-off

enclosure that is not fabricated under BP-01…BP-04. The buyer:

Procures the drivetrain — the two Harmonic Drive LLC strain-wave gears (NW-CO-001 RA,

NW-CO-002 DEC), the two NEMA17 + 27:1 planetary stepper packages (NW-CO-006), and the two

microstepping drivers / controller (NW-CO-007).

Procures the four v1 remediation items — the angular-contact bearing pairs (NW-CO-003 7008,

NW-CO-004 7006), the on-axis absolute encoders (NW-CO-005), and the temperature-compensated

focuser (NW-CO-008). See §0.

Procures the enclosure motion + weather hardware — V-groove track wheels (NW-CO-010), the

roll-off roof drive / gate operator (NW-CO-011), and the metal roofing panel + flashing (NW-CO-012).

Procures the power system — the 48 V LiFePO4 battery pack + solar (NW-CO-013), mandatory for

off-grid v2.

Consolidates the fastener buy — ASTM A574 socket-head cap screws and ASTM F1554 anchor bolts

across all packages (NW-CO-014 → fastener_schedule.md).

Optionally procures the cast-iron counterweight set (NW-CO-009) if the counterweighted variant

is bid.

Delivers manufacturer certificates of conformance (CoC), datasheets, and interface confirmations

(bearing precision class, encoder protocol, drive bore/torque) so each buy is traceable against the

fixed fabricated interfaces.

Out of scope for BP-05 (the fabricated parts these items bolt into — separate packages):

| Interface | Fabricated under | BP-05 item that mates to it |
| --- | --- | --- |
| RA / DEC axis housings, bearing seats, drive registers | BP-01 (machining) | NW-CO-001/-002 drives; NW-CO-003/-004 bearings; NW-CO-005 encoders |
| RA / DEC drive spindles (carry bearing inner races, couple the strain-wave gears) | BP-02 (turned parts) | NW-CO-001/-002 drives; NW-CO-003/-004 bearings |
| Pier / adapter plate | BP-03 (pier) | NW-CO-014 anchors (F1554) via fastener_schedule.md |
| Roll-off roof frame, rails, wheel brackets, drive bracket, wind hold-downs | BP-04 (roll-off) | NW-CO-010 wheels; NW-CO-011 drive; NW-CO-012 roofing; F1554 hold-down anchors |

---

## 2. Data package the buyer receives (per MIL-STD-31000A)

| Item | Format / standard | Role |
| --- | --- | --- |
| SCHEDULE.md | Markdown | The purchase table: item, NW-CO-xx, qty, key specs (from partspec), supplier CLASS + representative catalogue part numbers, remediation flags, per-item procurement notes. |
| fastener_schedule.md | Markdown | Consolidated ASTM A574 SHCS + ASTM F1554 anchor buy across BP-01…BP-04 interfaces. |
| cots_schedule.csv (rows NW-CO-001…-014, + NW-PF-004) | CSV / XLSX (BOM per ASME Y14.34) | Machine-readable buy list generated from the parts registry. |
| master_bom.csv (BP-05 rows) | CSV / XLSX | Roll-up into the full-project BOM. |
| Interface dimensions | Repeated in SCHEDULE.md from BP-01…BP-04 control drawings (PDF) + STEP AP242 solids | Fixed mating dims the catalogue part must satisfy (bearing bores/OD, drive bores, wheel bores, anchor holes). |

Order of precedence. For a purchased part the **manufacturer's datasheet governs the part's own

dimensions and ratings; the fixed fabricated interface (BP-01…BP-04 control drawing / STEP AP242

solid) governs the mating dimension the part must fit.** Where a catalogue part cannot meet a fixed

interface, the buyer raises an RFI before ordering — the interface is not changed to suit stock.

General tolerances of any buyer-detailed adapter per ISO 2768; fits per ISO 286 (bearing seats

H7 / journals j6 are set by BP-01/BP-02, not here). All representative catalogue numbers below are

"representative — confirm": they establish the class, rating, and interface, not a sole source.

---

## 3. Line-item summary (source: `partspec.parts_for('BP-05')`)

All 14 lines are COTS — no fabrication drawing, no stock mass. Key specs are quoted from the parts

registry (gen/partspec.py, traced to calc/params.py where marked SOURCED). Full specs, suppliers,

and representative catalogue numbers are in SCHEDULE.md.

| Part no. | Name | Qty | Headline spec (from partspec) | Class | Status |
| --- | --- | --- | --- | --- | --- |
| NW-CO-001 | Harmonic drive, RA | 1 | CSF-32-100-2A-GR — ratio 100, rated 127 Nm [93.7 lbf·ft], peak 343 Nm [253 lbf·ft], hollow bore Ø80.0 mm [3.150 in] | Strain-wave (sole-class) | Core |
| NW-CO-002 | Harmonic drive, DEC | 1 | CSF-25-80-2A-GR — ratio 80, rated 70 Nm [51.6 lbf·ft], peak 186 Nm [137 lbf·ft], hollow bore Ø64.0 mm [2.520 in] | Strain-wave (sole-class) | Core |
| NW-CO-003 | Angular-contact bearing 7008 (RA pair) | 2 | Bore Ø40 mm [1.575 in], OD Ø68 mm [2.677 in], width 15 mm [0.591 in], DB back-to-back | Super-precision ABEC-7 | REMEDIATION (v1 mandatory) |
| NW-CO-004 | Angular-contact bearing 7006 (DEC pair) | 2 | Bore Ø30 mm [1.181 in], OD Ø55 mm [2.165 in], width 13 mm [0.512 in], DB back-to-back | Super-precision ABEC-7 | REMEDIATION (v1 mandatory) |
| NW-CO-005 | On-axis absolute encoder (RA + DEC) | 2 | Resolution < 1″; interface BiSS-C / SSI | Absolute ring + readhead | REMEDIATION (v1 mandatory) |
| NW-CO-006 | Stepper NEMA17 + 27:1 planetary | 2 | 1.8° step, 27:1 planetary, Irun 1.5 A / Igoto 2.0 A, holding 0.45 Nm | Stepper + gearhead | Core |
| NW-CO-007 | Motor driver (TMC5160) / OnStepX board | 2 | Irun 1.5 A, Igoto 2.0 A, 16 microsteps | Microstepping driver | Core |
| NW-CO-008 | Temperature-compensated focuser | 1 | Temp coeff −2.5 steps/°C (ASSUMED) | Motorised absolute focuser | REMEDIATION (v1 mandatory) |
| NW-CO-009 | Counterweights (5 kg ×2, 2.5 kg ×1) | 3 | 12.5 kg total available; shaft Ø31.75 mm [1.250 in] × 457.2 mm [18.000 in] (BP-02) | Cast iron | OPTIONAL |
| NW-CO-010 | V-groove track wheels | 8 | Ø~4 in [~101.6 mm], ≥150 kg [≥331 lb] each | Steel V-groove | Core |
| NW-CO-011 | Roof drive (gate operator) | 1 | Move force 235 N [52.8 lbf], SF 2.1 vs ~500 N [112 lbf] drive; fail-safe + wind interlock | Sliding-gate operator | Core |
| NW-CO-012 | Metal roofing panel + flashing | 1 | Area ≈ 9.0 m² [≈96.9 ft²] (3.0 × 3.0 m) | Standing-seam / corrugated steel | Core |
| NW-CO-013 | 48 V LiFePO4 battery pack + solar | 1 | 48 V bus, ~5 kWh, 13.4 h autonomy | LiFePO4 + PV | REMEDIATION (v2 mandatory; v1 grid+UPS) |
| NW-CO-014 | Fastener schedule (SHCS, anchors) | 1 | ASTM A574 SHCS + ASTM F1554 Gr36 anchors — see fastener_schedule.md | Fastener buy | Core |

---

## 4. Cross-package interfaces the buyer must satisfy

Each purchased part fits a fixed fabricated feature. The buyer confirms the catalogue part meets

the mating dimension before ordering; the mating dimension is not adjustable to suit stock.

| BP-05 item | Fits (fixed by) | Fixed mating dimension |
| --- | --- | --- |
| NW-CO-001 (CSF-32) | RA housing drive register (NW-MH-001) + RA spindle (NW-TP-002) | Drive bore Ø80.0 mm [3.150 in]; wave-gen register; 8 × M4 on Ø104 mm [4.094 in] PCD |
| NW-CO-002 (CSF-25) | DEC housing drive register (NW-MH-002) + DEC spindle (NW-TP-003) | Drive bore Ø64.0 mm [2.520 in]; 8 × M4 on Ø83 mm [3.268 in] PCD |
| NW-CO-003 (7008 pair) | RA housing seat H7 (NW-MH-001) + RA journal j6 (NW-TP-002) | Seat bore Ø68 mm [2.677 in] H7; journal Ø40 mm [1.575 in] j6 |
| NW-CO-004 (7006 pair) | DEC housing seat H7 (NW-MH-002) + DEC journal j6 (NW-TP-003) | Seat bore Ø55 mm [2.165 in] H7; journal Ø30 mm [1.181 in] j6 |
| NW-CO-005 (encoder ring) | RA / DEC axis (on-axis, one per axis) | Ring bore to clear the axis; readhead standoff — ASSUMED, confirm to axis geometry |
| NW-CO-010 (V-groove wheels) | Wheel axle brackets (NW-RR-004), M16 axle | Wheel bore for M16 [Ø16 mm] axle; V-groove to match rail (NW-RR-003) |
| NW-CO-011 (roof drive) | Drive bracket (NW-RR-005) | Rack/chain mount; 180 kg [397 lb] roof; end-stop + wind interlock |
| NW-CO-012 (roofing) | Roof frame + purlins (NW-RR-001/-002) | ≈9.0 m² [≈96.9 ft²] skin; edge/ridge flashing to frame |
| F1554 anchors (fastener_schedule.md) | Pier top plate (NW-PF-002) + wind hold-downs (NW-RR-006) | 4 × Ø0.75 in [Ø19.05 mm] each group; PE to size final |

---

## 5. Buyer deliverables

Purchase orders placed against SCHEDULE.md and fastener_schedule.md, with the **four v1

remediation lines** (NW-CO-003/-004/-005/-008) confirmed as the remediated parts, not baseline.

Certificates of conformance (CoC) / datasheets for every line, and specifically:

Bearings (NW-CO-003/-004): **precision-class cert (≥ ABEC-7 / P4), DB-set matching cert, preload

class** — confirming they fit the H7 seats / j6 journals set by BP-01/BP-02.

Encoders (NW-CO-005): **BiSS-C (or SSI) protocol confirmation and accuracy/resolution

(sub-arcsec)** datasheet — confirming < 1″ on-axis.

Harmonic drives (NW-CO-001/-002): rated/peak torque, ratio, and hollow-bore datasheet —

confirming Ø80.0 / Ø64.0 mm bores and the 8 × M4 PCDs.

Roof drive (NW-CO-011): fail-safe behaviour + wind-interlock capability confirmation.

48 V pack (NW-CO-013): capacity (kWh), 48 V bus, cell chemistry (LiFePO4), safety listing.

Interface-fit confirmation — a short matrix confirming each catalogue part meets the fixed

mating dimension in §4 (raise an RFI where it does not).

Fastener CoC — ASTM A574 SHCS mill cert / CoC and ASTM F1554 Gr36 anchor mill cert +

galvanize (ASTM A123) cert, per fastener_schedule.md.

Deviation / RFI log — every representative catalogue number confirmed to an actual ordered part,

and every ASSUMED value (§6) resolved before order.

---

## 6. ASSUMED design-intent / representative selection — buyer & PE to confirm (NOT final)

Carried as ASSUMED design-intent or representative catalogue selection in the parts registry;

not released procurement decisions. Confirm before ordering:

All representative catalogue part numbers in SCHEDULE.md (SKF/NSK/FAG bearings, Renishaw/

Heidenhain encoder, LiftMaster/US-Automatic gate operator, ZWO/Optec/Pegasus focuser, EG4/Battle-Born

48 V pack, DuraGates/CasterHQ wheels) are "representative — confirm". They fix the **class,

rating, and interface**, not a sole source. Buyer confirms availability, lead time, and fit.

On-axis encoder ring geometry & interface (NW-CO-005) — ring bore, readhead standoff, and

BiSS-C vs SSI are ASSUMED; confirm against the actual RA/DEC axis geometry and the OnStepX /

controller input.

Roof drive product & sizing (NW-CO-011) — the **gate-operator class, fail-safe mode, and wind

interlock are ASSUMED design-intent** (enclosure proof: 235 N [52.8 lbf] move force, SF 2.1);

the specific operator, its duty rating for the 180 kg [397 lb] roof, and the interlock logic are

PE/controls to confirm.

V-groove wheel product & rail match (NW-CO-010) — Ø4 in [101.6 mm], ≥150 kg [≥331 lb]/wheel is

ASSUMED; confirm the V-profile matches the BP-04 box-track section (NW-RR-003) and the ≥4× load

factor on the 180 kg roof + snow.

Roofing panel type/gauge & flashing (NW-CO-012) — standing-seam vs corrugated, gauge, and

fastening are ASSUMED; confirm against the ASCE 7 snow/wind case and the purlin spacing (BP-04).

48 V pack sizing / v1 vs v2 (NW-CO-013) — ~5 kWh / 13.4 h autonomy is ASSUMED; the DGX duty

cycle drives ~59 % of the load. v1 may run grid + UPS; the pack is **mandatory only for off-grid

v2**.

Temp-comp focuser coefficient & coupling (NW-CO-008) — the −2.5 steps/°C coefficient is

ASSUMED; confirm the focuser couples to the OTA drawtube and the temperature-compensation curve

against the 22 K night swing.

Motor + gearhead + driver products (NW-CO-006/-007) — NEMA17 1.8° + 27:1 planetary + TMC5160 /

OnStepX are SOURCED for ratings (P.MOTOR) but the **specific catalogue motor, gearhead, and

controller board are representative** — confirm.

Counterweights are OPTIONAL (NW-CO-009) — omitted in the counterweight-FREE build; buy only if

the counterweighted variant is elected.

Fastener grades, lengths, and torque (NW-CO-014) — ASTM A574 SHCS and ASTM F1554 Gr36 grades

are ASSUMED design-intent; **lengths, quantities, and preload/torque are ASSUMED and are

bidder/PE to confirm (weld sizes and any structural anchor sizing are PE** items). See

fastener_schedule.md.

---

## 7. References

Parts registry: design/mechanical/tender/gen/partspec.py → parts_for('BP-05') (single source of truth).

BOM / COTS: design/mechanical/tender/bom/{cots_schedule,master_bom}.csv.

Design basis: design/mechanical/MECHANICAL_DESIGN.md §9 (selected configuration, cost deltas, the

5 remediations, v1/v2 roadmap); design/mechanical/tradestudy/SECTION.md (drive/encoder/bearing/

enclosure/power selection rationale, disqualification gate).

Interfaces: BP-01 (../BP-01_mount_machining/), BP-02 (../BP-02_turned_parts/),

BP-03 (../BP-03_pier_foundation/), BP-04 (roll-off) — fixed mating dimensions.

Standards register: MIL-STD-31000A (TDP); ASME Y14.34 (associated lists/BOM), Y14.100, Y14.24,

Y14.1; ISO 286 (fits), ISO 2768 (general tolerances); ASTM A574 (SHCS), ASTM F1554 Gr36 (anchors),

ASTM A123 (galvanize). Encoder interface BiSS-C / SSI. Formats: STEP ISO 10303 AP242 (interface

solids), PDF (interface drawings), CSV/XLSX (BOM).

# BP-05 — COTS Procurement Schedule (Purchase Table)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Package | BP-05 — COTS procurement schedule |
| Source of truth | partspec.parts_for('BP-05') (14 lines) + bom/cots_schedule.csv |
| Issue date / Rev | 2026-08-06 / A |
| TDP / BOM standards | MIL-STD-31000A; ASME Y14.34 (associated lists / BOM) |

How to read this schedule. Every line is COTS (buy, no fabrication drawing). *Key specs* are quoted

from the parts registry (SOURCED = traced to calc/params.py; ASSUMED = design-intent, confirm).

*Supplier class* is the component class the design requires. *Representative catalogue part no.* is a

real part that meets the class/rating/interface — "representative, confirm", established via a short

supplier search; it is not a sole source and the buyer confirms availability, lead time, and fit.

Dual units throughout: mm primary, inch in brackets. Bold "REMEDIATION" = a mandatory design

proof-out fix (see §0 of README.md). Fasteners (NW-CO-014) are broken out in fastener_schedule.md.

---

## A. Purchase table

| # | NW-CO | Item | Qty | Key specs (from partspec) | Supplier CLASS | Representative catalogue part no. — *confirm* | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | NW-CO-001 | Harmonic drive, RA | 1 | Ratio 100; rated 127 Nm [93.7 lbf·ft]; peak 343 Nm [253 lbf·ft]; hollow bore Ø80.0 mm [3.150 in] *(SOURCED P.RA_DRIVE)*; backlash ≤1.0 arcmin | Strain-wave gear | Harmonic Drive LLC CSF-32-100-2A-GR *(registry designation = mfr part; sole-class)* | Core |
| 2 | NW-CO-002 | Harmonic drive, DEC | 1 | Ratio 80; rated 70 Nm [51.6 lbf·ft]; peak 186 Nm [137 lbf·ft]; hollow bore Ø64.0 mm [2.520 in] *(SOURCED P.DEC_DRIVE)*; backlash ≤1.0 arcmin | Strain-wave gear | Harmonic Drive LLC CSF-25-80-2A-GR *(registry designation = mfr part; sole-class)* | Core |
| 3 | NW-CO-003 | Angular-contact bearing 7008 (RA pair) | 2 | Bore Ø40 mm [1.575 in]; OD Ø68 mm [2.677 in]; width 15 mm [0.591 in]; DB back-to-back; 15° contact; ABEC-7/P4 | Super-precision angular-contact ball bearing | SKF 7008 CD/P4A (universal-match: 7008 CDGA/P4A for factory DB set); equiv NSK 7008A5TYNSULP4 / FAG HCB7008-E-T-P4S | REMEDIATION — v1 mandatory |
| 4 | NW-CO-004 | Angular-contact bearing 7006 (DEC pair) | 2 | Bore Ø30 mm [1.181 in]; OD Ø55 mm [2.165 in]; width 13 mm [0.512 in]; DB back-to-back; 15° contact; ABEC-7/P4 | Super-precision angular-contact ball bearing | SKF 7006 CD/P4A (universal-match: 7006 CDGA/P4A); equiv NSK 7006A5 / FAG HCB7006 | REMEDIATION — v1 mandatory |
| 5 | NW-CO-005 | On-axis absolute encoder (RA + DEC) | 2 | Resolution < 1″ (on-axis); interface BiSS-C / SSI; corrects harmonic PE | Absolute angle ring + readhead | Renishaw RESOLUTE™ (BiSS-C) readhead + RESA30 rotary angle ring, 26-bit (0.02″ resolution); equiv Heidenhain RCN/ECA absolute ring | REMEDIATION — v1 mandatory |
| 6 | NW-CO-006 | Stepper motor NEMA17 + 27:1 planetary | 2 | Step 1.8°; planetary 27:1; Irun 1.5 A; Igoto 2.0 A; holding 0.45 Nm; 16 microsteps *(SOURCED P.MOTOR)* | Hybrid stepper + planetary gearhead | StepperOnline 17HS19-2004S1 + PG27 gearhead (equiv Oriental Motor PKP + gearhead) *— representative* | Core |
| 7 | NW-CO-007 | Motor driver (TMC5160) / OnStepX board | 2 | Irun 1.5 A; Igoto 2.0 A; 16 microsteps *(SOURCED P.MOTOR)* | Microstepping stepper driver + controller | Analog Devices/Trinamic TMC5160 on an OnStepX controller (e.g. MaxPCB / FYSETC) *— representative* | Core |
| 8 | NW-CO-008 | Temperature-compensated focuser | 1 | Temp coeff −2.5 steps/°C *(ASSUMED)*; motorised absolute; compensates Al-tube focus drift over 22 K swing | Motorised absolute focuser w/ temp probe | Optec TCF-S (true temp-comp); equiv ZWO EAF + temperature sensor or Pegasus Astro FocusCube v2 *— representative* | REMEDIATION — v1 mandatory |
| 9 | NW-CO-009 | Counterweights (5 kg ×2, 2.5 kg ×1) | 3 | 12.5 kg total available *(SOURCED P.COUNTERWEIGHTS)*; fits shaft Ø31.75 mm [1.250 in] (NW-TP-001, BP-02) | Cast-iron mount counterweight | Generic 1.25 in-bore cast-iron CW discs (e.g. ADM / ZWO CW set) *— representative* | OPTIONAL (CW-free build omits) |
| 10 | NW-CO-010 | V-groove track wheels | 8 | Ø~4 in [~101.6 mm]; ≥150 kg [≥331 lb] each; 4 per side; ≥4× on 180 kg roof + snow | Steel V-groove gate/track wheel | DuraGates 4″ galvanized V-groove wheel (≤~425 kg [~937 lb]/wheel) or CasterHQ V-track wheel *— representative* | Core |
| 11 | NW-CO-011 | Roof drive (gate operator) | 1 | Move force 235 N [52.8 lbf]; SF 2.1 vs ~500 N [112 lbf] drive; rack-and-pinion/chain; fail-safe + wind interlock | Commercial sliding-gate operator | LiftMaster SL3000UL (1/2 HP, ≤~454 kg [1000 lb], 15 m travel); equiv US Automatic Patriot RSL / Nice-Apollo *— representative* | Core |
| 12 | NW-CO-012 | Metal roofing panel + flashing | 1 | Area ≈ 9.0 m² [≈96.9 ft²] (3.0 × 3.0 m) *(SOURCED P.ENCLOSURE)*; weather skin + ridge/edge flashing + closures | Standing-seam / corrugated steel roofing | 24 ga standing-seam or corrugated galvanized/Galvalume panel + matching flashing/closures *(commodity — representative)* | Core |
| 13 | NW-CO-013 | 48 V LiFePO4 battery pack + solar | 1 | 48 V bus; ~5 kWh; 13.4 h autonomy (vs 12 V 3.3 h; night 10 h); DGX ≈59 % of load | 48 V LiFePO4 pack + PV/MPPT + hybrid inverter | EG4 LifePower4 V2 48 V 100 Ah (5.12 kWh) rack battery + 48 V hybrid inverter + PV array/MPPT; equiv Battle Born / SOK *— representative* | REMEDIATION — v2 mandatory (v1 grid+UPS) |
| 14 | NW-CO-014 | Fastener schedule (SHCS, anchors) | 1 | ASTM A574 SHCS + ASTM F1554 Gr36 anchors *(grades ASSUMED)* | Fastener buy (consolidated) | See fastener_schedule.md | Core |

---

## B. Per-item procurement notes

NW-CO-001 / -002 — Harmonic Drive LLC strain-wave gears (drivetrain core).

The registry designations CSF-32-100-2A-GR and CSF-25-80-2A-GR are the manufacturer part numbers

(SOURCED from P.RA_DRIVE.name / P.DEC_DRIVE.name), so the class is effectively sole-source to

Harmonic Drive LLC's CSF-2A series (second-source only if a proven equivalent hollow-bore strain-wave

unit of identical ratio/torque/bore is qualified). Confirm the hollow-bore variant (Ø80.0 /

Ø64.0 mm) and the output-flange bolt pattern against the RA/DEC spindles (8 × M4 on Ø104 / Ø83 mm PCD,

BP-02). Rated torque governs continuous tracking; peak governs slew/wind gust.

NW-CO-003 / -004 — angular-contact bearing pairs (REMEDIATION, v1 mandatory).

These replace the baseline deep-groove 6008 / 6006 whose compliance was 98 % of the 43.5″ stiffness

FAIL. Buy matched pairs mounted back-to-back (DB) for moment stiffness — either universal-match

(CDGA/P4A, arrange DB in assembly) or a factory-matched DB set. Precision class ≥ ABEC-7 / ISO P4.

Confirm bore/OD/width against the H7 housing seats (BP-01) and j6 spindle journals (BP-02): 7008 =

Ø40/Ø68/15 mm, 7006 = Ø30/Ø55/13 mm. Specify preload class and DB matching on the CoC. **Do not

substitute deep-groove** — it re-opens the stiffness FAIL.

NW-CO-005 — on-axis absolute encoder (REMEDIATION, v1 mandatory).

Closes the tracking loop on the axis so it corrects the harmonic gear's periodic error. Baseline

motor-side-only encoding was DISQUALIFIED at 5.02″ RMS (5× the 1.0″ gate); the on-axis ring reaches

0.54″. Buy an absolute angle ring + readhead with a BiSS-C (or SSI) serial interface and

sub-arcsecond accuracy/resolution (representative: Renishaw RESOLUTE + RESA30, 26-bit = 0.02″

resolution). Confirm the ring bore, readhead standoff, and interface against the actual RA/DEC axis

geometry and the OnStepX / controller input — these are ASSUMED, confirm. One per axis (×2).

NW-CO-006 / -007 — steppers + drivers (drivetrain core).

Ratings are SOURCED (P.MOTOR: 1.8° step, 27:1 planetary, Irun 1.5 A, Igoto 2.0 A, holding 0.45 Nm,

16 microsteps); the specific catalogue motor, gearhead, and controller board are **representative,

confirm. The planetary periodic error is mooted by the on-axis encoder** (NW-CO-005) — the servo

closes on the absolute ring for position and the motor encoder for velocity. TMC5160 on an OnStepX board

is the reference control stack.

NW-CO-008 — temperature-compensated focuser (REMEDIATION, v1 mandatory).

Passive (fixed) focus walks ~10× depth-of-focus over the 22 K night swing (thermal proof). Buy a

motorised absolute focuser with a temperature probe and a compensation curve (representative: Optec

TCF-S true temp-comp, or ZWO EAF + temp sensor, or Pegasus FocusCube v2). The −2.5 steps/°C

coefficient is ASSUMED — confirm against the as-built OTA and calibrate. Confirm mechanical coupling

to the OTA drawtube.

NW-CO-009 — counterweights (OPTIONAL).

The selected topology is the counterweight-FREE GEM (torque proof SF 2.5/2.6; deletes 15.4 kg +

29 % RA inertia; cost delta −$110). Buy only if the counterweighted variant is elected. If bought,

the 12.5 kg set (5 + 5 + 2.5 kg) rides the Ø31.75 mm [1.250 in] shaft NW-TP-001 (BP-02, itself optional).

NW-CO-010 — V-groove track wheels (enclosure motion core).

Eight wheels (4 per side) carry the 180 kg [397 lb] roof + snow on the BP-04 box track (NW-RR-003).

Ø~4 in [~101.6 mm], ≥150 kg [≥331 lb]/wheel rated (target ≥4× on the loaded roof — representative

DuraGates 4″ carries ~425 kg [~937 lb]/wheel, ample). Confirm the V-profile matches the rail section

and the axle bore fits the M16 axle of the wheel brackets (NW-RR-004, BP-04). ASSUMED, confirm.

NW-CO-011 — roof drive / gate operator (enclosure motion core).

Enclosure proof: 235 N [52.8 lbf] move force, SF 2.1 vs a ~500 N [112 lbf]-class drive. Buy a

commercial sliding-gate operator (rack-and-pinion or chain) rated for the 180 kg [397 lb] roof.

Must be fail-safe and interlocked with the wind system (no open above the gust limit; hold closed on

survival wind, coordinated with the NW-RR-006 hold-downs). Representative: LiftMaster SL3000UL. The

operator product, duty rating, and interlock logic are ASSUMED design-intent — PE/controls confirm.

NW-CO-012 — metal roofing panel + flashing (weather skin core).

Weatherproof skin over the roll-off frame, ≈9.0 m² [≈96.9 ft²] (SOURCED roof 3.0 × 3.0 m). Panel type

(standing-seam vs corrugated), gauge, and fastening are ASSUMED — confirm against the ASCE 7

snow/wind case and the purlin spacing (NW-RR-002, BP-04). Include **ridge/edge flashing, closures, and

gaskets** for a sealed roll-off joint.

NW-CO-013 — 48 V LiFePO4 battery pack + solar (REMEDIATION, v2 mandatory).

Power proof: a 12 V pack gives only 3.3 h vs the 10 h night; 48 V gives 13.4 h (DGX ≈59 % of the

load). Buy a 48 V LiFePO4 pack (~5 kWh) + solar array/MPPT + 48 V hybrid inverter for off-grid

autonomy. Mandatory only for the off-grid v2; v1 may run grid + UPS (MECHANICAL_DESIGN.md §9

roadmap). Representative: EG4 LifePower4 V2 48 V 100 Ah (5.12 kWh). Sizing ASSUMED — confirm against

the final load schedule and DGX duty cycle.

NW-CO-014 — fastener schedule.

Consolidated ASTM A574 SHCS + ASTM F1554 Gr36 anchor buy across BP-01…BP-04 → see

fastener_schedule.md. Grades are ASSUMED design-intent; lengths/quantities/torque are **ASSUMED,

bidder/PE to confirm; structural anchor sizing is a PE** item.

---

## C. Remediation & option roll-up (buyer checklist)

| Category | Lines | Rule |
| --- | --- | --- |
| v1 MANDATORY remediations | NW-CO-003, NW-CO-004, NW-CO-005, NW-CO-008 | Must be the remediated parts — no baseline substitution without engineering sign-off. |
| v2 MANDATORY remediation | NW-CO-013 | Off-grid autonomy only; v1 may run grid + UPS. |
| Core buy (build-critical) | NW-CO-001, -002, -006, -007, -010, -011, -012, -014 | Required for the v1 build; representative catalogue numbers to confirm. |
| OPTIONAL | NW-CO-009 | Counterweight-FREE build omits; buy only for the counterweighted variant. |
| 5th remediation (elsewhere) | NW-RR-006 (BP-04) | 4× wind hold-downs — fabricated steel, not BP-05; anchors captured in fastener_schedule.md. |

All representative catalogue part numbers are **"representative — confirm"**: they fix the class,

rating, and interface, not a sole source. Confirm availability, lead time, and fit against the fixed

BP-01…BP-04 interfaces (`README.md` §4) before placing any order; resolve every ASSUMED value via

RFI first.

# BP-05 / NW-CO-014 — Consolidated Fastener Schedule (SHCS + Anchors)

**ISSUED FOR BID / FOR PE REVIEW — NOT FOR CONSTRUCTION**

| Field | Value |
| --- | --- |
| Part | NW-CO-014 — Fastener schedule (consolidated buy across BP-01…BP-04) |
| Governing specs | ASTM A574 (alloy-steel socket-head cap screws), ASTM F1554 Gr36 (anchor bolts), ASTM A123 (galvanize, anchors) |
| Fits | ISO 286 (threaded fits), ISO 2768 (general) |
| Issue date / Rev | 2026-08-06 / A |

This schedule consolidates the threaded fasteners implied by the mating interfaces in the parts

registry (gen/partspec.py, key_dims_mm) into a single buy. The **fastener grades are ASSUMED

design-intent; thread sizes are derived from the fixed interfaces** (SOURCED where a key_dims

entry names them); and lengths, quantities, and torque are ASSUMED — bidder/PE to confirm against

the as-built grip lengths and the governing structural loads. **Weld sizes and any structural anchor

sizing are PE items** and are NOT fixed here.

Dual units throughout: mm primary, inch in brackets.

---

## 1. Socket-head cap screws — ASTM A574 (alloy steel, high-strength)

| Thread | Ø | Where used (interface) | Fixed by | Qty* | Length* | Status |
| --- | --- | --- | --- | --- | --- | --- |
| M4 | Ø4 mm [0.157 in] | RA spindle → CSF-32 output flange, 8 × M4 on Ø104 mm [4.094 in] PCD | NW-TP-002 / NW-MH-001 (SOURCED pattern) | 8 | ASSUMED | Core |
| M4 | Ø4 mm [0.157 in] | DEC spindle → CSF-25 output flange, 8 × M4 on Ø83 mm [3.268 in] PCD | NW-TP-003 / NW-MH-002 (SOURCED pattern) | 8 | ASSUMED | Core |
| M6 | Ø6 mm [0.236 in] | Pier adapter → RA housing, 4 × M6 (also RA housing corner holes ×4) | NW-PF-003 → NW-MH-001 (SOURCED pattern) | 4 | ASSUMED | Core |
| M8 | Ø8 mm [0.315 in] | DEC saddle clamp bar, 2 × M8 clamp screws | NW-MH-003 / NW-MH-002 (SOURCED pattern) | 2 | ASSUMED | Core |
| M12 | Ø12 mm [0.472 in] | Counterweight shaft stud end M12 × 40 + M12 safety-stop | NW-TP-001 (SOURCED) | 2 | 40 mm [1.575 in] stud | OPTIONAL (CW-free build omits) |
| M16 | Ø16 mm [0.630 in] | V-groove wheel axles, wheel-bracket bores (8 wheels) | NW-RR-004 (ASSUMED) | 8 | ASSUMED | Core *(axle/shoulder bolt — confirm type)* |

\* Quantities are the interface pattern counts; add make-up/spares. Lengths are ASSUMED — set from

the as-built grip (housing wall + flange stack + thread engagement) and confirm.

SHCS notes.

Grade. ASTM A574 (alloy steel, ~property class 12.9 equivalent) is the ASSUMED grade per the

standards register. Galvanic caution (ASSUMED, confirm): several joints land in **Type III

hardcoat-anodized 6061-T6 (BP-01) and passivated 303 SS** (BP-02); at those aluminium/stainless

interfaces the PE may elect stainless SHCS to ISO 3506 A2-70 / A4-70 in lieu of A574 to avoid

galvanic coupling, accepting the lower proof load. Confirm per joint.

Torque / preload. ASSUMED — set per fastener grade and joint (lubricated vs dry), bidder/PE to

specify. The M4 drive-flange screws are the precision-critical joints (they locate the strain-wave

output to the axis) — torque to a controlled value with thread-locker as required.

Finish. Plain/black-oxide A574 for interior joints; where exposed to weather use stainless or a

suitably plated screw — confirm.

---

## 2. Anchor bolts — ASTM F1554 Gr36 (galvanized per ASTM A123)

| Group | Ø | Embedment / projection | Where used | Fixed by | Qty | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Pier anchor set | Ø0.75 in [19.05 mm] | Embedment 304.8 mm [12.000 in]; projection 50.0 mm [1.969 in] | Cast into pier, carries the top plate | NW-PF-004 (BP-03) — cast via template | 4 | Core *(BP-03 buy line)* |
| Wind hold-down anchors | Ø0.75 in [19.05 mm] | ASSUMED (PE to size) | Clamp roof/enclosure against 9.2 kN survival uplift | NW-RR-006 (BP-04) — 4× hold-down brackets | 4 | REMEDIATION *(SF 3.9; each ≥2 klbf [≈8.9 kN])* |

Anchor notes.

The pier anchor set (4×) is procured under BP-03 as line NW-PF-004 and cast into the pier via a

setting template; it is repeated here so the F1554 buy can be consolidated. The **wind hold-down

anchors (4×) serve the enclosure/building foundation** (the pier is structurally isolated) and

belong to the BP-04 hold-down brackets NW-RR-006 (the 5th proof-out remediation).

PE GATE. Final anchor **diameter, grade, embedment, edge distance, and count are PE-sized per

ACI 318 Ch.17** for the governing wind/seismic uplift (bounding roof uplift ≈9.2 kN; each hold-down

≥2 klbf gives SF 3.9). The Ø0.75 in F1554 Gr36 values here are **ASSUMED design-intent — PE to

confirm and stamp** (see BP-03 README §0, the PE-STAMP gate).

Finish. Hot-dip galvanize per ASTM A123; supply mill cert / CoC + galvanize coating record

and the anchor proof/pull test per the BP-03 acceptance plan.

---

## 3. Not covered here (flagged)

Weld sizes / NDE (BP-03 top plate, BP-04 roof frame, rails, brackets) — **ASSUMED design-intent;

bidder/PE to confirm per AWS D1.1 (steel) / AWS D1.2 (aluminium), symbols per AWS A2.4**,

with WPS/PQR welder qualification. Not a fastener buy.

Roofing panel fasteners / closures (NW-CO-012) — supplied with the roofing system; type/spacing

ASSUMED, confirm to the ASCE 7 snow/wind case.

Rail-to-pier / rail-to-building bolting (NW-RR-003) — structural connection; PE to detail.

Leveling nuts, washers, grout, thread-locker — ASSUMED consumables; bidder to include.

---

## 4. Consolidated buy summary

| Spec | Sizes | Total pieces (interface count)* |
| --- | --- | --- |
| ASTM A574 SHCS | M4, M6, M8, (M12 optional), M16 | 8 + 8 + 4 + 2 + (2) + 8 = 32 (+ M12 ×2 optional) |
| ASTM F1554 Gr36 anchors, galv. A123 | Ø0.75 in [19.05 mm] | 8 (4 pier via NW-PF-004 + 4 hold-down via NW-RR-006) |

\* Interface counts only — add make-up, spares, and stack washers/nuts. All lengths, torque, final

grade selection (A574 vs stainless at galvanic joints), and structural anchor sizing are **ASSUMED

design-intent — bidder/PE to confirm.**